## Cover
UAT WALKTHROUGH
Business Unit Walkthrough Users
BRD-02 Operations Cashiering - sign-in IDs for the walkthrough
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-02
Version | 1.0
Date | 11 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Users | BIBS DEV environment: https://dev.brokerverse.cloud. Password: Issued separately by the iorta TechNXT Project Team | 11
Walkthrough script | The Cashiering steps of the walkthroughs and the walkthrough WT-E for the Business Unit (FRS Appendix K) | 21
Legend
Pass
Fail
Blocked
Environment: BIBS DEV environment: https://dev.brokerverse.cloud. Passwords: Issued separately by the iorta TechNXT Project Team; no password is written in this workbook.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Walkthrough Users, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Users | Persona | Business role of the FRS
Users | User name | As shown on the screens
Users | Sign-in ID | User ID to type on the Login page
Users | Group profile | Role held
Users | Company / branch / unit
Users | What the user does in the walkthrough
Users | Menu path to start
Users | Menus the user should see | Cashiering entries of the user's menu (Figure of Appendix E)
Users | Walkthrough steps | Steps of the sheet Walkthrough script
Users | Password | Never written here
Walkthrough script | Walkthrough
Walkthrough script | Step
Walkthrough script | Persona
Walkthrough script | Sign-in ID
Walkthrough script | Screen | Screen of Appendix E
Walkthrough script | Action
Walkthrough script | Expected result
Walkthrough script | Result |  | Not run, Pass, Fail, Blocked
Walkthrough script | Done by
Walkthrough script | Date
Walkthrough script | Remarks

## Users
Users
BIBS DEV environment: https://dev.brokerverse.cloud. Password: Issued separately by the iorta TechNXT Project Team
Persona | User name | Sign-in ID | Group profile | Company / branch / unit | What the user does in the walkthrough | Menu path to start | Menus the user should see | Walkthrough steps | Password
Processing (books the accounts) | Paolo Processor | proc | Processing | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Processing | Books the account on New Business; the invoice then reaches Operations | Client & Policy › Booking › Booking Workbench | No Cashiering menu entry; the menus of the user's own team | WT-A.1 | Issued separately by the iorta TechNXT Project Team
Cashier | Carmela Cashier | cashier | Cashiering (HO / branch) | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Operations - Cashiering | Receives payments, issues ARs (branch) and ORs (HO), uploads payment files, requests cancellations and reinstatements, assigns dispositions, prints | Operations › Operations › Invoice Search | Operations › Operations › Operations Home; Operations › Operations › Invoice Search; Cashiering › Cashiering Workbench; Cashiering › Create AR/OR; Cashiering › Posting; Cashiering › Receive Payment; Cashiering › Receipts; Cashiering › Unapplied Payments; Cashiering › Unapplied Payment List; Cashiering › Day-End List; Cashiering › Search Log; Cashiering › Incoming Requests; Cashiering › Pre-booked Payments; Cashiering › Payment Uploads; Cashiering › Payment Files; Cashiering › PDC Warehouse; Cashiering › Batch Print; Cashiering › Commission ORs; Cashiering › Settlement ORs; Cashiering › AR and OR Forms; Cashiering › Receipt Series; Cashiering › Cashiering Setup; Operations › Operations › Report Archive; Reports › Reports › Report Centre; Operations › Operations › Notification Settings | WT-A.2, WT-A.3, WT-A.4, WT-B.8, WT-D.3, WT-E.2, WT-E.3, WT-E.4, WT-E.5, WT-E.7, WT-E.9, WT-E.10 | Issued separately by the iorta TechNXT Project Team
Cashier | Benjie Branch Cashier | cashbr | Cashiering (HO / branch) | BDO Insurance and Reinsurance Brokers, Inc. / Cebu Branch / Operations - Cashiering | Receives payments, issues ARs (branch) and ORs (HO), uploads payment files, requests cancellations and reinstatements, assigns dispositions, prints | Finance › Cashiering › Receive Payment | Operations › Operations › Operations Home; Operations › Operations › Invoice Search; Cashiering › Cashiering Workbench; Cashiering › Create AR/OR; Cashiering › Posting; Cashiering › Receive Payment; Cashiering › Receipts; Cashiering › Unapplied Payments; Cashiering › Unapplied Payment List; Cashiering › Day-End List; Cashiering › Search Log; Cashiering › Incoming Requests; Cashiering › Pre-booked Payments; Cashiering › Payment Uploads; Cashiering › Payment Files; Cashiering › PDC Warehouse; Cashiering › Batch Print; Cashiering › Commission ORs; Cashiering › Settlement ORs; Cashiering › AR and OR Forms; Cashiering › Receipt Series; Cashiering › Cashiering Setup; Operations › Operations › Report Archive; Reports › Reports › Report Centre; Operations › Operations › Notification Settings | WT-E.8 | Issued separately by the iorta TechNXT Project Team
Cashiering Team Leader / Head | Cecilia Cashiering Lead | cashtl | Cashiering Team Leader / Head | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Operations - Cashiering | Approves cancellations, reinstatements and dispositions; maintains receipt series | Finance › Cashiering › Unapplied Payments | Operations › Operations › Operations Home; Operations › Operations › Invoice Search; Cashiering › Cashiering Workbench; Cashiering › Create AR/OR; Cashiering › Posting; Cashiering › Receive Payment; Cashiering › Receipts; Cashiering › Unapplied Payments; Cashiering › Unapplied Payment List; Cashiering › Day-End List; Cashiering › Search Log; Cashiering › Incoming Requests; Cashiering › Pre-booked Payments; Cashiering › Payment Uploads; Cashiering › Payment Files; Cashiering › PDC Warehouse; Cashiering › Batch Print; Cashiering › Commission ORs; Cashiering › Settlement ORs; Cashiering › AR and OR Forms; Cashiering › Receipt Series; Cashiering › Cashiering Setup; Operations › Operations › Report Archive; Reports › Reports › Report Centre; Operations › Operations › Notification Settings | WT-B.9, WT-D.4, WT-E.1, WT-E.6 | Issued separately by the iorta TechNXT Project Team
Marketing Collection | Miguel Marketing Collection | mktcoll | Marketing Collection (HO / branches) | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Marketing - Collection | Hold and special remittance requests; the PR 2307 reversal from tagging to routing to Disbursement; endorsement requests, corrections of returned requests, slips and supporting documents | Client & Policy › Adjustment › New Request | Operations › Operations › Operations Home; Operations › Operations › Invoice Search; Cashiering › Cashiering Workbench; Cashiering › Unapplied Payment List; Cashiering › Search Log; Operations › Operations › Report Archive; Reports › Reports › Report Centre; Operations › Operations › Notification Settings | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team
Remittance Team Leader / Head | Rosario Remittance Lead | remittl | Remittance Team Leader / Head | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Operations - Remittance | Approves batches and special remittances; maintains incentive rules; assigns work | Finance › Remittance › Remittance Batches | No Cashiering menu entry; the menus of the user's own team | WT-A.7 | Issued separately by the iorta TechNXT Project Team
Commission Receivables Handler | Corazon Commission | commrec | Commission Receivables Handler | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Operations - Commission Receivables | DP entries from the tagging, read-only review, billing and SOA outputs, answers and account status, ageing, collection; BIR certificate submissions | Finance › Commission Receivables › DP Billings | Operations › Operations › Operations Home; Operations › Operations › Invoice Search; Cashiering › Search Log; Operations › Operations › Report Archive; Reports › Reports › Report Centre; Operations › Operations › Notification Settings | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team
Disbursement | Dante Disbursement | disb | Disbursement | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Disbursement | Works the Disbursement queue: acknowledge, DV number, paid, return; receives and releases the BIR 2307 certificates | Operations › Operations › Disbursement Queue | Operations › Operations › Operations Home; Operations › Operations › Invoice Search; Cashiering › Search Log; Operations › Operations › Disbursement Queue; Operations › Operations › Report Archive; Reports › Reports › Report Centre; Operations › Operations › Notification Settings | WT-B.10 | Issued separately by the iorta TechNXT Project Team
Comptrollership | Consuelo Comptroller | comptrol | Comptrollership | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Comptrollership | Acknowledges BIR certificates; views journals and reports | Finance › General Ledger › Journals | Operations › Operations › Operations Home; Operations › Operations › Invoice Search; Cashiering › Search Log; Operations › Operations › Report Archive; Reports › Reports › Report Centre; Operations › Operations › Notification Settings | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team
System Administrator | SIT System Administrator | admin | System Administrator | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / IT - System Administration | Interfaces (flow-in feeds), parameters and lists (section 9) | Operations › Operations › Interfaces | Operations › Operations › Operations Home; Operations › Operations › Invoice Search; Cashiering › Search Log; Operations › Operations › Interfaces; Operations › Operations › Report Archive; Reports › Reports › Report Centre; Operations › Operations › Notification Settings | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team
Auditor | Audrey Auditor | auditor | Auditor | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Internal Audit | Read access to Operations and reports | Reports › Reports › Report Centre | Operations › Operations › Operations Home; Operations › Operations › Invoice Search; Cashiering › Search Log; Operations › Operations › Report Archive; Reports › Reports › Report Centre; Operations › Operations › Notification Settings | WT-E.11 | Issued separately by the iorta TechNXT Project Team

## Walkthrough script
Walkthrough script
The Cashiering steps of the walkthroughs and the walkthrough WT-E for the Business Unit (FRS Appendix K)
Walkthrough | Step | Persona | Sign-in ID | Screen | Action | Expected result | Result | Done by | Date | Remarks
WT-A | WT-A.1 | Processing (New Business) | proc | New Business screen | Opens the account from Ready to Book, checks the invoice and the journal preview and clicks Book Account | The Booked Invoice with its invoice number; the invoice is copied into the Operations ledger Booked | Not run
WT-A | WT-A.2 | Cashier (Head Office) | cashier | Invoice Search (E.24) | Searches the ARN on Invoice Search | The new invoice with its gross premium, outstanding premium, Unpaid and With Outstanding Balance In the ledger | Not run
WT-A | WT-A.3 | Cashier (Head Office) | cashier | Receive Payment (E.5) | Opens Receive Payment, enters the ARN, the payor, the amount paid and the payment date, and checks the preview | Application Preview: Booked, the invoice with each component and the amount applied to it, Excess to Unapplied 0.00 Preview | Not run
WT-A | WT-A.4 | Cashier (Head Office) | cashier | Receipt (E.7) | Clicks Issue AR and Apply | Message: <AR> issued and applied to 1 invoice(s); the receipt opens with its application by component AR issued and applied | Not run
WT-A | WT-A.7 | Remittance Team Leader | remittl | Remittance Batch | Opens the batch from For Approval and clicks Approve and Push | The batch is Approved - with Disbursement with its payment request and the commission OR Approved | Not run
WT-B | WT-B.8 | Cashier (Head Office) | cashier | Unapplied Payment (E.9) | Opens the unapplied payment left by the re-application, assigns a refund to the client and submits it | The disposition is For Approval Refund for approval | Not run
WT-B | WT-B.9 | Cashiering Team Leader / Head | cashtl | Unapplied Payment (E.9) | Opens the unapplied payment and clicks Approve | The disposition is Completed and the balance 0.00; the refund is sent to Disbursement Refund approved | Not run
WT-B | WT-B.10 | Disbursement | disb | Disbursement Queue | Opens the Disbursement Queue | The refund request to the client in To Acknowledge Refund with Disbursement | Not run
WT-D | WT-D.3 | Cashier (Head Office) | cashier | Receipt (E.7) | Opens a receipt, clicks Cancel Receipt, chooses the reason and submits the cancellation | The receipt shows the cancellation For Approval in its workflow header Cancellation requested | Not run
WT-D | WT-D.4 | Cashiering Team Leader / Head | cashtl | Receipt (E.7) | Opens the receipt and clicks Approve and Post | The receipt is Cancelled; its unapplied balance is closed Cancelled | Not run
WT-E | WT-E.1 | Cashiering Team Leader / Head | cashtl | Receipt Series (E.20) | Opens Receipt Series and reads the AR series of Head Office and Cebu and the OR series of Head Office | Each series with its prefix, range, numbers left, ATP number and warning level; OR series for Head Office only Series checked | Not run
WT-E | WT-E.2 | Cashier (Head Office) | cashier | Payment Uploads (E.13) | Opens Payment Uploads, chooses Bills Payment and uploads the file of the UAT data | The run summary with the applied, unapplied, pre-booked, excess and failed rows; the run report to download File processed | Not run
WT-E | WT-E.3 | Cashier (Head Office) | cashier | Pre-booked Payments (E.12) | Opens Pre-booked Payments and clicks Re-match Now on the payment of the run | The payment waits for the booking of its account, or is applied if the account is now booked Pre-booked followed | Not run
WT-E | WT-E.4 | Cashier (Head Office) | cashier | PDC Warehouse (E.15) | Opens PDC Warehouse and adds a post-dated check with its maturity date | The check in the warehouse with its number and maturity date Check warehoused | Not run
WT-E | WT-E.5 | Cashier (Head Office) | cashier | Unapplied Payments (E.8) | Opens Unapplied Payments, the excess of the run, assigns a Refund and submits it | The disposition is For Approval Disposition submitted | Not run
WT-E | WT-E.6 | Cashiering Team Leader / Head | cashtl | Unapplied Payment (E.9) | Opens the Unapplied payment and clicks Approve | The disposition is approved and the refund request is in the Disbursement queue Refund requested | Not run
WT-E | WT-E.7 | Cashier (Head Office) | cashier | Receipts (E.6) | Opens Receipts and issues an Official Receipt for a service fee | The OR with the next Head Office OR number OR issued | Not run
WT-E | WT-E.8 | Cashier (Cebu branch) | cashbr | Receive Payment (E.5) | Signs in as the Cebu cashier, opens Receive Payment, enters the account and the amount and checks the preview | The preview of the application by component; the AR takes the next Cebu number AR issued | Not run
WT-E | WT-E.9 | Cashier (Head Office) | cashier | Batch Print (E.16) | Opens Batch Print, selects the receipts of the day and prints them | One print batch with the receipts selected Receipts printed | Not run
WT-E | WT-E.10 | Cashier (Head Office) | cashier | Report Centre (Operations reports) (E.27) | Opens the Report Centre and runs the Applied Premium Report for the day in Excel | The report with the payments of the day Report run | Not run
WT-E | WT-E.11 | Auditor | auditor | Report (E.28) | Signs in as the Auditor and opens the same report | The report on the screen without download View only | Not run

## Lists
Result
Not run
Pass
Fail
Blocked