## Cover
UAT WALKTHROUGH
Business Unit Walkthrough Users
BRD-06 Renewal - sign-in IDs for the walkthrough
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-06
Version | 1.0
Date | 11 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Users | BIBS DEV environment: https://dev.brokerverse.cloud. Password: Issued separately by the iorta TechNXT Project Team | 11
Walkthrough script | The walkthrough of BRD-06 for the Business Unit (FRS Annex AL) | 25
Legend
Pass
Fail
Blocked
Environment: BIBS DEV environment: https://dev.brokerverse.cloud. Passwords: Issued separately by the iorta TechNXT Project Team; no password is written in this workbook.
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Business Unit Walkthrough Users, version 1.0. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Users | Persona | Business role of the FRS
Users | User name | As shown on the screens
Users | Sign-in ID | User ID to type on the Login page
Users | Group profiles | Role held
Users | Company / branch / unit
Users | What the user does in the walkthrough
Users | Menu path to start
Users | Menus the user should see | Renewal entries of the user's menu (FRS Annex AA)
Users | Walkthrough steps | Steps of the sheet Walkthrough script
Users | Password | Never written here
Walkthrough script | Walkthrough
Walkthrough script | Step
Walkthrough script | Persona
Walkthrough script | Sign-in ID
Walkthrough script | Action
Walkthrough script | Expected result
Walkthrough script | Result |  | Not run, Pass, Fail, Blocked
Walkthrough script | Done by
Walkthrough script | Date
Walkthrough script | Remarks

## Users
Users
BIBS DEV environment: https://dev.brokerverse.cloud. Password: Issued separately by the iorta TechNXT Project Team
Persona | User name | Sign-in ID | Group profiles | Company / branch / unit | What the user does in the walkthrough | Menu path to start | Menus the user should see | Walkthrough steps | Password
Marketing Team Leader | Marites Marketing Lead | mkttl | Marketing Team Leader / Head (approver) | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Marketing | Generates the expiring list; initiates; assigns and re-assigns AOs; transfers and receives accounts; reviews, returns and posts; overrides the outstanding-balance flag; RAs; reports | Client & Policy › Renewal › Expiry List | Client & Policy › Renewal › Renewal Home; Client & Policy › Renewal › Expiry List (RMEL); Client & Policy › Renewal › My Dispositions; Client & Policy › Renewal › TL Review; Client & Policy › Renewal › Transfers; Client & Policy › Renewal › Letters; Client & Policy › Renewal › Reports › Renewal reports | WT-A.1, WT-A.6, WT-A.7, WT-A.8, WT-D.2, WT-E.1, WT-E.3 | Issued separately by the iorta TechNXT Project Team
Marketing Team Leader | Rosario Renewal Team Lead | rnwtl | Marketing Team Leader / Head (approver) | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Marketing | Generates the expiring list; initiates; assigns and re-assigns AOs; transfers and receives accounts; reviews, returns and posts; overrides the outstanding-balance flag; RAs; reports | Client & Policy › Renewal › Renewal Home | Client & Policy › Renewal › Renewal Home; Client & Policy › Renewal › Expiry List (RMEL); Client & Policy › Renewal › My Dispositions; Client & Policy › Renewal › TL Review; Client & Policy › Renewal › Transfers; Client & Policy › Renewal › Letters; Client & Policy › Renewal › Reports › Renewal reports | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team
Marketing AO / Admin, Account Broker | Aileen Account Officer | ao | Marketing Account Officer | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Marketing | Views assigned accounts; dispositions; remarks; requests transfers; updates returned accounts; RAs; reports | Client & Policy › Renewal › My Dispositions | Client & Policy › Renewal › Renewal Home; Client & Policy › Renewal › Expiry List (RMEL); Client & Policy › Renewal › My Dispositions; Client & Policy › Renewal › Transfers; Client & Policy › Renewal › Letters; Client & Policy › Renewal › Reports › Renewal reports | WT-A.2, WT-A.3, WT-A.4, WT-A.5, WT-B.5, WT-B.6, WT-C.3, WT-C.4, WT-D.1, WT-D.3, WT-D.4, WT-E.2 | Issued separately by the iorta TechNXT Project Team
Marketing AO / Admin, Account Broker | Arnel Account Officer | ao2 | Marketing Account Officer | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Marketing | Views assigned accounts; dispositions; remarks; requests transfers; updates returned accounts; RAs; reports | Client & Policy › Renewal › Renewal Home | Client & Policy › Renewal › Renewal Home; Client & Policy › Renewal › Expiry List (RMEL); Client & Policy › Renewal › My Dispositions; Client & Policy › Renewal › Transfers; Client & Policy › Renewal › Letters; Client & Policy › Renewal › Reports › Renewal reports | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team
Processing Team Leader | Patricia Processing Lead | proctl | Processing Team Leader | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Processing | Generates the list for processing; uploads dispositioned files; assigns to POs; updates data; computations; insurer extract and responses; RAs; reports | Client & Policy › Renewal › Processing Worklist | Client & Policy › Renewal › Renewal Home; Client & Policy › Renewal › Expiry List (RMEL); Client & Policy › Renewal › Processing Worklist; Client & Policy › Renewal › Insurer Batches; Client & Policy › Renewal › Letters; Client & Policy › Renewal › Renewal Setup; Client & Policy › Renewal › Reports › Renewal reports | WT-B.1 | Issued separately by the iorta TechNXT Project Team
Processing Officer / Broker | Paolo Processor | proc | Processing | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Processing | Processes assigned accounts; uploads; updates data; computations; insurer extract and responses; RAs; reports | Client & Policy › Renewal › Insurer Batches | Client & Policy › Renewal › Renewal Home; Client & Policy › Renewal › Expiry List (RMEL); Client & Policy › Renewal › Processing Worklist; Client & Policy › Renewal › Insurer Batches; Client & Policy › Renewal › Letters; Client & Policy › Renewal › Renewal Setup; Client & Policy › Renewal › Reports › Renewal reports | WT-B.2, WT-B.3, WT-B.4 | Issued separately by the iorta TechNXT Project Team
LAMD user | Leonardo Loan Monitoring | lamd | LAMD (loan status validation) | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Loans Administration and Monitoring (LAMD) | Uploads paid-off and RMU reports; validation and eligibility checks only | Client & Policy › Renewal › LAMD Reports | Client & Policy › Renewal › Renewal Home; Client & Policy › Renewal › Expiry List (RMEL); Client & Policy › Renewal › LAMD Reports | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team
Contact Center user | Cecilia Contact Center | contactc | Contact Center (renewal follow-up) | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Contact Center | Views renewal lists; records follow-up remarks; uploads client documents | Client & Policy › Renewal › Follow-ups | Client & Policy › Renewal › Renewal Home; Client & Policy › Renewal › Expiry List (RMEL); Client & Policy › Renewal › Follow-ups | WT-C.1, WT-C.2 | Issued separately by the iorta TechNXT Project Team
Business Administrator | Bea Business Admin | badmin | Business Administrator | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Business Administration | Maintains lists of values, renewal rules and templates; assigns user profiles | Client & Policy › Renewal › Renewal Home | Client & Policy › Renewal › Renewal Home; Client & Policy › Renewal › Expiry List (RMEL); Client & Policy › Renewal › Renewal Setup; Client & Policy › Renewal › Reports › Renewal reports | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team
System Administrator | SIT System Administrator | admin | System Administrator | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / IT - System Administration | Defines profiles and assigns functions to them | Setup & Administration › Administration › Roles & Permissions | Setup & Administration › Administration › Roles & Permissions (no Renewal entry) | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team
Auditor | Audrey Auditor | auditor | Auditor | BDO Insurance and Reinsurance Brokers, Inc. / Head Office - Makati / Internal Audit | Read access to the renewal records and reports | Client & Policy › Renewal › Renewal Home | Client & Policy › Renewal › Renewal Home, Expiry List (read only) | Not in a walkthrough step | Issued separately by the iorta TechNXT Project Team

## Walkthrough script
Walkthrough script
The walkthrough of BRD-06 for the Business Unit (FRS Annex AL)
Walkthrough | Step | Persona | Sign-in ID | Action | Expected result | Result | Done by | Date | Remarks
WT-A An expiring account from the Expiry List to the Team Leader's post | WT-A.1 | Marketing Team Leader | mkttl | Opens the Expiry List, tab Unassigned Disposition, ticks the renewal of Pacific Harbor Logistics Inc. and clicks Assign Disposition: Arnel Account Officer, then Assign and Push | Message: 1 assigned; the renewal leaves the tab | Not run
WT-A An expiring account from the Expiry List to the Team Leader's post | WT-A.2 | Marketing AO / Admin, Account Broker | ao | Opens My Dispositions | The renewal assigned to him with its expiry, the Review classification and the flags Outstanding and Claims | Not run
WT-A An expiring account from the Expiry List to the Team Leader's post | WT-A.3 | Marketing AO / Admin, Account Broker | ao | Opens the renewal, tab Account History, and clicks View Account History | The payments of the expiring invoice and the open claim; the viewing is recorded | Not run
WT-A An expiring account from the Expiry List to the Team Leader's post | WT-A.4 | Marketing AO / Admin, Account Broker | ao | Clicks Set Disposition: For Renewal with the remarks of the client's call, then Save | Message: Saved; the disposition For Renewal on the renewal | Not run
WT-A An expiring account from the Expiry List to the Team Leader's post | WT-A.5 | Marketing AO / Admin, Account Broker | ao | Clicks Push | Message: Pushed to the Team Leader; the status Review in Progress | Not run
WT-A An expiring account from the Expiry List to the Team Leader's post | WT-A.6 | Marketing Team Leader | mkttl | Opens TL Review, tab For Review, ticks the renewal and clicks Post, then confirms | The outcome: 1 refused, the renewal cannot be posted while the claims, endorsement and outstanding premium checks fail | Not run
WT-A An expiring account from the Expiry List to the Team Leader's post | WT-A.7 | Marketing Team Leader | mkttl | Clicks Override: Outstanding balance, reason Approved by the Team Leader, with remarks (the open claim and the endorsement are overridden the same way) | Message: 1 overridden; the override kept in the History tab of the renewal | Not run
WT-A An expiring account from the Expiry List to the Team Leader's post | WT-A.8 | Marketing Team Leader | mkttl | Clicks Post again and confirms | Message: 1 posted; the renewal moves to Processing | Not run
WT-B Processing, the insurer's answer and the Renewal Advice | WT-B.1 | Processing Team Leader | proctl | Opens the Processing Worklist, tab For Processing, ticks the renewal and clicks Assign PO: Paolo Processor, then Assign | Message: 1 assigned; the renewal In Processing | Not run
WT-B Processing, the insurer's answer and the Renewal Advice | WT-B.2 | Processing Officer / Broker | proc | Opens Insurer Batches, clicks New Batch with Luzon Assurance Co. and the expiry date of the renewal, then Create Batch, and opens the batch | The batch Draft with the renewal and the columns of the insurer extract | Not run
WT-B Processing, the insurer's answer and the Renewal Advice | WT-B.3 | Processing Officer / Broker | proc | Clicks Send to Insurer and confirms | Message: Batch sent to the insurer; the batch Sent with its reply date | Not run
WT-B Processing, the insurer's answer and the Renewal Advice | WT-B.4 | Processing Officer / Broker | proc | Opens the renewal and clicks Record Insurer Response: Renew as is with the insurer reference, then Record | Message: Saved; the renewal RA Ready | Not run
WT-B Processing, the insurer's answer and the Renewal Advice | WT-B.5 | Marketing AO / Admin, Account Broker | ao | Opens Letters, tab RA Ready, ticks the renewal, clicks Generate RA: First notice, then Generate | Message: 1 generated; the renewal in RA Generated, locked on the Marketing side | Not run
WT-B Processing, the insurer's answer and the Renewal Advice | WT-B.6 | Marketing AO / Admin, Account Broker | ao | Opens the tab RA Generated, ticks the renewal, clicks Send and confirms | Message: 1 sent; the Renewal Advice e-mailed protected to the client | Not run
WT-C The Contact Center follow-up and the client's acceptance | WT-C.1 | Contact Center user | contactc | Opens Follow-ups, tab RA Sent | The renewal waiting for the client's reply | Not run
WT-C The Contact Center follow-up and the client's acceptance | WT-C.2 | Contact Center user | contactc | Opens the renewal and clicks Add Follow-up: Call, Client will renew, the next action date and the remarks, then Save | Message: Saved; the follow-up on the Remarks & Follow-ups tab | Not run
WT-C The Contact Center follow-up and the client's acceptance | WT-C.3 | Marketing AO / Admin, Account Broker | ao | Opens the renewal and clicks Record Acceptance: Payment with the payment reference, then Record | Message: Saved; the renewal For Placement and Booking | Not run
WT-C The Contact Center follow-up and the client's acceptance | WT-C.4 | Marketing AO / Admin, Account Broker | ao | Opens the tab Letters | The Renewal Advice in the e-mail queue to the client and the acceptance by payment | Not run
WT-D Not for Renewal and the closing letter | WT-D.1 | Marketing AO / Admin, Account Broker | ao | Opens the renewal, views its account history, clicks Set Disposition: Not for Renewal, reason Loan fully paid, with remarks, then Save | Message: Saved; the disposition Not for Renewal with its reason | Not run
WT-D Not for Renewal and the closing letter | WT-D.2 | Marketing Team Leader | mkttl | After the Account Officer's push, ticks the renewal on TL Review, clicks Post and confirms | Message: 1 posted; the renewal goes to the closing letters | Not run
WT-D Not for Renewal and the closing letter | WT-D.3 | Marketing AO / Admin, Account Broker | ao | Opens Letters, tab NAL / NFR, ticks the renewal, clicks Send Letters and confirms | Message: 1 sent; the renewal is closed | Not run
WT-D Not for Renewal and the closing letter | WT-D.4 | Marketing AO / Admin, Account Broker | ao | Opens the renewal, tab Letters | The Not for Renewal Letter in the e-mail queue to the client | Not run
WT-E A transfer to another unit, and the controls the user sees | WT-E.1 | Marketing Team Leader | mkttl | The Team Leader of Corporate Marketing Team 1 opens Transfers, tab Incoming, chooses Accept in the row action menu and confirms with remarks | Message: Transfer accepted; the renewal joins the Unassigned tab of the unit | Not run
WT-E A transfer to another unit, and the controls the user sees | WT-E.2 | Marketing AO / Admin, Account Broker | ao | Aileen Account Officer gives a disposition on a renewal without opening its account history | Open the Account History before you give the disposition | Not run
WT-E A transfer to another unit, and the controls the user sees | WT-E.3 | Marketing Team Leader | mkttl | Marites Marketing Lead transfers a renewal of her unit to CBG Metro Team 1, her own unit | The receiving unit must be another unit | Not run

## Lists
Result
Not run
Pass
Fail
Blocked