START HERE GUIDE

Start Here

Guide to the BRD-13 Data Migration sign-off set, release set v2.0

BIBS – BDOI Broker System

| Client | BDO Insurance and Reinsurance Brokers, Inc. |
| --- | --- |
| Document | BIBS-SH-BRD-13 |
| Version | 2.0 |
| Date | 5 October 2026 |
| Status | Issued for BDOI business sign-off |
| Classification | Confidential |

Prepared by iorta TechNXT for BDOI

iNXT BrokerVerse. This document is confidential to BDO Insurance and Reinsurance Brokers, Inc. and iorta TechNXT.

Document Control

| Version | Date | Author | Reviewer | Approver | Change |
| --- | --- | --- | --- | --- | --- |
| 2.0 | 5 Oct 2026 | iorta TechNXT Project Manager | iorta TechNXT Business Analysis |  | First issue with the BRD-13 Data Migration business sign-off set (one handbook, one workbook and the test plan in place of the separate migration documents) |

Distribution List

| Name / Unit | Role | Organisation | Purpose |
| --- | --- | --- | --- |
| Program Manager, Business Project Services | Business owner and approver | BDO Unibank ESG | Sign-off |
| Data Migration Lead | Reviewer and signatory | BDOI | Object decisions, trial migrations, cut-over plan |
| Data owners: Marketing Business System, Retail and Corporate Marketing, Operations, Disbursement, Compliance and Analytics | Reviewers and signatories | BDOI | Review of their objects |
| Comptrollership | Reviewer and signatory | BDOI | Legacy accounts, GL opening, reconciliation, opening-balance adjustments, year-end option |
| Renewal processing team | Reviewer and signatory | BDOI | Renewal advices already sent, day-1 renewal queue |
| BDOI IT | Reviewer and signatory | BDOI | Extracts, transfer, freeze, read-only access, decommissioning |
| Project team | Delivery | iorta TechNXT | Sessions, answers, revisions, change requests, the migration runs |

Contents

1 What this set is for	4

2 The set at a glance	4

3 Where to start	4

4 Steps up to closure	5

5 Change control after sign-off	6

# 1 What this set is for

This set describes the proposed migration of the BDOI legacy data (EBIX, QPS, ISYS, CMS and the Excel trackers) into BIBS and the Migration Console that runs it, so that the business owner, each data owner, Comptrollership, the Renewal processing team and BDOI IT can confirm what moves, how it is checked and how the cut-over is run, and sign it off. Signing fixes the decisions per data object, the load templates, the screens, rules and messages of the Migration Console, the reconciliation and the sign-off gates, and the cut-over plan; a later change goes through the Change Management Register with its mandays. The screenshots use fictitious seed data only.

# 2 The set at a glance

The files are numbered so that they sort in reading order in the folder BRD-13_Data_Migration of Drop 0.

Table 1: The documents of the set, in reading order

| File | What it is for | Who reads it | When |
| --- | --- | --- | --- |
| 00_BIBS_StartHere_BRD-13_Data_Migration_v2.0.docx | Start Here: the map of the set, who reads what, the steps up to sign-off and the dates | Everyone | First, on issue |
| 01_BIBS_GuideDeck_BRD-13_Data_Migration_v2.0.pptx | Guide deck: the migration approach, the objects and decisions, roles and data owners, trial migrations and dress rehearsal, sign-off gates, cut-over and go / no-go, migrated and new data, caveats, entry and exit criteria, handover | Business owner, data owners, Comptrollership, BDOI IT; presented at the kick-off | Kick-off session |
| 02_BIBS_Handbook_BRD-13_Data_Migration_v2.0.docx | Data Migration Handbook: A strategy and approach; B functional specification of the Migration Console with screenshots, fields, actions, rules and messages, the markers of migrated data and the legacy batches; C reconciliation and the sign-off gates per object; D the cut-over runbook, run-off and decommissioning; the proposed rules for confirmation | Data owners and Comptrollership for their objects and parts; BDOI IT; the Renewal processing team | During the review, with the console walkthroughs |
| 03_BIBS_Workbook_BRD-13_Data_Migration_v2.0.xlsx | Migration Workbook: object catalogue and decisions, extract planning, the load templates (one sheet per layout), code maps, validation rules, data owners, cut-over task plan, reconciliation sign-off per object, proposed rules with the BDOI decision, the screens; comments log, meeting minutes, version history, sign-off certificate | Every reviewer; the signatories sign it | During the review and at sign-off |
| 04_BIBS_TestPlan_BRD-13_Data_Migration_v2.0.xlsx | Test plan workbook: the test cases traced to the requirements and to the screens, with the trial migration, reconciliation, rollback, rerun and cut-over rehearsal scenarios | Data owners who verify the trial migrations; BDOI IT | After the handbook; used again in the trial migrations |
| 05_BIBS_TestPlan_BRD-13_Data_Migration_Summary_v2.0.docx | Test plan summary: scope, approach, coverage and the cases by area | Business owner, BDOI IT | Before sign-off |

# 3 Where to start

Table 2: Reading order per role

| Role | Where to start |
| --- | --- |
| Business owner (Program Manager, Business Project Services) | 00 Start Here; 01 Guide deck; Handbook Part A (approach, objects and decisions, cycles, cut-over) and the chapter Proposed business rules and clarifications for confirmation; workbook sheets Object catalogue, Proposed rules and Sign-off certificate |
| Data owners per object: Marketing Business System (R01, R05, R06, C01, C03); Heads of Retail and Corporate Marketing (R03, C01); Operations (R04, R07, P01, F01-F04, F06); Comptrollership (R02, R08, F01, F02, G01, G03); Disbursement (R09, C03); Compliance and Analytics (C04, H01, H02); Renewal processing team (P03) | Handbook Part A chapter 3 (objects and decisions) and chapter 6 (templates and mapping); the load template sheets of your objects, Code maps and Validation rules; Part C chapters 32 and 34 for the reconciliation and the samples you verify; workbook sheets Object catalogue, Data owners, Extract planning, Reconciliation sign-off |
| Comptrollership | Handbook Part A chapter 7 (legacy invoices and sub-ledgers) and chapter 11 (cut-over strategy); Part D chapter 44 (year-end cut-over); Part B screens Reconciliation and Opening-Balance Adjustments; Part C chapter 33 (Migration Clearing and the adjustment reconciliation); the proposed rules PR-DM-01, 02, 06, 10 and 14; workbook sheets G01, G03, G03D, F01C and Reconciliation sign-off |
| Renewal processing team | Handbook Part A chapter 8 (renewal-driven transition); Part B Batches (resubmissions of the RA-sent file); Part D tasks of the go-live renewal extraction and the day-1 queue; workbook sheet P03 and the load template workbook of P03 exported by the console |
| BDOI IT | Handbook Part A chapter 6 (templates, secure transfer, masking) and chapter 12 (data security); Part B Extracts and Layouts and Rules; Part D (freeze, final extracts, rollback, decommissioning); proposed rules PR-DM-03 and PR-DM-04; workbook sheets File rules, Load templates, Control file, Cut-over tasks |
| iorta TechNXT project team | All documents; keeps the comments log, the meeting minutes and the version history of the workbook, answers every comment and keeps the traceability to the trial migrations, SIT and UAT |

SIT users of the seed data for the review: miglead (Data Migration Lead), migsteward (Data Steward), migowner (data owner), migops (Migration Operator), migrecon (reconciliation approver), miggonogo (go / no-go board), comptrol (Comptrollership), legacyaudit and legacyrev (Legacy Inquiry and its access log), cashier, cashtl and topmgmt (Unapplied to Income, Legacy PR 2307 Reversal), commrec and commtl (DP PR Legacy Reversal). The passwords are sent separately to the named reviewers.

# 4 Steps up to closure

Table 3: From issue to closure

| No. | Step | Who (R, A, C, I) | Output | When / duration |
| --- | --- | --- | --- | --- |
| 1 | Set issued | R: iorta TechNXT Project Manager; A: iorta TechNXT delivery lead; I: all reviewers | Release set v2.0 in the BRD-13 folder of Drop 0; invitations to the sessions | Day 0 (Mon 5-Oct-2026) |
| 2 | Kick-off and walkthrough of the Migration Console on SIT | R: iorta TechNXT Business Analysis; A: Program Manager; C: data owners, Comptrollership, BDOI IT, Renewal processing team | Console shown live; first questions logged in the comments log; minutes | 3 sessions, 7 to 9-Oct-2026 |
| 3 | Review with the workbook; decisions on the proposed rules | R: data owners and their stewards, Comptrollership, BDOI IT; A: Program Manager; C: iorta TechNXT (questions) | Every row marked Accept, Change requested or Comment; decisions on the rules needed by 16-Oct-2026 (M1); comments log entries | Until Wed 21-Oct-2026 (M1 rules by Fri 16-Oct-2026) |
| 4 | Comments consolidated and a Q&A session | R: iorta TechNXT Project Manager and Business Analysis; A: Program Manager; C: reviewers | One consolidated comments log, each item typed (clarification, correction, change request) and answered; Q&A minutes | 3 working days, Q&A on Mon 26-Oct-2026 |
| 5 | One revision cycle (v2.1) | R: iorta TechNXT Business Analysis; A: iorta TechNXT delivery lead; C: reviewers who raised the items | Release set v2.1 with the changed rows marked and the decided rules applied; change requests raised for the rest | v2.1 on Wed 28-Oct-2026; check by the reviewers until Thu 29-Oct-2026 |
| 6 | Sign-off meeting and signature | R: iorta TechNXT Project Manager; A: Program Manager; C: data owners, Comptrollership, Compliance, BDOI IT | Signed sign-off certificate; minutes; objects decided (G1) and layouts frozen, version 1 (M2) | Fri 30-Oct-2026 (M2) |
| 7 | Handover to the migration runs | R: iorta TechNXT delivery lead; A: Program Manager; I: BDOI IT, other BRD owners | Decisions and owners entered in the Migration Console; first full extracts in the templates by 29-Jan-2027 (M3) | From Mon 2-Nov-2026 |
| 8 | Traceability into the trial migrations, SIT and UAT | R: iorta TechNXT test lead; A: Program Manager; C: data owners | Trial migrations 1 to 4 and the dress rehearsal run and signed against the set; results against each row | Trial migrations Apr - Oct 2027; dress rehearsal Nov 2027; cut-over Jan 2028 |

How to review. Read the Handbook part of your role, or follow the same screens on SIT during the sessions. In the Migration Workbook, set BU review to Accept, Change requested or Comment on each row of your objects (sheets Object catalogue, Data owners, Extract planning, the load template sheets, Code maps, Validation rules, Cut-over tasks, Reconciliation sign-off) and on the screen sheets, write the change in BU comment, and add your name and the date. On the sheet Proposed rules, record the BDOI decision on each proposed rule. Questions go to the Comments log sheet. One workbook per unit is enough.

Table 4: SIT walkthrough sessions

| Date | Time | Session | Units |
| --- | --- | --- | --- |
| Wed 7-Oct-2026 | 09:30-12:00 | Kick-off with the guide deck; the approach, the objects and their decisions; Migration Home, Data Objects, Code Maps, Layouts and Rules, and the load templates | Business owner, data owners, Data Migration Lead, BDOI IT |
| Thu 8-Oct-2026 | 09:30-12:30 | One object from extract to acceptance: Extracts, Batches and a batch, Client Matching, Reconciliation, Sign-off; rejected rows and the resubmission of the RA-sent file | Data owners and stewards, Renewal processing team, BDOI IT |
| Fri 9-Oct-2026 | 09:30-12:30 | Financial objects and the cut-over: legacy invoices on Invoice 360, the legacy batches, Opening-Balance Adjustments, Migration Clearing, Cutover and go / no-go, Run-off and Decommissioning, Legacy Inquiry | Comptrollership, Operations, Cashiering, Commission, Compliance, BDOI IT |

Table 5: Key dates

| Date | What |
| --- | --- |
| Mon 5-Oct-2026 | Set issued (release set v2.0) |
| 7 to 9-Oct-2026 | Kick-off and SIT walkthroughs |
| Fri 16-Oct-2026 | Decisions on the proposed rules marked M1 |
| Wed 21-Oct-2026 | Reviewed workbooks returned to the project team |
| Mon 26-Oct-2026 | Q&A session on the consolidated comments log |
| Wed 28-Oct-2026 | Release set v2.1 with the agreed corrections, when needed |
| Fri 30-Oct-2026 | Sign-off meeting (M2): objects decided, layouts frozen, owners named |

# 5 Change control after sign-off

Signing fixes the decisions per data object, the load templates and the control file, the code map sets, the validation rules, the screens, fields, actions, rules and messages of the Migration Console, the markers of migrated data, the legacy batches, the reconciliation per object, the sign-off gates, the cut-over plan and the cross-BRD contract as specified. Settings marked "default" (thresholds, tolerances, retention days, dates of the cut-over calendar) and the open decisions with their dates are not fixed. A change to anything fixed is raised in the Change Management Register with the object, layout, screen, rule or message concerned, assessed with its mandays and its effect on the other BRDs, approved by the owners of every BRD it touches, and delivered as a new version of the set; only the affected pages and layouts are signed again.