RECONCILIATION APPROACH

Migration Reconciliation Approach and Sign-off

BRD-13 Data Migration - how every data object is proven from source to target

BIBS – BDOI Broker System

| Client | BDO Insurance and Reinsurance Brokers, Inc. |
| --- | --- |
| Document | BIBS-DMR-BRD-13 |
| Version | 1.1 |
| Date | 26 September 2026 |
| Status | Issued for BDOI review |
| Classification | Confidential |

Prepared by iorta TechNXT for BDOI

iNXT BrokerVerse. This document is confidential to BDO Insurance and Reinsurance Brokers, Inc. and iorta TechNXT.

Document Control

| Version | Date | Author | Reviewer | Approver | Change |
| --- | --- | --- | --- | --- | --- |
| 1.0 | 26 Sep 2026 | iorta TechNXT Solution Architect | iorta TechNXT Project Manager | Head, Comptrollership (pending) | First issue for BDOI review, with the Data Migration Strategy and Approach v1.0 |
| 1.1 | 26 Sep 2026 | iorta TechNXT Solution Architect | iorta TechNXT Project Manager | Head, Comptrollership (pending) | With the Strategy v1.1 (BDOI timeline, go-live January 2028; four mocks). L5 compares each legacy control account with the opening detail; sign of a Migration Clearing difference corrected in the worked example; cohort completeness of the carried RMEL cohorts (P03); package remapping samples |

Distribution List

| Name / Unit | Role | Organisation | Purpose |
| --- | --- | --- | --- |
| Head, Comptrollership; Product Owner FRBS / ACSL | Approver | BDOI | Reconciliation approver for financial objects |
| Data owners of each object | Approver | BDOI | Business verification and acceptance (G6) |
| BDOI Data Migration Lead; Program Manager | Reviewer | BDOI | Go / no-go evidence |
| Audit / Compliance | Reviewer | BDOI | Evidence retention; archive reconciliation |
| Project team | Delivery | iorta TechNXT | Reconciliation runs and reports |

Contents

1 Purpose and scope	4

2 Reconciliation levels	4

3 Control totals BDOI sends	5

4 Reconciliation per data object	6

5 GL reconciliation: Migration Clearing	7

6 Business verification on screen (gate G6)	8

6.1 Sample plan	8

6.2 Acceptance rule	9

7 Breaks, waivers and exclusions	9

8 Evidence and retention	10

9 Sign-off forms	10

9.1 Object reconciliation and acceptance (G5 and G6)	11

9.2 Cutover reconciliation summary (go / no-go GNG-3)	12

9.3 Archive reconciliation (before decommissioning)	13

# 1 Purpose and scope

BRID 1.1b asks that, after cutover, "all data objects and items are reconcilable from source to target" from the generated data migration reports (BRD p.7). This document states how each object is reconciled, what BDOI verifies on the BIBS screens, how breaks are handled, which evidence is kept, and the forms that BDOI signs. It applies to every mock, the dress rehearsal and the production cutover, and to the archive loads before decommissioning.

It completes the Data Migration Strategy and Approach (section 6.10) and FRS BRD-13 (FR-DM-020, FR-DM-021, FR-DM-003). Account codes are not named: the legacy control accounts and the Migration Clearing account are assigned by Comptrollership (DMQ18, register DCR-197).

# 2 Reconciliation levels

Five levels are run by BIBS after each load (job MIG_RECONCILE) and on demand. Levels L1 to L4 apply to every object; L5 to the financial objects.

Table 1: Reconciliation levels

| Level | Measure | How it is computed | Pass rule |
| --- | --- | --- | --- |
| L1 | Record counts | Control file row count; rows received, staged, valid, warning, invalid, loaded, skipped, rejected, excluded (per batch and its reruns) | Received = control count; loaded + skipped + rejected + excluded = staged; rejected rows are 0 for financial objects or excluded by the owner |
| L2 | Amounts | Per amount column and currency: control total, staged sum, and the value read from BIBS (ledger components of origin LEGACY, unapplied balances, journal lines) | Difference 0.00 (tolerance MIG_AMOUNT_TOLERANCE, default 0.00) at each stage |
| L3 | Hash totals | Hash total of the key column as the layout defines it; SHA-256 per staged row; count of distinct keys in the cross-reference | Control = staged = cross-reference |
| L4 | Fields | Every mapped field of every loaded row read back through the owning service and compared with the staged, mapped value | Equal; a difference explained by the code map (mapped value) is not a break |
| L5 | GL | Migration Clearing balance per branch and currency, analysed per legacy control account (trial balance line against the opening detail posted to that account); each legacy control account against its legacy sub-ledger (ACSL GL-SL reconciliation with ledger context LEGACY) | Migration Clearing 0.00; per control account TB line = opening detail; control account = sub-ledger |

Breaks. Any difference is a break (status BREAK). A break is fixed by a rerun (new extract, new map version or a corrected row) or explained. An explanation gives a reason from the list MIG_BREAK_REASON (rounding at source, record excluded by the owner, mapping difference, legacy data error, late legacy transaction, other) and a text, and is approved by the reconciliation approver. A reconciliation cannot be signed (gate G5) while a break is open.

Reports. MIG-RECON-SUMMARY (object by level with status), MIG-RECON-DETAIL (lines, breaks, explanations, approvals), MIG-REJECTS (rejected and invalid rows with their messages), MIG-GL-CLEARING (Migration Clearing per branch and currency; legacy control accounts against sub-ledgers). All export to Excel and PDF.

# 3 Control totals BDOI sends

Every data file comes with a control file (workbook sheet "Control File" and template CONTROL_template.ctl.csv). It always carries the row count and the SHA-256 of the data file, plus the hash total of the key and the amount totals of the layout:

Table 2: Control totals required per layout (row count and SHA-256 for every layout)

| Layout | Content | Hash total (L3) | Amount totals per currency (L2) |
| --- | --- | --- | --- |
| R01 | Lists of values and MIS values | Count of distinct (list_type, code) | - |
| R02 | Branches and invoicing branches | Count of distinct branch_code | - |
| R03 | Sales organisation (units and account officers) | Count of rows per record_type | - |
| R04 | Insurers | Count of distinct insurer_code | - |
| R04B | Insurer branches | Count of distinct (insurer_code, branch_code) | - |
| R05 | Product lines, cover types, products and risk codes | Count of distinct risk_code | - |
| R06 | Packages (active versions) | Count of distinct (package_code, package_version) | - |
| R07 | Commission rates by insurer and product | Count of rows | - |
| R08 | Chart of accounts mapping | Count of distinct legacy_account_code | - |
| R09 | Payees | Count of distinct payee_code | - |
| R11 | Receipt series in use | Count of rows | - |
| C01 | Client master | Count of distinct legacy_client_no | - |
| C02 | Client addresses and contacts | Count of rows | - |
| C03 | Client payout accounts | Count of rows | - |
| P01 | In-force policy headers | Count of distinct legacy_policy_ref | sum_insured, gross_premium, net_premium |
| P01S | Policy insurer shares | Count of rows | - |
| P03 | RMEL cohorts January to May 2028 (carried renewals) | Count of distinct legacy_policy_ref per rmel_month | expiring_premium, proposed_sum_insured, proposed_premium |
| F01 | Open legacy invoices - header | Count of distinct legacy_invoice_no | gross_premium, commission, vat_on_commission |
| F01S | Open legacy invoices - insurer shares | Count of rows | - |
| F01C | Open legacy invoices - components and positions | Count of rows | booked, adjusted, paid, remitted, written_off, open_balance |
| F02 | Unapplied premium payments (UPP) | Count of distinct legacy_upp_ref | amount, balance |
| F03 | Open collection state | Count of rows | promise_amount, installment_amount |
| F04 | Remittance in flight | Count of rows | amount |
| F06 | PDCs, check pick-ups and refunds in process | Count of rows per record_type | amount |
| G01 | GL opening trial balance | Count of rows | debit_fc, credit_fc, debit_php, credit_php |
| H01 | Archive records (closed transactions and history) | Count of distinct (record_type, legacy_key) | amount |
| H02 | Archive documents index | Count of rows; SHA-256 per file | - |

The workbook sheet "Control Totals" lists the same measures one per row, with columns for the value from BDOI, the value in BIBS, the difference and the status. It is the tie-out sheet of L1 to L3 for each cycle.

# 4 Reconciliation per data object

Table 3: What is reconciled per object

| Object | L1 counts | L2 amounts | L3 hash | L4 fields | L5 GL / business check |
| --- | --- | --- | --- | --- | --- |
| R01-R08, R11 | Values received, mapped, created, rejected | - | Distinct keys | Created values (name, status, dates) | Unmapped-code report empty; every CREATE value authorised in its master; every legacy package in the PACKAGE map |
| R09 | Payees received and loaded | - | Distinct payee codes | All loaded fields | Payee list in Disbursement |
| C01, C02 | Legacy clients received, clusters, merged, new, loaded | - | Distinct legacy client numbers = cross-reference entries | Identity, contact, segment, KYC fields of the survivor | Client review queue empty; each legacy number resolves to one BIBS client |
| C03 | Accounts received and loaded | - | Distinct (client, account) | All fields | - |
| P01, P01S | Headers received and loaded; shares | Sum insured, gross and net premium per currency | Distinct legacy policy references | All header fields and shares | Headers linked to their clients and legacy invoices |
| P03 | Candidates per expiry month (January-May 2028) | Expiring and proposed premium per currency | Distinct references per month | Disposition, handler, dates, RA, mapped packages | Cohort completeness per month: P01 headers expiring T to T+140 = P03 rows + renewals booked in legacy + rejected rows; candidates in Renewal with source LEGACY; catch-up candidates = headers without a P03 row |
| F01, F01S, F01C | Invoices, share rows, component rows | Booked, adjusted, paid, remitted, written off and open per component and currency | Distinct invoice numbers | Header fields, shares, every component and bucket | L5 - Premium Receivable, PR2307, DTIP, Commission Receivable (legacy) against the legacy invoices; Migration Clearing 0.00 |
| F02 | UPP items | Amount and balance per currency | Distinct UPP references | All fields, stage and disposition | L5 - Unapplied Collections (legacy) against the migrated UPP balances |
| F03 | Rows per record type | Promise and installment amounts | Distinct (invoice, type, seq) | All fields | Worklist items show the carried promises and assignments |
| F04, F06 | Rows per record type | Amount per currency | Distinct keys | All fields | Holds and PDCs visible in Remittance and Cashiering |
| G01 | Trial balance lines | Debit and credit per branch and currency, in currency and PHP | Lines per branch | Account, branch, currency and amounts per line | Trial balance in BIBS = legacy trial balance per branch and currency; Migration Clearing 0.00 |
| H01, H02 | Records per record type; documents | Amount per record type and currency | Distinct keys per record type; SHA-256 per document | Labelled legacy columns | Samples found in Legacy Inquiry with their documents |

# 5 GL reconciliation: Migration Clearing

The open-item objects and the trial balance are loaded from two independent sources in legacy: the invoice and UPP detail (F01, F02) and the GL (G01). Migration Clearing proves that they agree (Figure 1):

•	each legacy invoice and each UPP item is loaded with an opening entry whose balancing line goes to Migration Clearing;

•	the trial balance is loaded as OPENING journals; its lines on the legacy control accounts (premium receivable, PR2307, DTIP, commission receivable, unrealised commission, deferred VAT, unapplied collections) are mapped to Migration Clearing instead of the legacy control accounts, because the opening entries build those balances in detail;

•	when the detail equals the GL, Migration Clearing is 0.00 per branch and currency.

Figure 1: Migration Clearing nets to zero when the detail equals the legacy GL

Worked example (one branch, PHP, one invoice and one UPP item; made-up figures; the unrealised commission follows DMQ13 and is taken here as fully unrealised):

Table 4: Migration Clearing for one branch

| Line | Debit | Credit | Effect on Migration Clearing |
| --- | --- | --- | --- |
| F01 opening of I00123456 - Premium Receivable - Legacy | 10,000.00 |  |  |
| F01 opening - Commission Receivable - Legacy | 4,480.00 |  |  |
| F01 opening - DTIP - Legacy |  | 23,050.00 |  |
| F01 opening - Unrealised Commission and Deferred VAT - Legacy |  | 4,480.00 |  |
| F01 opening - balancing line to Migration Clearing | 13,050.00 |  | Debit 13,050.00 |
| F02 opening of UPP-2026-004321 - Unapplied Collections - Legacy |  | 5,000.00 |  |
| F02 opening - balancing line to Migration Clearing | 5,000.00 |  | Debit 5,000.00 |
| G01 trial balance - legacy control-account lines (PR 10,000.00 Dr, commission 4,480.00 Dr, DTIP 23,050.00 Cr, unrealised and deferred 4,480.00 Cr, UPP 5,000.00 Cr) mapped to Migration Clearing |  | 18,050.00 (net) | Credit 18,050.00 |
| G01 trial balance - cash in bank 18,050.00 Dr, mapped to the BIBS bank account | 18,050.00 |  | - |
| Migration Clearing |  |  | 0.00 |

A missing invoice. A difference on Migration Clearing has the sign of the trial balance, because the TB puts the legacy control-account lines on Migration Clearing with their own sign and the opening entries put the detail there with the opposite sign. So an invoice missing from F01 leaves a debit equal to its net receivable position (open premium receivable, PR2307 and commission receivable, less open DTIP, unrealised commission and deferred VAT) when that is positive, and a credit when it is negative (FR-DM-021 acceptance 3). Two cases, made-up figures:

•	F01 missed an invoice paid in full and not remitted, with DTIP 5,000.00 open and commission receivable 800.00 (realised on collection): Migration Clearing shows a credit of 4,200.00 in that branch.

•	F01 missed an unpaid invoice with premium receivable 3,000.00, DTIP 3,000.00, commission receivable 480.00 and the same 480.00 unrealised: Migration Clearing nets to 0.00. The per-account comparison of MIG-GL-CLEARING finds it: the TB is 3,000.00 debit higher than the detail on Premium Receivable - Legacy, 3,000.00 credit higher on DTIP - Legacy, and 480.00 higher on each commission account.

Either break is investigated and fixed or explained before go / no-go.

Legacy control accounts against sub-ledgers. After the loads, the ACSL GL to Sub-ledger Reconciliation is run with ledger context LEGACY: each legacy control account must equal the open positions of the legacy invoices (or legacy UPP) behind it. This is criterion 6 of the go / no-go and is repeated daily in hypercare and at every month-end until the legacy context closes.

# 6 Business verification on screen (gate G6)

L1 to L5 prove that what BDOI sent is what BIBS holds. Business verification proves that what BIBS holds means what the business expects: the right client, the right policy, the right balance, on the screens users will work with. The data owner (or the steward on the owner's behalf) checks a sample per object in the environment of the cycle and signs the object acceptance.

## 6.1 Sample plan

The Migration Lead draws the samples from the loaded batch (random with a fixed seed recorded on the form, plus the targeted records). Samples are checked against the legacy screen or a legacy report of the same as-of date.

Table 5: Business verification samples per object

| Object | Sample | What is checked on the BIBS screen |
| --- | --- | --- |
| R01-R08, R11 | Every CREATE value; 10 mapped values per map set; every legacy package with more than one BIBS target (conditional PACKAGE entries); every receipt series | Value, description and status in the master; the package version chosen for sample headers and renewals of each split; next AR / OR number = legacy last used + 1 |
| C01-C03 | 30 random clients per source system; 20 merged clusters; 10 decisions of the review queue; 10 corporate clients | Client search by legacy number; name, identity, contacts, segment, AO, KYC status and review date; cluster shows every legacy number |
| P01 | 30 random headers; 10 with several insurers; 10 expiring within 140 days | Account search by policy and legacy reference; dates, insurer and shares, sum insured, premium, client link, legacy invoices listed |
| P03 | 20 candidates per carried expiry month (January-May 2028); every candidate with package UNRESOLVED (up to 30); 10 catch-up candidates | Candidate in Renewal with disposition, handler, RA status, proposed terms, package and remarks; UNRESOLVED candidates in the Exception bucket; catch-up candidates at the first stage |
| F01 | 20 largest open balances per currency; 30 random; 10 endorsement or cancellation invoices; 10 direct-payment; 10 with 2307; up to 20 foreign-currency | Invoice 360: legacy badge, source, legacy number, original values, booked / paid / remitted / open per component, shares; Collections item for open premium |
| F02 | 20 largest balances; 20 random; every item with a disposition in progress (up to 30) | Unapplied Payments workbench: legacy AR, amount, balance, tab, references, disposition |
| F03, F04, F06 | 20 random per object | Promise and assignment on the Collections item; hold or special request in Remittance; PDC in the warehouse list |
| G01 | Every branch and currency total; 20 largest account lines | Trial balance report in BIBS against the legacy trial balance |
| H01, H02 | 10 records per record type; 10 documents | Legacy Inquiry search by the legacy key; labelled columns; document opens and matches its checksum |

## 6.2 Acceptance rule

•	Financial objects (F01, F02, G01) and identity fields of clients: no error is accepted. One error stops the sign-off: the cause is found, fixed at source, in the map or in the loader, the batch is rerun, and a new sample is drawn.

•	Other fields: an error that is isolated and cosmetic (for example capitalisation of an address) is listed on the form with its fix (legacy correction before the next extract, or correction in BIBS after go-live by the owner). Two or more errors of the same kind in a sample are treated as systematic: the sample is doubled and the cause is fixed before sign-off.

•	The result is recorded on the object sign-off form (section 9.1) with the sample seed, the records checked and the errors found.

# 7 Breaks, waivers and exclusions

Table 6: How differences are closed

| Situation | Handling | Approved by |
| --- | --- | --- |
| Row rejected by a data-quality rule | Fixed at source and re-extracted, fixed by a new map version, or waived (master data only) | Data steward; waiver by the data owner |
| Financial row that cannot be fixed before go-live | Excluded from the batch with a manual-entry plan (who keys it in BIBS after go-live, when, and the amount) | Data owner and Comptrollership |
| Amount or count difference between control file and staging | The extract is rejected at intake; BDOI IT re-sends | - |
| Difference between staging and BIBS (L2, L4) | Loader or mapping defect: fixed and rerun; never explained away | iorta Migration Lead |
| Migration Clearing not 0.00 | Traced to the invoice, UPP or TB line; fixed by rerun or by a legacy correction and a new extract; a residual rounding difference is explained with its amount | Reconciliation approver (Comptrollership) |
| Late legacy transaction after the freeze | Recorded as a break; the transaction is re-keyed in BIBS after go-live and the legacy system owner explains the access | Data owner; BDOI IT |

# 8 Evidence and retention

For each object and cycle the evidence pack holds: the extract numbers with file names, SHA-256 and control totals; the map versions used; MIG-DQ-ISSUES with waivers; MIG-REJECTS; MIG-RECON-SUMMARY and MIG-RECON-DETAIL; MIG-GL-CLEARING for financial objects; the sample list with the check results; and the signed forms of section 9. The pack is exported from the Migration Console and filed in the project records. Staging rows and files are purged within 5 days of sign-off, but counts, hashes, totals, reports and sign-offs are kept (proposed 10 years, DMQ29).

# 9 Sign-off forms

The forms below are signed in the Migration Console (gates G5 and G6) and printed for the project file. One form per object and cycle.

## 9.1 Object reconciliation and acceptance (G5 and G6)

| Object and name | .......... .................................................... |
| --- | --- |
| Cycle and environment | Mock 1 / Mock 2 / Mock 3 / Mock 4 / Dress rehearsal / Production Environment: ................ |
| Batch numbers (MGB-) | ........................................................................ |
| Extract numbers (MGX-) and as-of | ........................................................................ |
| Code map versions used | ........................................................................ |
| Sample seed and size | Seed ............ Records checked ............ |

Table 7: Reconciliation results (from MIG-RECON-SUMMARY)

| Level | Measure | Source (control) | BIBS | Difference | Status (MATCHED / EXPLAINED) |
| --- | --- | --- | --- | --- | --- |
| L1 | Rows received / staged / loaded / skipped / rejected / excluded |  |  |  |  |
| L2 | Amount totals per currency (list) |  |  |  |  |
| L3 | Hash total of the key |  |  |  |  |
| L4 | Field differences (count) | - |  |  |  |
| L5 | Migration Clearing; control account vs sub-ledger | - |  |  |  |
| G6 | Business verification sample - errors found | - |  |  |  |

Table 8: Breaks explained, waivers and exclusions

| # | Break, waiver or exclusion | Reason and explanation | Approved by / manual-entry plan |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |

| Name | Role | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
|  | Reconciliation approver - G5 (Comptrollership for financial objects) | BDOI |  |  |
|  | Data owner - G6 object accepted | BDOI |  |  |
|  | Data Migration Lead - G6 | BDOI |  |  |
|  | Migration Lead (reconciliation run) | iorta TechNXT |  |  |

## 9.2 Cutover reconciliation summary (go / no-go GNG-3)

| Cutover | Production Go-live date (T): ................ Freeze: T-3 22:00 |
| --- | --- |
| Rollback point (snapshot ID and time) | ........................................................................ |

Table 9: Day-1 objects at go / no-go

| Object | Batch | Loaded / staged | G5 signed | G6 signed |
| --- | --- | --- | --- | --- |
| R01-R08, R11 |  |  |  |  |
| C01-C03 |  |  |  |  |
| P01, P03 |  |  |  |  |
| F01 |  |  |  |  |
| F02 |  |  |  |  |
| F03, F04, F06 |  |  |  |  |
| G01 |  |  |  |  |

Table 10: Migration Clearing and legacy control accounts per branch and currency

| Branch / currency | Migration Clearing | Control accounts vs sub-ledgers | Status |
| --- | --- | --- | --- |

| Name | Role | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
|  | Head, Comptrollership | BDOI |  |  |
|  | Data Migration Lead | BDOI |  |  |
|  | Program Manager (for the go / no-go board) | BDO Unibank ESG |  |  |
|  | Project Manager | iorta TechNXT |  |  |

## 9.3 Archive reconciliation (before decommissioning)

| Legacy system | EBIX / QPS / ISYS / CMS / File shares |
| --- | --- |
| Record types archived | ........................................................................ |
| Archive batches (MGB-) | ........................................................................ |

Table 11: Archive counts and totals per record type

| Record type | Legacy count | Archived count | Amount total legacy | Amount total archive | Samples checked in Legacy Inquiry |
| --- | --- | --- | --- | --- | --- |

| Name | Role | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
|  | Legacy system owner | BDOI |  |  |
|  | Audit / Compliance | BDOI |  |  |
|  | Head, Comptrollership | BDOI |  |  |