## Cover
CHANGE CONTROL
Change Request Register
User Access Maintenance; goes with the FRS User Access Maintenance v1.5
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-11
Version | 1.2
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Register | All change requests of BRD-11. Withdrawn in v1.2: CR-UA-003, CR-UA-011, CR-UA-014. Rescoped: CR-UA-007. | 16
Decision Log | Decision Log | 4
Legend
Open
Closed
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Change Request Register, version 1.2. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Register | CR
Register | Title
Register | Status v1.2 |  | Open, Withdrawn, Closed, Approved, Rejected
Register | FRS v1.5
Register | Man-days
Register | Note
Decision Log | Date
Decision Log | Item
Decision Log | Decision

## Register
Register
All change requests of BRD-11. Withdrawn in v1.2: CR-UA-003, CR-UA-011, CR-UA-014. Rescoped: CR-UA-007.
CR | Title | Status v1.2 | FRS v1.5 | Man-days | Note
CR-UA-001 | Separation-of-duties rules | Closed | - | 0 | Closed: BRD requirement, OOTB
CR-UA-002 | Dormant-user deactivation | Closed | - | 0 | Closed: OOTB (OB-UA-02)
CR-UA-003 | Break-glass administrators | Withdrawn | - | 6 | No break-glass account in the agreed model (BDOI IT, 15 Oct 2026).
CR-UA-004 | Warning before system sign-out | Closed | - | 0 | Closed: BRD requirement
CR-UA-005 | Synchronisation with UIDM-ISC | Closed | - | 0 | Closed: integration scope (IS-UA-01)
CR-UA-006 | Revocation on SSO status change | Closed | - | 0 | Closed: integration scope (IS-UA-01)
CR-UA-007 | Data access by company and branch | Open | FRUM.003.03 | 12.5 | Rescoped: company and branch scope per user. The supervisor and record-owner scope of v1.4 is dropped.
CR-UA-008 | No conflicting permissions in a profile | Closed | - | 0 | Closed: BRD requirement
CR-UA-009 | Export file names | Closed | - | 0 | Closed: BRD requirement
CR-UA-010 | Source address in the audit log | Closed | - | 0 | Closed: BRD requirement (addenda NFR 4.03)
CR-UA-011 | Approval time limits and reminders of access requests | Withdrawn | - | 5.25 | User access requests are handled in UIDM-ISC.
CR-UA-012 | Periodic access review | Closed | - | 0 | Closed: OOTB (OB-UA-05)
CR-UA-013 | E-mail copy of notices | Closed | - | 0 | Closed: BRD requirement; user request notices in UIDM-ISC
CR-UA-014 | End date on the granting request (temporary access) | Withdrawn | - | 7.75 | Requests and effective dates are handled in UIDM-ISC.
CR-UA-015 | One session per device | Closed | - | 0 | Closed: BRD requirement (Collections NFR 10.07)
CR-UA-016 | Emergency direct edit of group profiles | Open | FRUM.012.04 | 6.5 | Kept: group-profile path, not a request workflow.

## Decision Log
Decision Log
Change Request Register – BIBS – BDOI Broker System
Date | Item | Decision
11 Oct 2026 | Register v1.1 | Five open change requests after the product owner review.
15 Oct 2026 | CR-UA-003 | Withdrawn: no break-glass account (BDOI IT).
16 Oct 2026 | CR-UA-011, CR-UA-014 | Withdrawn: user access requests and effective dates are in UIDM-ISC.
16 Oct 2026 | CR-UA-007 | Rescoped to company and branch data access.

## Lists
Status v1.2
Open
Withdrawn
Closed
Approved
Rejected