## Cover
FIT-GAP
BRD vs Out-of-the-Box vs Best Practice
User Access Maintenance; goes with the FRS User Access Maintenance v1.5
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-11
Version | 1.2
Date | 16 October 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Fit-Gap | Each requirement of the FRS v1.5 against the BRD and the iNXT BrokerVerse OOTB platform. | 44
Best Practice | Blue points: in no BRD, FRS or OOTB; recommendation only. | 5
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
BRD vs Out-of-the-Box vs Best Practice, version 1.2. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Fit-Gap | FRUM
Fit-Gap | BRD
Fit-Gap | Requirement
Fit-Gap | Colour
Fit-Gap | Fit |  | Fit, Fit (OOTB extra), Integration, Change request, Withdrawn
Fit-Gap | Note
Best Practice | No.
Best Practice | Recommendation
Best Practice | Priority
Best Practice | Man-days

## Fit-Gap
Fit-Gap
Each requirement of the FRS v1.5 against the BRD and the iNXT BrokerVerse OOTB platform.
FRUM | BRD | Requirement | Colour | Fit | Note
FRUM.001.01 | BRD 1.001, 2.001, 3.001, 4.001; NFR 4, 17 | Every user signs in through Microsoft Entra ID (OpenID Connect). The second factor is asked by Entra ID. | Black (BRD) | Integration | BIBS links the Entra ID identity to an active BIBS user with the same Windows ID; an unknown or inactive identity is refused.
FRUM.001.02 | BRD 1.001, 2.001, 3.001, 4.001; NFR 4, 17 | After sign-in the user sees only the menus and actions of the group profiles held. | Black (BRD) | Fit | Permissions are the union of the active group profiles; data is limited to the user's data access.
FRUM.001.03 | BRD 1.001, 2.001, 3.001, 4.001; NFR 4, 17 | The user is warned after 15 minutes without activity and signed out after 30 minutes. | Black (BRD) | Fit | Stay Logged In resets the timer; Log Out ends the session. Both values are UAM settings.
FRUM.001.04 | BRD 1.001, 2.001, 3.001, 4.001; NFR 4, 17 | The user is warned before the system-triggered sign-out at the end of the session. | Black (BRD) | Fit | The warning time is a UAM setting (30 minutes by default).
FRUM.001.05 | BRD 1.001, 2.001, 3.001, 4.001; NFR 4, 17 | Production offers no password sign-in. Test accounts sign in with a local password only in DEV, SIT and UAT. | Black (BRD) | Fit | Production refuses local sign-in, password change and password reset; the Login page shows only the Entra ID button.
FRUM.001.06 | BRD 1.001, 2.001, 3.001, 4.001; NFR 4, 17 | Break-glass administrator accounts (v1.4) are withdrawn. | - | Withdrawn | No account bypasses Entra ID. CR-UA-003 is withdrawn.
FRUM.002.01 | BRD 1.002 | UIDM-ISC creates the user in BIBS with a SCIM 2.0 joiner event, after the request is approved in UIDM-ISC. | Black (BRD) | Integration | The event carries the User ID, Windows ID, name, e-mail, department, unit, location and UIDM request number. The user starts active without a group profile.
FRUM.002.02 | BRD 1.002 | BIBS refuses to create or change a user from its own screens. | Black (BRD) | Fit | The Users screen is read-only for the user record; any attempt is refused with "Users are maintained in UIDM-ISC".
FRUM.002.03 | BRD 1.002 | A joiner whose User ID or Windows ID belongs to another user is refused and listed as a refused event. | Black (BRD) | Integration | The User Access Administrator is alerted (see FRUM.014.02).
FRUM.003.01 | BRD 1.003, 1.004, 1.005 | UIDM-ISC changes a user's details with a mover event and the group profiles with a group membership event. | Black (BRD) | Integration | Each change is kept attribute by attribute in the access history with the UIDM request number.
FRUM.003.02 | BRD 1.003, 1.004, 1.005 | A leaver event deactivates the user and ends every open session at once. | Black (BRD) | Integration | A rehire event reactivates the user; group profiles come again from UIDM-ISC.
FRUM.003.03 | BRD 1.003, 1.004, 1.005 | The User Access Administrator sets the companies and branches a user may act for. | Orange (CR) | Change request | The change applies at once and is logged. Change request CR-UA-007 (data access by company and branch).
FRUM.003.04 | BRD 1.003, 1.004, 1.005 | The User Access Administrator ends all sessions of a user. | Green (OOTB) | Fit (OOTB extra) | Asks for confirmation; logged with the reason.
FRUM.003.05 | BRD 1.003, 1.004, 1.005 | The User Access Administrator unlocks a test account locked after failed sign-ins. | Black (BRD) | Fit | Applies to local test accounts outside production only.
FRUM.003.06 | BRD 1.003, 1.004, 1.005 | A user without a sign-in for the dormancy period is deactivated by the daily run, after a notice. | Green (OOTB) | Fit (OOTB extra) | Default 90 days, notice 7 days before. The User Access Administrator is told to disable the user in UIDM-ISC too.
FRUM-004.01 | BRD NFR 4; Annex I of BDOI's FRS | Passwords and second-factor methods of bank users are kept by Microsoft Entra ID. | Black (BRD) | Integration | BIBS stores no password of a bank user and offers no password change for them.
FRUM-004.02 | BRD NFR 4; Annex I of BDOI's FRS | Local test accounts follow BDOI's password guidelines in DEV, SIT and UAT. | Black (BRD) | Fit | Lock-out after 3 failed sign-ins; expiry 90 days; minimum age 1 day; last 10 passwords not reused.
FRUM-004.03 | BRD NFR 4; Annex I of BDOI's FRS | A test account's password is reset by another System Administrator, never by its owner. | Black (BRD) | Fit | Refused in production and wherever local passwords are off.
FRUM.005.01 | BRD 3.002.1, 4.002.1 | The Group Profile Maker proposes a new group profile: code, name, description, privilege level, permissions and reason. | Black (BRD) | Fit | Save Draft keeps it; Submit for Approval sends it to the checkers. No approver is chosen.
FRUM.005.02 | BRD 3.002.1, 4.002.1 | The new group profile exists only once approved (and implemented when the setting asks for it). | Black (BRD) | Fit | Until then it is listed under Proposed New Group Profiles.
FRUM.006.01 | BRD 3.002.2 to 3.002.4, 4.002.2 | The Group Profile Maker proposes a change of name, description, level or permissions of an active group profile. | Black (BRD) | Fit | Blank fields keep the current value; the change must alter at least one item.
FRUM.006.02 | BRD 3.002.2 to 3.002.4, 4.002.2 | The Group Profile Maker proposes the deactivation or reactivation of a group profile. | Black (BRD) | Fit | On deactivation the members lose the profile's access; they are told by notice.
FRUM.006.03 | BRD 3.002.2 to 3.002.4, 4.002.2 | A group profile has at most one open change. | Black (BRD) | Fit | A second proposal is refused until the open one is decided or withdrawn.
FRUM.007.01 | BRD 3.003; NFR 1.g | Five reports: User Access, User Group Profile, Group Profile Membership, User Access Audit Log and Group Profile Changes, each exported to PDF, Excel and CSV. | Black (BRD) | Fit | Fields and parameters are in the RNO document.
FRUM.007.02 | BRD 3.003; NFR 1.g | The Access Matrix shows the group profiles against the permissions, and by action, with an Excel export. | Black (BRD) | Fit | Read-only for every persona.
FRUM.007.03 | BRD 3.003; NFR 1.g | The certification extract lists every account, group profile and permission in CSV or XLSX. | Green (OOTB) | Fit (OOTB extra) | Each extract is logged with who took it, when, the rows and the SHA-256 of the file; Information Security is told.
FRUM-008.01 | BRD 4.003; NFR 6; addenda NFR 4.03 | Every user access event is in the audit trail with the from and to values, who, when, the source address and the request or change number. | Black (BRD) | Fit | Users, sessions, group profiles and their changes, SoD rules, identity events, mismatches, certification extracts and settings.
FRUM-008.02 | BRD 4.003; NFR 6; addenda NFR 4.03 | Sign-ins, failed sign-ins and sign-outs are logged and can be included in the audit log report. | Black (BRD) | Fit
FRUM.009.01 | BRD 1.002 to 1.009 | Withdrawn. User access requests are raised, corrected, cancelled and followed in UIDM-ISC; BIBS receives only the approved result. | - | Withdrawn | BDOI's review comment "c/o UIDM".
FRUM.010.01 | BRD 2.002, 3.002; NFR 11 | Any Group Profile Checker other than the maker approves, returns for correction or rejects a submitted change. | Black (BRD) | Fit | Return and Reject need a remark. The maker corrects a returned change and submits it again.
FRUM.010.02 | BRD 2.002, 3.002; NFR 11 | A change of a High or Admin group profile, or submitted outside the working hours, needs a second approval by another checker. | Black (BRD) | Fit | The second approver differs from the maker and the first approver.
FRUM.010.03 | BRD 2.002, 3.002; NFR 11 | An approved change applies at once, or waits for the System Administrator to implement it when the setting asks for it. | Black (BRD) | Fit | The implementer differs from the maker.
FRUM.010.04 | BRD 2.002, 3.002; NFR 11 | A change that would break an active separation-of-duties rule is refused. | Black (BRD) | Fit
FRUM.010.05 | BRD 2.002, 3.002; NFR 11 | The approver list and effective date of v1.4 are withdrawn. | - | Withdrawn | No approver is chosen; a change applies on its decision date.
FRUM.011.01 | BRD 1.009 | Withdrawn. Bulk changes are made in UIDM-ISC and reach BIBS as individual SCIM events. | - | Withdrawn
FRUM.012.01 | BRD NFR 2-3; Operations addendum | Separation-of-duties rules name two group profiles, or two permissions, one user may not hold together. | Black (BRD) | Fit | A rule is proposed and authorised by Information Security; deactivation also needs authorisation.
FRUM.012.02 | BRD NFR 2-3; Operations addendum | A daily check lists the users who breach an active rule and tells Information Security of the new ones. | Black (BRD) | Fit | The breach is corrected in UIDM-ISC.
FRUM.012.03 | BRD NFR 2-3; Operations addendum | UAM settings change only after another user approves the change. | Black (BRD) | Fit | The maker may withdraw a pending change; every change is logged.
FRUM.012.04 | BRD NFR 2-3; Operations addendum | The System Administrator may edit a group profile directly only while Information Security has opened the emergency path. | Orange (CR) | Change request | Every edit is logged and alerted. Change request CR-UA-016.
FRUM.013.01 | BRD NFR 10 | BIBS sends the notices of group-profile changes, access changes, dormancy, identity events, reconciliation, separation of duties, settings and certification extracts. | Black (BRD) | Fit | The list and texts are in the RNO document. Notices of user access requests come from UIDM-ISC.
FRUM.013.02 | BRD NFR 10 | A notice is also e-mailed when the user's preference or the setting asks for it. | Black (BRD) | Fit
FRUM.014.01 | BRD NFR 4, 11; integration scope IS-UA-01, IS-UA-02 | Identity Sync shows the last call from UIDM-ISC, the last successful event, errors of the last 24 hours, refused events and open mismatches. | Black (BRD) | Integration
FRUM.014.02 | BRD NFR 4, 11; integration scope IS-UA-01, IS-UA-02 | An event BIBS cannot apply is refused, listed with its reason and alerted to the User Access Administrator. | Black (BRD) | Integration | Retry processes it again after UIDM-ISC corrected the data; Dismiss closes it with a remark.
FRUM.014.03 | BRD NFR 4, 11; integration scope IS-UA-01, IS-UA-02 | A daily reconciliation compares every user and its group profiles with UIDM-ISC and lists the mismatches. | Black (BRD) | Integration | Synchronise Now runs it at once. A mismatch is resolved with a remark once UIDM-ISC corrected the user.

## Best Practice
Best Practice
Blue points: in no BRD, FRS or OOTB; recommendation only.
No. | Recommendation | Priority | Man-days
BP-UA-01 | Monitoring of privileged sessions | Medium | 6
BP-UA-02 | Alert on unusual sign-in | Medium | 5
BP-UA-03 | Log of views of sensitive records | Medium | 6
BP-UA-04 | Joiner-mover-leaver timeliness report | Medium | 4
BP-UA-06 | Generic and shared account register | Low | 3

## Lists
Fit
Fit
Fit (OOTB extra)
Integration
Change request
Withdrawn