RUNBOOK

Cutover Runbook

BRD-13 Data Migration - production cutover from T-30 to hypercare exit

BIBS – BDOI Broker System

| Client | BDO Insurance and Reinsurance Brokers, Inc. |
| --- | --- |
| Document | BIBS-DMC-BRD-13 |
| Version | 1.1 |
| Date | 26 September 2026 |
| Status | Issued for BDOI review |
| Classification | Confidential |

Prepared by iorta TechNXT for BDOI

iNXT BrokerVerse. This document is confidential to BDO Insurance and Reinsurance Brokers, Inc. and iorta TechNXT.

Document Control

| Version | Date | Author | Reviewer | Approver | Change |
| --- | --- | --- | --- | --- | --- |
| 1.0 | 26 Sep 2026 | iorta TechNXT Project Manager | iorta TechNXT Solution Architect | BDOI Program Manager (pending) | First issue; dates are relative to T until BDOI confirms the go-live date (DMQ25); re-issued after the dress rehearsal with named people and measured timings |
| 1.1 | 26 Sep 2026 | iorta TechNXT Project Manager | iorta TechNXT Solution Architect | BDOI Program Manager (pending) | Calendar of the BDOI timeline (go-live January 2028, proposed Monday 3 January 2028) with the relative days mapped to dates; tasks moved off the year-end holidays (GNG-2 and the last business day to T-5, completion drives to T-12, client load to T-11); carried RMEL cohorts of January-May 2028 with the completeness check and the catch-up extraction; default names of the decommissioning criteria. Named people and measured durations follow in version 1.2 after the dress rehearsal |

Distribution List

| Name / Unit | Role | Organisation | Purpose |
| --- | --- | --- | --- |
| Program Manager, Business Project Services | Approver | BDO Unibank ESG | Owner of the cutover; chair of the go / no-go board |
| Go / no-go board members | Approver | BDOI | Checkpoints GNG-1, GNG-2, GNG-3 |
| BDOI IT (legacy EBIX, QPS, ISYS, CMS) | Task owner | BDOI | Freeze, extracts, read-only, rollback |
| Comptrollership; Operations; Marketing; Compliance | Task owner | BDOI | Accounts, reconciliation, verification, communication |
| Project team | Task owner | iorta TechNXT | Loads, reconciliation, environment, hypercare |

Contents

1 Purpose and use	4

2 Cutover organisation	4

2.1 Command centre	4

2.2 Roles	5

3 Timeline	5

3.1 Calendar	5

3.2 Freeze windows	7

4 Go / no-go checkpoints	8

5 Task list	9

5.1 Phase A - Readiness	9

5.2 Phase B - Pre-load and daily deltas	10

5.3 Phase C - Legacy freeze and final extracts	11

5.4 Phase D - Production load	11

5.5 Phase E - Reconciliation, verification and go / no-go	12

5.6 Phase F - Go-live	13

5.7 Phase G - Hypercare	13

6 Rollback	15

7 Communication plan	15

8 Hypercare	16

8.1 Roster	16

8.2 Exit criteria	16

9 Decommissioning checklists	17

Sign-off	18

# 1 Purpose and use

This runbook is the plan of the production cutover of BIBS: from 30 days before go-live (T) to the end of hypercare. It lists every task with its owner, start, duration, predecessors and the evidence that proves it is done; the go / no-go checkpoints with their criteria; the freeze windows; the rollback procedure; the communication plan; the hypercare roster and exit criteria; and the decommissioning checklists of the legacy systems.

•	T is the go-live date. The BDOI timeline sets it in January 2028 (DMQ25); the proposal is Monday 3 January 2028, the first business day after the legacy year-end close (DMQ39, register DCR-242). Days are calendar days; times are Philippine time (PHT). Section 3.1 maps the relative days to dates; tasks that would fall on the year-end holidays are placed on the nearest working day.

•	The same tasks are in the Cutover Task Plan workbook (BIBS_Migration_BRD-13_Cutover_Task_Plan_v1.1.xlsx), where names, actual times and status are recorded, and in the Migration Console as the plan of kind PRODUCTION (FR-DM-120). The console is the record during the cutover; the workbook is the planning and review copy.

•	The plan is rehearsed in four mocks (April, July, August and October 2027) and a dress rehearsal (November 2027) (Strategy chapter 10). This version gives planned durations; version 1.2, issued after the dress rehearsal, gives the measured durations and the named people.

•	The early renewal release of the concept paper of 6 September 2026 is superseded by the single January 2028 go-live (register DCR-240). The renewals of the January-May 2028 expiries that are not booked in legacy at the freeze are carried into BIBS in this cutover (tasks CT-028, CT-046, CT-070).

# 2 Cutover organisation

## 2.1 Command centre

•	Location and channels. A command centre room at BDOI head office, a standing bridge line and a chat channel for the cutover team, open from T-3 17:00 to T+5.

•	Status calls. T-3 to T: every 4 hours and at each checkpoint. T+1 to T+5: 08:00 and 17:00. Afterwards daily at 17:00 until hypercare exit.

•	Decisions. Task owners report completion with the evidence in the console. The Data Migration Lead decides within the plan; anything that changes the plan, the scope or a checkpoint goes to the go / no-go board.

•	Escalation. Task owner to the Data Migration Lead (15 minutes), to the iorta Project Manager and the Program Manager (30 minutes), to the go / no-go board (1 hour, or immediately for a stop condition).

Stop conditions (the board meets at once): a rejected final extract that cannot be re-sent within 2 hours; a load failure that leaves a financial object incomplete; Migration Clearing not 0.00 after the reconciliation window; a legacy posting after the freeze; loss of the production environment or of the snapshot.

## 2.2 Roles

Table 1: Roles used in the task plan

| Code | Role | Organisation |
| --- | --- | --- |
| PM | BDOI Program Manager (ESG - Business Project Services) | BDOI |
| DML | BDOI Data Migration Lead | BDOI |
| OWN | Data owners (department heads of each object) | BDOI |
| STW | Data stewards | BDOI |
| COMP | Comptrollership (reconciliation approver for financial objects) | BDOI |
| OPS | Operations (Financial Transactions, Cashiering, Remittance, Collections) | BDOI |
| MKT | Marketing (Retail and Corporate) and Renewal handlers | BDOI |
| CMP | Compliance and Audit | BDOI |
| BIT | BDOI IT (legacy systems, extracts, network, SFTP) | BDOI |
| GNG | Go / no-go board (Program Manager, heads of Operations, Comptrollership, Marketing, Compliance, IT; iorta Project Manager) | BDOI and iorta TechNXT |
| IPM | iorta TechNXT Project Manager | iorta TechNXT |
| IML | iorta TechNXT Migration Lead (loaders, reconciliation, console) | iorta TechNXT |
| IOP | iorta TechNXT Migration Operator (intake, validation, loads) | iorta TechNXT |
| IDO | iorta TechNXT DevOps (AWS environment, snapshots, access, monitoring) | iorta TechNXT |
| IQA | iorta TechNXT QA (smoke tests, defect triage) | iorta TechNXT |

# 3 Timeline

Table 2: Cutover phases

| Phase | Name | When | Tasks | IDs |
| --- | --- | --- | --- | --- |
| A | Readiness | T-30 to T-15 (4 to 19 Dec 2027) | 13 | CT-001 to CT-013 |
| B | Pre-load and daily deltas | T-14 to T-4 (20 to 30 Dec 2027) | 18 | CT-014 to CT-031 |
| C | Legacy freeze and final extracts | T-3 (Friday 31 Dec 2027) | 5 | CT-032 to CT-036 |
| D | Production load | T-2 (Saturday 1 Jan 2028) | 13 | CT-037 to CT-049 |
| E | Reconciliation, verification and go / no-go | T-1 (Sunday 2 Jan 2028) | 8 | CT-050 to CT-057 |
| F | Go-live | T (Monday 3 Jan 2028) | 7 | CT-058 to CT-064 |
| G | Hypercare | T+1 to the first month-end close (January 2028) | 11 | CT-065 to CT-075 |

## 3.1 Calendar

Table 3: Relative days on the calendar of the proposed go-live

| Day | Date (T = 3-Jan-2028) | Note |
| --- | --- | --- |
| T-30 | Sat 4 Dec 2027 | Dress rehearsal (15-26 Nov 2027) already done; reserve slot 6-10 Dec 2027 if its exit criteria were missed |
| T-26 | Wed 8 Dec 2027 | Feast of the Immaculate Conception (special non-working day) - the Comptrollership set-up (CT-007) is planned from T-25 |
| T-21 | Mon 13 Dec 2027 | Communications to branches, insurers and bank channels |
| T-15 | Sun 19 Dec 2027 | GNG-1 (board meets on Friday 17 December if preferred) |
| T-14 | Mon 20 Dec 2027 | Production pre-load of reference data starts |
| T-12 | Wed 22 Dec 2027 | Client extract; completion drives for remittance batches and in-flight items (moved from T-9, Christmas Day) |
| T-11 | Thu 23 Dec 2027 | Client load and sign-off; daily client deltas start (moved from T-10, Christmas Eve) |
| T-10 | Fri 24 Dec 2027 | Christmas Eve (special non-working day) - no task planned |
| T-9 | Sat 25 Dec 2027 | Christmas Day - no task planned |
| T-7 | Mon 27 Dec 2027 | Code map freeze; legacy reference-data change freeze |
| T-5 | Wed 29 Dec 2027 | Last legacy business day; GNG-2 (moved from T-4, Rizal Day); freeze announcement |
| T-4 | Thu 30 Dec 2027 | Rizal Day (regular holiday) - no task planned |
| T-3 | Fri 31 Dec 2027 | Last day of the year (special non-working day) - legacy EOD and year-end close; business freeze 22:00; final extracts |
| T-2 | Sat 1 Jan 2028 | New Year's Day - production load (cut-over team on duty) |
| T-1 | Sun 2 Jan 2028 | Reconciliation, verification, GNG-3 at 18:00 |
| T | Mon 3 Jan 2028 | Go-live 08:00; carried RMEL candidates in Renewal; point of no return 18:00 |
| T+1 | Tue 4 Jan 2028 | Hypercare; Renewal catch-up extraction and first daily extraction |
| T+30 | Wed 2 Feb 2028 | First month-end close (January 2028) completed; hypercare exit decision |

Figure 1: The cutover weekend (T = Monday 3 January 2028, proposed; times PHT)

## 3.2 Freeze windows

Table 4: Freeze windows

| Freeze | From | Until | Scope | Exception route |
| --- | --- | --- | --- | --- |
| Reference data | T-7 (map freeze) | Go-live | Insurers, products, risk codes, packages, AOs, branches, LOVs in EBIX and QPS | Change request approved by the data owner; new code map version; delta load of R objects |
| Client master | T-3 22:00 (last delta) | Go-live | New and changed clients in QPS / EBIX / CMS | None after the freeze; changes keyed in BIBS after go-live |
| Business transactions | T-3 22:00 (after the last legacy EOD) | Go-live | All postings in EBIX, QPS, CMS - bookings, receipts, UPP, dispositions, remittances, endorsements, GL journals | None; an urgent item is recorded on paper and keyed in BIBS on T |
| BIBS configuration | T-2 00:00 | T+3 | Parameters, accounting rules, code maps, workflows in production | Emergency change approved by the go / no-go board |
| BIBS releases | T-7 | T+14 | Deployments to production | Hotfix of a Critical defect approved by the go / no-go board |

# 4 Go / no-go checkpoints

Each checkpoint is recorded in the Migration Console with the value of every criterion at the time of the decision (FR-DM-121). A criterion that is not met blocks GO unless the board records a waiver with its reason (only for criteria marked as waivable in the console; the financial and clearing criteria of GNG-3 are never waived).

Table 5: GNG-1 at T-15 - Start the production pre-load

| # | Criterion |
| --- | --- |
| 1 | Dress rehearsal completed within the window with at least 20 percent margin, rollback rehearsed |
| 2 | Production environment, roles and PH-only access ready; masking off only in production |
| 3 | Legacy control accounts, Migration Clearing and LG_ rule lines approved in production (DMQ18) |
| 4 | Code map versions for production approved |
| 5 | Transfer path (SFTP or console) tested |
| 6 | No open Critical defect of the migration or of a Day-1 module |

Table 6: GNG-2 at T-5 - Enter the legacy freeze on T-3

| # | Criterion |
| --- | --- |
| 1 | Reference data and clients loaded and accepted (G6) in production; daily deltas running |
| 2 | Client review queue empty |
| 3 | Final extract jobs timed within the window (dry run) |
| 4 | In-flight items and remittance batches closed or listed for carry-forward |
| 5 | RMEL cohorts to carry (January-May 2028) confirmed; disposition files complete |
| 6 | Communications sent; branches and insurers informed |

Table 7: GNG-3 at T-1 18:00 - Go live on T

| # | Criterion |
| --- | --- |
| 1 | Every Day-1 object at G6 (100 percent) |
| 2 | Counts - received = control and loaded + skipped + rejected + excluded = staged, for every object |
| 3 | Financial rejects (F01, F02, G01) - 0, or each excluded item approved by the owner with a manual-entry plan |
| 4 | Amount reconciliation of open items, UPP and trial balance - 0.00 difference per currency |
| 5 | Migration Clearing - 0.00 per branch and currency |
| 6 | Legacy control accounts equal their sub-ledgers (ACSL, context LEGACY) - 0.00 |
| 7 | Client review queue empty; screening run complete |
| 8 | Business smoke test passed |
| 9 | Rollback point (snapshot) taken and verified |
| 10 | Hypercare roster and support channels in place |

Table 8: POINT OF NO RETURN at T 18:00 - Continue in BIBS; fallback to legacy no longer offered (DMQ32)

| # | Criterion |
| --- | --- |
| 1 | No Critical defect that stops receipts, payment application, remittance or booking |
| 2 | Migration Clearing still 0.00; no posting in legacy since the freeze |
| 3 | Every branch has transacted in BIBS |

# 5 Task list

Columns: When is the day relative to T and the planned start time; Owner is the accountable role (codes in section 2.2); Hours is the planned elapsed time; After lists the tasks that must be complete first; Verification is the evidence recorded in the console.

## 5.1 Phase A - Readiness

Table 9: Phase A - Readiness

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-001 | T-30 | Confirm the dress rehearsal met its exit criteria (all objects loaded and reconciled L1-L5, window met with 20 percent margin, rollback rehearsed) | DML | 4 | - | Dress rehearsal report signed by the Data Migration Lead and the iorta Migration Lead |
| CT-002 | T-30 | Confirm the go-live date, the freeze start (last legacy EOD) and the blackout dates (DMQ25); publish the cutover calendar | PM | 2 | CT-001 | Calendar approved by the Program Manager and circulated |
| CT-003 | T-29 | Name the cutover team, the command centre room and bridge line, and the hypercare roster (section Hypercare) | PM | 4 | CT-002 | Roster with names and phone numbers in the runbook annex |
| CT-004 | T-28 | Freeze the production cutover plan in the Migration Console (plan kind PRODUCTION, tasks and owners from this list) | IML | 4 | CT-002 | MIG-CUTOVER-STATUS shows the plan with every task owned |
| CT-005 | T-28 | Production environment ready - BIBS release of the go-live build deployed, MIG_ENVIRONMENT_CLASS = PRODUCTION, MIG_CUTOVER_DATE = T, jobs scheduled | IDO | 8 | - | Deployment record; parameter screen; job list |
| CT-006 | T-27 | Grant the migration roles in production (DATA_MIGRATION_LEAD, DATA_STEWARD, DATA_OWNER, MIGRATION_OPERATOR, MIGRATION_RECON_APPROVER, MIGRATION_GONOGO) through User Access requests; check PH-only network access | IDO | 8 | CT-005 | User Access approvals; access test from an allowed and a blocked location |
| CT-007 | T-25 | Comptrollership sets up in production the legacy control accounts, Migration Clearing and the LG_ accounting rule lines (DMQ18), through maker-checker | COMP | 16 | CT-005 | Chart and accounting rules approved; test posting in the dress rehearsal environment matched |
| CT-008 | T-25 | Approve the final code map versions for production (all sets); record versions in the plan | OWN | 16 | - | MIG-MAP-VERSIONS lists one APPROVED version per set |
| CT-009 | T-24 | Users of every persona created and trained; BIBS menus checked per persona (UAT readiness items 1 and 14) | PM | 40 | CT-006 | User list; training attendance; persona menu check |
| CT-010 | T-21 | Communicate the go-live and freeze to branches, insurers and bank channels (autopay files carry the legacy invoice number after go-live) | PM | 4 | CT-002 | Communications sent (communication plan items 1-4) |
| CT-011 | T-20 | Legacy clean-up drives - UPP with no reference, invoices open more than 5 years, duplicate clients flagged in Mock 3, unmapped codes | STW | 80 | - | Clean-up tracker; counts reduced against Mock 3 profiling |
| CT-012 | T-18 | SFTP drop or console upload path tested end to end from BDOI IT with a masked file; checksum verified | BIT | 4 | CT-005 | Test extract accepted and purged |
| CT-013 | T-15 | Go / no-go checkpoint GNG-1 (readiness to start the pre-load) | GNG | 2 | CT-001, CT-004, CT-006, CT-007, CT-008, CT-012 | Decision recorded in the console with the GNG-1 criteria |

## 5.2 Phase B - Pre-load and daily deltas

Table 10: Phase B - Pre-load and daily deltas

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-014 | T-14 08:00 | Take a production database snapshot before the pre-load | IDO | 1 | CT-013 | Snapshot ID recorded in the plan |
| CT-015 | T-14 09:00 | Extract and send R01-R08 and R11 (current values) with control files | BIT | 6 | CT-014 | Files received; intake checks passed (extract status CHECKED) |
| CT-016 | T-14 15:00 | Validate and load reference data R01-R08; authorise CREATE values in each master | IOP | 8 | CT-015 | Batches LOADED; MIG-UNMAPPED-CODES empty for R objects |
| CT-017 | T-13 | Reconcile and sign off the reference objects (G5, G6) | DML | 6 | CT-016 | MIG-SIGNOFF-STATUS shows G6 for R01-R08 |
| CT-018 | T-13 | Load payees R09 if in scope (DMQ30) | IOP | 4 | CT-017 | Batch SIGNED_OFF |
| CT-019 | T-12 | Extract and send the full client extract C01, C02, C03 (as of the previous EOD) | BIT | 8 | CT-017 | Files CHECKED; counts against the Mock 4 volumes within 5 percent |
| CT-020 | T-12 | Validate clients; run matching; clear the review queue | STW | 24 | CT-019 | Review queue empty; MIG-CLIENT-MATCH reviewed |
| CT-021 | T-11 | Load clients C01-C03; reconcile L1-L4; business sample checks; sign off (G5, G6) | IOP | 16 | CT-020 | MIG-RECON-SUMMARY all MATCHED or EXPLAINED; G6 signed |
| CT-022 | T-11 | Daily client delta (new and changed clients of the day) from T-11 to T-5 - extract 23:00, load 00:30 (job MIG_CLIENT_DELTA) | BIT | 1 | CT-021 | Delta batch SIGNED_OFF each morning by 07:00 |
| CT-023 | T-12 | Complete legacy remittance batches in process, or tag the holds and special remittances that carry forward (DMQ21) | OPS | 40 | - | List of carried items for F04 agreed by Operations - Remittance |
| CT-024 | T-12 | Complete in-flight legacy items where possible - pending endorsements, un-booked accounts, placed or bound renewals not yet booked, check pick-ups, refunds (DMQ33) | OPS | 40 | - | In-flight list reduced; the rest listed for carry-forward or re-keying |
| CT-025 | T-7 | Code map freeze - no new legacy code without a change request and a map version | OWN | 1 | CT-017 | Freeze notice sent; change log opened |
| CT-026 | T-7 | Legacy reference-data change freeze in EBIX and QPS (insurers, products, AOs, branches) | BIT | 1 | CT-025 | Maintenance screens locked or change log reviewed daily |
| CT-027 | T-7 | Dry run of the final extract jobs on the current day's data (timing and control files) | BIT | 6 | CT-015 | Extract timings within the plan; control files correct |
| CT-028 | T-5 | Confirm with Marketing the RMEL cohorts to carry (expiries 3-Jan to 22-May-2028) and the consolidated disposition files; list the renewals placed but not booked (in-flight); stop new legacy RMEL extractions | MKT | 4 | - | Cohort list and counts per month agreed; disposition files complete |
| CT-029 | T-5 | Go / no-go checkpoint GNG-2 (enter the legacy freeze) | GNG | 2 | CT-021, CT-022, CT-023, CT-024, CT-027, CT-028 | Decision recorded with the GNG-2 criteria |
| CT-030 | T-5 | Announce the freeze and the Monday opening to all users, branches and insurers | PM | 1 | CT-029 | Communication plan item 5 sent |
| CT-031 | T-5 17:00 | Last legacy business day - last business transactions; cashiers deposit and close; UPP of the day recorded (30 and 31 December are holidays, DMQ39) | OPS | 3 | CT-029 | Branch close checklist from every branch |

## 5.3 Phase C - Legacy freeze and final extracts

Table 11: Phase C - Legacy freeze and final extracts

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-032 | T-3 20:00 | Last legacy EOD and year-end close (EBIX, QPS, ISYS, CMS) | BIT | 2 | CT-031 | EOD logs complete without error |
| CT-033 | T-3 22:00 | Legacy business freeze - EBIX, QPS, CMS set to read-only for business users; batch jobs that post are disabled | BIT | 1 | CT-032 | Test posting refused in each legacy system; job list shows disabled jobs |
| CT-034 | T-3 22:15 | Final client delta (last changes of the day) extracted and loaded | IOP | 2 | CT-033 | Last delta batch SIGNED_OFF |
| CT-035 | T-3 22:30 | Final extracts after the EOD - P01, P01S, P03, F01, F01S, F01C, F02, F03, F04, F06, R11 (final numbers), G01 trial balance | BIT | 5 | CT-033 | Every file and control file in the intake; SHA-256 recorded |
| CT-036 | T-3 23:30 | Comptrollership confirms the legacy trial balance is final and balanced per branch and currency | COMP | 2 | CT-032 | Signed TB total per branch and currency |

## 5.4 Phase D - Production load

Table 12: Phase D - Production load

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-037 | T-2 02:00 | Take the production database snapshot - the rollback point | IDO | 1 | CT-034, CT-035 | Snapshot ID and restore test of the snapshot metadata recorded |
| CT-038 | T-2 03:00 | Intake checks of all final extracts (checksum, layout, row count, control totals, hash totals) | IOP | 1 | CT-037 | Every extract CHECKED; rejected files re-sent within 1 hour |
| CT-039 | T-2 04:00 | Validate P01 and P01S; resolve issues; approve load (G3, G4) | IOP | 2 | CT-038 | Error rate within the master threshold; G4 signed by the Data Migration Lead |
| CT-040 | T-2 06:00 | Load policy headers P01; reconcile L1-L4 | IOP | 3 | CT-039 | MIG-RECON-SUMMARY for P01 MATCHED |
| CT-041 | T-2 06:00 | Validate F01, F01S, F01C; resolve issues; approve load (G3, G4) | IOP | 3 | CT-038 | 0 financial errors or owner-approved exclusions with manual-entry plan |
| CT-042 | T-2 09:00 | Load open legacy invoices F01 with opening entries MIG_LEGACY_INVOICE_OPENING | IOP | 5 | CT-040, CT-041 | Batch LOADED without rejects |
| CT-043 | T-2 09:00 | Validate and load UPP F02 with opening entries MIG_UPP_OPENING | IOP | 3 | CT-038, CT-021 | Batch LOADED without rejects |
| CT-044 | T-2 14:00 | Load collection state F03, remittance items F04, PDCs and pick-ups F06 | IOP | 3 | CT-042 | Batches LOADED |
| CT-045 | T-2 15:00 | Load the GL opening trial balance G01 (OPENING journals per branch and currency) | IOP | 2 | CT-036, CT-042, CT-043 | Journals posted; TB in BIBS equals the legacy TB |
| CT-046 | T-2 16:00 | Validate and load the RMEL cohorts P03 (January-May 2028); run the cohort completeness check | IOP | 2 | CT-040 | Batch LOADED; P03 rows + headers renewed in legacy + rejected rows = P01 headers expiring T to T+140 per month; headers without a P03 row listed for the catch-up extraction |
| CT-047 | T-2 17:00 | Update the receipt series R11 to the final next numbers | IOP | 1 | CT-038 | Next AR / OR numbers = legacy last used + 1 per branch |
| CT-048 | T-2 18:00 | Reconcile L1-L4 of every financial object; run L5 - Migration Clearing per branch and currency, legacy control accounts vs sub-ledgers (ACSL, context LEGACY) | IML | 4 | CT-044, CT-045 | MIG-GL-CLEARING shows 0.00 per branch and currency |
| CT-049 | T-2 22:00 | Explain or fix every break (rerun batches); reconciliation approver signs G5 per object | COMP | 6 | CT-048 | MIG-RECON-SUMMARY all MATCHED or EXPLAINED with approval |

## 5.5 Phase E - Reconciliation, verification and go / no-go

Table 13: Phase E - Reconciliation, verification and go / no-go

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-050 | T-1 06:00 | Start the full sanction screening run of migrated clients (SCR_PERIODIC_SCREENING, full rescreen) | IOP | 6 | CT-021 | Run completed; hits in the screening queue for Compliance |
| CT-051 | T-1 07:00 | Business verification of samples per object on the BIBS screens (Reconciliation Approach, sample plan); data owners sign G6 | OWN | 6 | CT-049 | Sample checklists signed; G6 for every Day-1 object |
| CT-052 | T-1 09:00 | Business smoke test on production with test-marked transactions reversed afterwards - OTC payment preview on a legacy invoice, automatch preview, remittance extraction preview, Invoice 360, client and policy search by legacy reference | IQA | 4 | CT-049 | Smoke test checklist passed; no posting left open |
| CT-053 | T-1 13:00 | Check jobs, alerts and integrations for Monday (PAYMENT_AUTOMATCH hourly, payment file handlers, Renewal extraction, e-mail) | IDO | 2 | CT-052 | Job schedule and alert routing checked |
| CT-054 | T-1 15:00 | Prepare the go / no-go pack - MIG-GONOGO with measured criteria, open defects, sign-off status | IML | 2 | CT-050, CT-051, CT-052, CT-053 | Pack circulated to the board by 17:00 |
| CT-055 | T-1 18:00 | Go / no-go decision GNG-3 (go-live) | GNG | 1 | CT-054 | Decision recorded in the console with every criterion value |
| CT-056 | T-1 19:00 | If NO-GO - execute the rollback procedure (section Rollback) and reopen legacy for Monday | IDO | 6 | CT-055 | Legacy open for business Monday 08:00; BIBS restored to the rollback point |
| CT-057 | T-1 19:00 | If GO - send the go-live notice; open BIBS roles for business users from 06:00 Monday | PM | 1 | CT-055 | Communication plan item 6 sent |

## 5.6 Phase F - Go-live

Table 14: Phase F - Go-live

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-058 | T 06:00 | Enable business logins; confirm legacy stays read-only; legacy links shown in BIBS | IDO | 1 | CT-057 | Log-in test per persona; legacy posting refused |
| CT-059 | T 07:00 | Command centre opens; hypercare roster on duty | IPM | 1 | CT-058 | Attendance on the bridge |
| CT-060 | T 08:00 | BIBS open for business | PM | 0 | CT-059 | First transactions observed in each branch |
| CT-061 | T 09:00 | First payment file uploads and the first automatch run including migrated UPP; review results | OPS | 2 | CT-060 | Run summary; legacy and new postings in the right accounts |
| CT-062 | T 12:00 | Midday check - defects, queues, Migration Clearing still 0.00, no legacy posting | IML | 1 | CT-060 | Midday report to the board |
| CT-063 | T 18:00 | End-of-day review - point of no return (DMQ32); decide continue or fallback | GNG | 1 | CT-062 | Decision recorded |
| CT-064 | T 20:00 | First BIBS EOD jobs; check GL posting, sub-ledgers and the Cash Receipts Book | IDO | 2 | CT-063 | Job run log; CRB lists the day's receipts |

## 5.7 Phase G - Hypercare

Table 15: Phase G - Hypercare

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-065 | T+1 | Daily hypercare check - Migration Clearing 0.00, legacy control accounts vs sub-ledgers, automatch results, exception queues, failed jobs (daily until exit) | IML | 1 | CT-064 | Daily hypercare report |
| CT-066 | T+1 | Defect triage twice a day (10:00 and 16:00) with Operations, Comptrollership and iorta QA | IQA | 1 | CT-064 | Defect log updated; severity agreed |
| CT-067 | T+2 | First remittance extraction with legacy invoices for the main insurers; compare with the legacy remittance pattern | OPS | 4 | CT-064 | Schedules show legacy invoice numbers; OPS_REMITTANCE posts to DTIP legacy |
| CT-068 | T+3 | First Collections worklist refresh with legacy invoices; collectors confirm carried promises and assignments | OPS | 2 | CT-064 | Worklist counts agree with F03 |
| CT-069 | T+5 | Staging purge - payloads and intake files of the signed-off production batches deleted within 5 days (MIG_STAGING_PURGE) | IDO | 1 | CT-055 | No staging payload older than 5 days after sign-off; purge log |
| CT-070 | T+1 | Renewal - carried candidates created with source LEGACY in their stage; catch-up extraction of the headers expiring T to T+140 without a carried candidate; first daily extraction (expiry T+141) | MKT | 2 | CT-046 | Carried and catch-up candidate counts equal the completeness check; first placements of January expiries under way |
| CT-071 | T+7 | Week-1 review with the board - defects, volumes, performance, user feedback | GNG | 2 | CT-065 | Minutes; actions |
| CT-072 | T+10 | First DPPR or PR2307 legacy reversal batch (if any) approved and posted | COMP | 4 | CT-064 | Run report; legacy sub-ledgers reduced by the batch total |
| CT-073 | T+14 | Hypercare mid-point review against the exit criteria | GNG | 2 | CT-071 | Criteria status recorded |
| CT-074 | T+30 | First month-end close with legacy control accounts; ACSL GL-SL reconciliation with context LEGACY | COMP | 16 | CT-073 | ACSL reconciliation without difference; FRBS schedules include legacy balances |
| CT-075 | T+30 | Hypercare exit decision | GNG | 2 | CT-074 | Exit criteria met; hand-over to production support (L1 / L2 / L3) |

# 6 Rollback

The rollback returns BDOI to legacy with no loss of data. It is available until the point of no return, the end-of-day review on T at 18:00 (DMQ32). The rollback point is the production database snapshot taken at T-2 02:00 (task CT-037), before any open item, header or trial balance is loaded; reference data and clients pre-loaded before it stay loaded and are harmless because legacy stays the system of record until go-live.

Table 16: Rollback procedure

| Step | Name | Action | Owner |
| --- | --- | --- | --- |
| RB-1 | Stop | The go / no-go board records NO-GO (or a failure before T 18:00 that the board judges unrecoverable). The Program Manager announces the rollback on the bridge. | GNG |
| RB-2 | Lock BIBS | Disable business logins to BIBS; stop the scheduled jobs (PAYMENT_AUTOMATCH, payment file handlers, Renewal extraction, e-mail dispatch). | IDO |
| RB-3 | Capture | If business transactions were keyed in BIBS after 08:00 on T, export them (receipts, applications, bookings) with MIG-CUTOVER-STATUS and the Operations reports for re-keying in legacy. | IML |
| RB-4 | Restore | Restore the production database to the rollback-point snapshot (CT-037); restore the object store for attachments of the same time; verify the restore (row counts of key tables, application start). | IDO |
| RB-5 | Reopen legacy | Set EBIX, QPS and CMS back to read-write; re-enable the legacy batch jobs; confirm the last legacy EOD is intact. | BIT |
| RB-6 | Re-key | Operations re-keys in legacy the transactions captured in RB-3, with the BIBS AR numbers voided in the receipt register. | OPS |
| RB-7 | Communicate | Send the rollback notice to users, branches, insurers and bank channels (communication plan item 7). | PM |
| RB-8 | Review | Within 2 business days - root cause, new go-live date, which mocks to repeat; purge the production staging of the failed cutover within 5 days. | PM |

After the point of no return, there is no technical rollback. A defect is fixed forward in BIBS through the normal business functions (correction, reversal, adjustment), with the change visible in the Prod Recon legacy change report where it touches a legacy invoice.

# 7 Communication plan

Table 17: Communication plan

| # | Message | Audience | Channel | When | Owner |
| --- | --- | --- | --- | --- | --- |
| 1 | Go-live date, freeze and what changes for each department | All BDOI users, branch heads | E-mail from the Program Manager; team briefings | T-21 | PM |
| 2 | Payments after go-live - legacy invoice numbers stay valid; new invoices are BI- numbers | Insurers, BDO bank channels (bills payment, CLPC, direct credit), corporate clients | Letter / e-mail from Operations | T-21 | OPS |
| 3 | Freeze of reference data and the change request route | Product, Marketing and Operations maintainers | E-mail from the Data Migration Lead | T-8 | DML |
| 4 | Training schedule and log-in instructions | All BIBS users per persona | E-mail; training calendar | T-20 | PM |
| 5 | Last legacy business day T-5 (29 December); legacy freeze at T-3 22:00; BIBS opens T 08:00; what to do with urgent items over the holidays | All users, branches, insurers | E-mail; branch notice | T-5 | PM |
| 6 | Go-live confirmed; support channels and hypercare contacts | All users | E-mail; intranet | T-1 19:00 | PM |
| 7 | Rollback notice (only if NO-GO) - legacy stays in use; next steps | All users, branches, insurers, bank channels | E-mail; phone tree for branch heads | T-1 on NO-GO | PM |
| 8 | Daily hypercare status | Go / no-go board, department heads | Daily report and bridge call 17:00 | T to hypercare exit | IPM |
| 9 | Hypercare exit and hand-over to production support | All users, IT | E-mail | At exit | PM |

# 8 Hypercare

Hypercare runs from go-live to the first month-end close with the legacy control accounts (about T+30). The command centre stays open to T+5, then the daily 17:00 call continues until exit.

Daily checks (task CT-065): Migration Clearing 0.00 per branch and currency; legacy control accounts against their sub-ledgers (ACSL, context LEGACY); automatch runs and the unapplied items they left; payment file results; exception queues (rejected receipts, remittance exclusions, failed postings); failed jobs and alerts; open defects by severity; user tickets by department.

## 8.1 Roster

Table 18: Hypercare roster (names in the task plan, sheet Hypercare Roster)

| Function | Who | Coverage | Escalates to |
| --- | --- | --- | --- |
| Command centre lead | iorta TechNXT Project Manager | 07:00-20:00 T to T+5; 08:00-18:00 after | Program Manager |
| Migration and reconciliation | iorta Migration Lead; Migration Operator | 07:00-22:00 T to T+5; business hours after | iorta Project Manager |
| Application support (L2 / L3) | iorta developers - Operations, Accounting, CRM, Renewal | 07:00-20:00 T to T+5; on call to 22:00 | iorta Project Manager |
| Infrastructure | iorta DevOps | 24 x 7 on call T-3 to T+5; business hours after | iorta Project Manager |
| Business floor support | BDOI super-users per department (Cashiering, Remittance, Collections, Accounting, Marketing) | Branch hours T to T+10 | Data Migration Lead |
| Comptrollership | Reconciliation approver; GL lead | Daily 16:00 check T to first month-end | Head, Comptrollership |
| Legacy systems | BDOI IT legacy administrator | Business hours; on call T-3 to T+1 | BDOI IT head |
| Service desk (L1) | BDOI service desk | Service hours | BDOI IT head |

## 8.2 Exit criteria

Table 19: Hypercare exit criteria

| # | Exit criterion |
| --- | --- |
| 1 | No open Critical or High defect; Medium defects have an agreed fix date |
| 2 | Migration Clearing 0.00 and legacy control accounts equal their sub-ledgers on 10 consecutive business days |
| 3 | First month-end close completed with the ACSL GL-SL reconciliation (context LEGACY) without difference |
| 4 | Payment files, automatch, remittance, DPPR / PR2307 batches and endorsements on legacy invoices each processed at least once in production without incident |
| 5 | Staging and extract files of production purged within 5 days of sign-off (purge log) |
| 6 | Service desk ticket volume back to the level agreed in the support model; production support runbook (deliverable 24) accepted |

# 9 Decommissioning checklists

A legacy system is decommissioned only when every item of its checklist is met and signed (FR-DM-123; DMQ27). The legacy context in BIBS closes separately, when the legacy positions have run off. The words before the dash are the default criterion names that the Migration Console and its messages use.

Table 20: Decommissioning checklist - EBIX

| # | Criterion |
| --- | --- |
| 1 | Final extracts reconciled - F01, F02, F03, F04, F06, G01 and C01 signed off |
| 2 | Archive reconciled - archive objects H01, H02 and G02 of EBIX loaded and reconciled (counts and hash totals per record type against legacy) |
| 3 | Legacy Inquiry verified - by Audit / Compliance on samples of each record type |
| 4 | No open item needs the system - no open legacy invoice or legacy UPP needs an EBIX document; the legacy context in BIBS may still be open |
| 5 | Claims tail covered - no open claim that needs EBIX (DMQ27, DMQ30) |
| 6 | Access logs archived - read-only access logs exported to the archive |
| 7 | Retention covered - database backup retained per the retention decision (DMQ27); retention obligations covered (5 years online, 15 years archive, umbrella p.45) |
| 8 | Owners signed - EBIX system owner, Compliance and Comptrollership |

Table 21: Decommissioning checklist - QPS

| # | Criterion |
| --- | --- |
| 1 | Final extracts reconciled - C01, P01, P03 and the R objects signed off |
| 2 | No open item needs the system - last QPS-issued policy expired and its renewal decided (run-off tracker shows no open cohort), or the policy is archived |
| 3 | Archive reconciled - archive objects of QPS loaded and reconciled |
| 4 | Legacy Inquiry verified - by Audit / Compliance |
| 5 | Access logs archived - read-only access logs exported to the archive |
| 6 | Retention covered - database backup retained per DMQ27 |
| 7 | Owners signed - QPS system owner, Compliance and the Heads of Marketing |

Table 22: Decommissioning checklist - ISYS

| # | Criterion |
| --- | --- |
| 1 | No open item needs the system - claims and ACSL reports and the Marketing Diary replaced by BIBS reports |
| 2 | Archive reconciled - GL history (G02) and closed claims (H01 CLAIM) archived and reconciled |
| 3 | Owners signed - ISYS system owner, Claims and Comptrollership |

Table 23: Decommissioning checklist - CMS

| # | Criterion |
| --- | --- |
| 1 | Final extracts reconciled - collection state F03 and UPP F02 reconciled and signed off |
| 2 | Archive reconciled - disposition history archived (H01) if required by DMQ34 |
| 3 | Owners signed - Head of Operations (Collections) and BDOI IT |

Table 24: Decommissioning checklist - Excel masterlists and file shares

| # | Criterion |
| --- | --- |
| 1 | Final extracts reconciled - submitted-policy masterlists migrated (P04) or archived |
| 2 | Archive reconciled - KYC documents and legacy documents (C04, H02) archived with checksums |
| 3 | Retention covered - folders set to read-only, then removed per the retention decision |
| 4 | Owners signed - owning department and Compliance |

Table 25: Decommissioning checklist - Legacy context in BIBS

| # | Criterion |
| --- | --- |
| 1 | No open legacy invoice - every legacy invoice paid, reversed, written off or reclassified |
| 2 | No legacy UPP balance - every legacy UPP applied, refunded or reclassified |
| 3 | Legacy accounts at zero - legacy control accounts and Migration Clearing at 0.00 |
| 4 | Chart decision recorded - Comptrollership decides whether the legacy accounts are closed in the chart |

# Sign-off

By signing, BDOI approves this runbook as the plan of the production cutover. The confirmed go-live date (M6), the named people and the measured durations are added in version 1.2 after the dress rehearsal.

| Name | Role | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
|  | Program Manager, Business Project Services (chair, go / no-go board) | BDO Unibank ESG |  |  |
|  | Data Migration Lead | BDOI |  |  |
|  | Head, Operations | BDOI |  |  |
|  | Head, Comptrollership | BDOI |  |  |
|  | Head, BDOI IT | BDOI |  |  |
|  | Project Manager | iorta TechNXT |  |  |