## Start here
Master Data and Configuration Upload Templates
Every master, reference and configuration dataset BIBS needs before go-live, with the templates in the order the data is loaded
Client |  | BDO Insurance and Reinsurance Brokers, Inc.
Scope |  | Every master, reference and configuration dataset BIBS needs before go-live, all BRDs
Version and date |  | Version 1.1, 8 October 2026
Go-live |  | Go-live is proposed for Monday 3 January 2028 (T), at the year-end boundary (option A of the Data Migration set, for Comptrollership to confirm).
Owner |  | Program Manager, Business Project Services, with the BDOI owner of each dataset
Prepared by |  | iorta TechNXT
Classification |  | Confidential
How to fill in this workbook
1 | The index below lists every master, reference and configuration dataset BIBS needs before go-live, one template sheet each, in the order the data is loaded: a dataset whose codes others use comes first (Loads after names the templates it depends on). Each template has the column layout BIBS loads.
2 | Load route: Screen upload (5 templates) - the filled-in sheet is uploaded on the named screen, which checks every row; Migration Console (15) - the data is extracted from the legacy systems by BDOI IT in this layout and loaded by the Data Migration Console; Configuration screen (0) - upload on the screen being added; until then BDOI fills the template and it is loaded on the screen with maker-checker (sheet Gaps). Every record is authorised by a second user.
3 | On a template sheet, read the header block (purpose, who fills it in, how it is loaded, due, depends on) and the guide above each column (Mandatory, Format, Allowed values, What to enter; * marks a mandatory column). Overwrite or delete the grey example row and enter one row per record. Drop-downs offer the allowed values (sheet Reference lists) and the codes of the templates filled in before; a mandatory cell left empty turns red. For a large legacy dataset (clients, opening balances) BDOI IT sends the extract file in the layout instead of typing it.
4 | The review sheets (lists of values, system parameters, SLA and turnaround, numbering prefixes, notification events, document templates, accounting events) list what the platform delivers; write the value wanted or the decision on each row you own. The sheet Configured on screens lists the set-up decided in working sessions and entered directly on the screens.
5 | Set the Status of each template, follow Rows entered and Mandatory cells missing, raise questions on the sheet Questions and comments, and return the workbook to the iorta TechNXT project team by each due date. The owner confirms each template (Confirmed by and Date on the sheet) before it is loaded; the guide (BIBS_Templates_BRD-00_Master_Data_Upload_Guide_v1.1) explains the validation and the sign-off of the master data.
Index of the datasets in load order (dependencies first)
Step | ID | Dataset | Group | BRD | Drop | Provided by | Load route | Entered or loaded on | Loads after | Due | Rows entered | Mandatory cells missing | Status | Open
1 | D0-02 | Branches | Organisation | BRD-05 | Drop 1 | Head, Comptrollership | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › Setup › Branches | - | 4-Jan-2027 – Platform set-up for Drop 1 SIT |  |  | Not started | D0-02 →
2 | D0-04 | Cost centres and business lines | Organisation | BRD-05 | Drop 1 | Head, Comptrollership | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › Setup › Dimensions | - | 4-Jan-2027 – Platform set-up for Drop 1 SIT |  |  | Not started | D0-04 →
3 | D0-07 | Account categories and numbering | Chart of accounts, tax and accounting | BRD-05 | Drop 1 | Head, Comptrollership | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Finance › General Ledger › Chart of Accounts | - | 4-Jan-2027 – Platform set-up for Drop 1 SIT |  |  | Not started | D0-07 →
4 | MD-02 | Currencies | Chart of accounts, tax and accounting | BRD-05 | Drop 1 | Head, Comptrollership (Treasury) | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › Setup › Currencies & Rates | - | 4-Jan-2027 – Platform set-up for Drop 1 SIT |  |  | Not started | MD-02 →
5 | PM-09 | Lists of values and parameters | Products, packages and rates | BRD-03 | Drop 0 | Product Owner, MBS; System Administrator (entry) | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › Broking Setup › Lists of Values | - | 16-Jul-2027 – Values for UAT |  |  | Not started | PM-09 →
6 | R01 | Lists of values and MIS values | Clients and KYC | BRD-13 | Drop 0 | MBS data steward (to name); approved by Product Owner, Marketing Business System (MBS); extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | - | M3 (29 Jan 2027) |  |  | Not started | R01 →
7 | R04 | Insurers | Insurers, partners, intermediaries and payees | BRD-03 | Drop 0 | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | - | M3 (29 Jan 2027) |  |  | Not started | R04 →
8 | UA-02 | Role-to-permission matrix | Users, access and approvals | BRD-11 | Drop 0 | Business Administration with the unit heads; reviewed and signed by BDOI Information Security | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › User Access › Group Profile Requests | - | 9-Apr-2027 – Reference data for Trial migration 1 (M4) |  |  | Not started | UA-02 →
9 | UA-06 | Lists of values | Users, access and approvals | BRD-11 | Drop 0 | Business Administration | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Lists of Values (New Business set) under maker-checker | - | 1-Nov-2027 – before the templates that use its codes |  |  | Not started | UA-06 →
10 | D0-05 | Employees | Organisation | BRD-05 | Drop 1 | Human Resources; Head, Comptrollership | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › Setup › Employees | D0-02, D0-04 | 16-Jul-2027 – Values for UAT |  |  | Not started | D0-05 →
11 | D0-06 | Chart of accounts | Chart of accounts, tax and accounting | BRD-05 | Drop 1 | Head, Comptrollership | Screen upload | Finance › General Ledger › Chart Upload | D0-07 | 4-Jan-2027 – Platform set-up for Drop 1 SIT |  |  | Not started | D0-06 →
12 | MD-01 | Business partners (reinsurers, intermediaries, suppliers) | Insurers, partners, intermediaries and payees | BRD-05 | Drop 1 | Head, Comptrollership; Head, Operations for the reinsurers and intermediaries | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › Setup › Business Partners | D0-02 | 9-Apr-2027 – Reference data for Trial migration 1 (M4) |  |  | Not started | MD-01 →
13 | R03 | Sales organisation (units and account officers) | Organisation | BRD-01 | Drop 1 | Marketing data steward (to name); approved by Heads, Retail and Corporate Marketing; extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | D0-02, D0-04 | M3 (29 Jan 2027) |  |  | Not started | R03 →
14 | R05 | Product lines, cover types, products and risk codes | Products, packages and rates | BRD-03 | Drop 0 | MBS data steward (to name); approved by Product Owner, MBS; extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | PM-09 | M3 (29 Jan 2027) |  |  | Not started | R05 →
15 | UA-01 | Users and roles load | Users, access and approvals | BRD-11 | Drop 0 | Business Administration, with the unit heads who name their users | Screen upload | Setup & Administration › User Access › Bulk Request | UA-06, UA-02 | 1-Nov-2027 – Production values before the dress rehearsal |  |  | Not started | UA-01 →
16 | D0-03 | Holiday calendar | Organisation | BRD-05 | Drop 1 | Head, Comptrollership; Human Resources | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › Setup › Holiday Calendar | D0-02 | 4-Jan-2027 – Platform set-up for Drop 1 SIT |  |  | Not started | D0-03 →
17 | MD-03 | Exchange rates and their source | Chart of accounts, tax and accounting | BRD-05 | Drop 1 | Head, Comptrollership (Treasury) | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › Setup › Currencies & Rates | MD-02 | 16-Jul-2027 – Values for UAT |  |  | Not started | MD-03 →
18 | R02 | Branches and invoicing branches | Organisation | BRD-05 | Drop 1 | Comptrollership data steward (to name); approved by Head, Comptrollership; extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | D0-02 | M3 (29 Jan 2027) |  |  | Not started | R02 →
19 | R04B | Insurer branches | Insurers, partners, intermediaries and payees | BRD-03 | Drop 0 | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | R04 | M3 (29 Jan 2027) |  |  | Not started | R04B →
20 | R11 | Receipt series in use | Banks, bank accounts and cheque books | BRD-02 | Drop 1 | Cashiering data steward (to name); approved by Operations - Financial Transactions; extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | D0-02 | M3 (29 Jan 2027); final at T-3 |  |  | Not started | R11 →
21 | UA-04 | Separation-of-duties rules | Users, access and approvals | BRD-11 | Drop 0 | BDOI Information Security | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › User Access › Separation of Duties | UA-02 | 16-Jul-2027 – Values for UAT |  |  | Not started | UA-04 →
22 | UP-01 | Clients not held in the legacy systems | Clients and KYC | BRD-01 | Drop 1 | Heads, Retail and Corporate Marketing; Product Owner, MBS | Screen upload | Client & Policy › Clients › Clients | R01 | 16-Jul-2027 – Values for UAT |  |  | Not started | UP-01 →
23 | C01 | Client master | Clients and KYC | BRD-01 | Drop 1 | Marketing data steward (to name); approved by Product Owner, MBS; Heads, Retail and Corporate Marketing; extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | R01, R03, D0-02 | M3 (29 Jan 2027); deltas daily from T-14 days |  |  | Not started | C01 →
24 | D0-10 | Tax codes | Chart of accounts, tax and accounting | BRD-05 | Drop 1 | Head, Comptrollership (Tax) | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Finance › Tax & Statutory › Tax Codes & Forms | D0-06 | 16-Jul-2027 – Values for UAT |  |  | Not started | D0-10 →
25 | D0-11 | Company bank accounts | Banks, bank accounts and cheque books | BRD-05 | Drop 1 | Head, Comptrollership; Treasury | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Finance › Disbursement › Bank Accounts and Checks | D0-06, D0-02 | 4-Jan-2027 – Platform set-up for Drop 1 SIT |  |  | Not started | D0-11 →
26 | PM-01 | Product catalogue | Products, packages and rates | BRD-03 | Drop 0 | Product Owner, Marketing Business System (MBS) | Migration Console | Client & Policy › Product Maintenance › Products | PM-09, R05 | 9-Apr-2027 – Reference data for Trial migration 1 (M4) |  |  | Not started | PM-01 →
27 | R08 | Chart of accounts mapping | Chart of accounts, tax and accounting | BRD-05 | Drop 1 | Comptrollership data steward (to name); approved by Head, Comptrollership; Product Owner FRBS and ACSL; extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | D0-06 | M3 (29 Jan 2027) |  |  | Not started | R08 →
28 | UP-02 | Payees | Insurers, partners, intermediaries and payees | BRD-05 | Drop 1 | Product Owner, Comptrollership - Disbursement | Screen upload | Finance › Disbursement › Disbursement Uploads | MD-01 | 9-Apr-2027 – Reference data for Trial migration 1 (M4) |  |  | Not started | UP-02 →
29 | D0-01 | Company | Organisation | BRD-05 | Drop 1 | Head, Comptrollership | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › Setup › Companies | D0-06 | 4-Jan-2027 – Platform set-up for Drop 1 SIT |  |  | Not started | D0-01 →
30 | D0-08 | Accounting rules | Chart of accounts, tax and accounting | BRD-05 | Drop 1 | Head, Comptrollership | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Finance › Accounting Engine › Accounting Rules | D0-04, D0-06 | 4-Jan-2027 – Platform set-up for Drop 1 SIT |  |  | Not started | D0-08 →
31 | D0-09 | Legacy control accounts | Chart of accounts, tax and accounting | BRD-05 | Drop 1 | Head, Comptrollership | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Finance › General Ledger › Chart of Accounts | D0-06 | 1-Dec-2026 – Drafts with the Drop 0 sign-off |  |  | Not started | D0-09 →
32 | D0-15 | Approval limits and matrices | Users, access and approvals | BRD-00 | Programme | Owners of the modules; Head, Comptrollership for the amounts | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Submitted Policies Setup, EB Setup, Compliance Setup (Configuration Versions) and Disbursement approver routing | UA-02, UA-01 | 16-Jul-2027 – Values for UAT |  |  | Not started | D0-15 →
33 | R07 | Commission rates by insurer and product | Insurers, partners, intermediaries and payees | BRD-03 | Drop 0 | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | R04, R05 | M3 (29 Jan 2027) |  |  | Not started | R07 →
34 | TX-02 | Tax forms and filing calendar | Chart of accounts, tax and accounting | BRD-05 | Drop 1 | Head, Comptrollership (Tax) | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Finance › Tax & Statutory › Tax Codes & Forms | D0-06 | 16-Jul-2027 – Values for UAT |  |  | Not started | TX-02 →
35 | UA-03 | Approvers, approval rules and limits | Users, access and approvals | BRD-11 | Drop 0 | Business Administration; BDOI Information Security for the second approval; Comptrollership for the authorisation limits | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › User Access › New Request | UA-01 | 16-Jul-2027 – Values for UAT |  |  | Not started | UA-03 →
36 | PM-02 | Coverages, perils and field rules | Products, packages and rates | BRD-03 | Drop 0 | MBS | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Client & Policy › Product Maintenance › Coverages & Clauses | PM-09, PM-01 | 16-Jul-2027 – Values for UAT |  |  | Not started | PM-02 →
37 | PM-03 | Clause library | Products, packages and rates | BRD-03 | Drop 0 | TSU (wordings); MBS (maintenance) | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Client & Policy › Product Maintenance › Coverages & Clauses | PM-09, PM-01 | 16-Jul-2027 – Values for UAT |  |  | Not started | PM-03 →
38 | C02 | Client addresses and contacts | Clients and KYC | BRD-01 | Drop 1 | Marketing data steward (to name); approved by Product Owner, MBS; Heads, Retail and Corporate Marketing; extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | C01 | M3 (29 Jan 2027); deltas daily from T-14 days |  |  | Not started | C02 →
39 | C03 | Client payout accounts | Clients and KYC | BRD-05 | Drop 1 | Disbursement data steward (to name); approved by Product Owner, Comptrollership - Disbursement; extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | C01 | M3 (29 Jan 2027) |  |  | Not started | C03 →
40 | D0-12 | Check books | Banks, bank accounts and cheque books | BRD-05 | Drop 1 | Treasury; Product Owner, Comptrollership - Disbursement | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Finance › Disbursement › Bank Accounts and Checks | D0-11 | 1-Nov-2027 – Production values before the dress rehearsal |  |  | Not started | D0-12 →
41 | D0-13 | Petty cash funds | Banks, bank accounts and cheque books | BRD-05 | Drop 1 | Head, Comptrollership | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Finance › Payables & Cash › Petty Cash | D0-02, D0-05, D0-06, D0-11 | 1-Nov-2027 – Production values before the dress rehearsal |  |  | Not started | D0-13 →
42 | D0-14 | Bank statement layouts | Banks, bank accounts and cheque books | BRD-05 | Drop 1 | Head, Comptrollership; Treasury | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › Setup › Bank Statement Layouts | D0-11 | 16-Jul-2027 – Values for UAT |  |  | Not started | D0-14 →
43 | G01 | GL opening trial balance | Chart of accounts, tax and accounting | BRD-05 | Drop 1 | Comptrollership data steward (to name); approved by Head, Comptrollership; extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | R08, D0-02 | M3 (29 Jan 2027); final at T-2; at each true-up |  |  | Not started | G01 →
44 | PM-04 | Rate tables | Products, packages and rates | BRD-03 | Drop 0 | Product Owner, MBS; Comptrollership (taxes) | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Client & Policy › Product Maintenance › Rates & Taxes | PM-01 | 16-Jul-2027 – Values for UAT |  |  | Not started | PM-04 →
45 | PM-10 | Incentive criteria | Products, packages and rates | BRD-03 | Drop 0 | Incentive Maintenance user (MBS); Comptrollership (CPC2 definition, PQ04) | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Client & Policy › Product Maintenance › Incentive Criteria | PM-09, PM-01 | 16-Jul-2027 – Values for UAT |  |  | Not started | PM-10 →
46 | TX-01 | Party tax profiles (clients, insurers, payees) | Chart of accounts, tax and accounting | BRD-05 | Drop 1 | Head, Comptrollership (Tax) | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Finance › Tax & Statutory › Party Tax Profiles | D0-10, R04, C01, MD-01, UP-02 | 16-Jul-2027 – Values for UAT |  |  | Not started | TX-01 →
47 | PM-06 | Packages in force at go-live | Products, packages and rates | BRD-03 | Drop 0 | TSU (prepares); Product Owner, MBS (approves) | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Client & Policy › Product Maintenance › New Package Request | PM-01, PM-02, R04, PM-03 | 1-Nov-2027 – Production values before the dress rehearsal |  |  | Not started | PM-06 →
48 | R06 | Package code map (legacy package to BIBS package version) | Products, packages and rates | BRD-03 | Drop 0 | TSU (to name); approved by Product Owner, MBS (approves); TSU (prepares); extracted by BDOI IT | Migration Console | Data Migration › Data Migration › Extracts and Batches | R05, PM-06 | M5 (18 Jun 2027); final at T-7 |  |  | Not started | R06 →
49 | PM-08 | Document templates | Products, packages and rates | BRD-03 | Drop 0 | TSU and MBS (texts); Business Administrator (maintenance) | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › Broking Setup › Document Templates | - | 16-Jul-2027 – Values for UAT |  |  | Not started | PM-08 →
50 | UA-05 | Password, session and sign-in parameters | Users, access and approvals | BRD-11 | Drop 0 | BDOI Information Security; BDOI IT for the sign-in mode | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker) | Setup & Administration › Administration › System Parameters | - | 16-Jul-2027 – Values for UAT |  |  | Not started | UA-05 →
51 | UP-03 | Watchlist entries (sanctions, PEP and internal lists) | Compliance | BRD-10 | Drop 1 | Compliance (Chief Compliance Officer) | Screen upload | Setup & Administration › Compliance Setup › List Sources and Runs | - | 16-Jul-2027 – Values for UAT |  |  | Not started | UP-03 →
Groups of datasets
Group |  |  | Templates | [5 empty] | Upload |  | Migration Console |  | Configuration screen
Organisation |  |  | D0-01, D0-02, R02, D0-03, D0-04, D0-05, R03 | [5 empty] | 0 |  | 2 |  | 5
Users, access and approvals |  |  | UA-06, UA-02, UA-01, UA-03, UA-04, UA-05, D0-15 | [5 empty] | 1 |  | 0 |  | 6
Chart of accounts, tax and accounting |  |  | D0-07, D0-06, R08, D0-09, D0-08, D0-10, TX-02, TX-01, MD-02, MD-03, G01 | [5 empty] | 1 |  | 2 |  | 8
Banks, bank accounts and cheque books |  |  | D0-11, D0-12, D0-13, D0-14, R11 | [5 empty] | 0 |  | 1 |  | 4
Products, packages and rates |  |  | PM-09, R05, PM-01, PM-02, PM-03, PM-04, PM-06, R06, PM-10, PM-08 | [5 empty] | 0 |  | 3 |  | 7
Insurers, partners, intermediaries and payees |  |  | R04, R04B, R07, MD-01, UP-02 | [5 empty] | 1 |  | 3 |  | 1
Clients and KYC |  |  | R01, C01, C02, C03, UP-01 | [5 empty] | 1 |  | 4 |  | 0
Compliance |  |  | UP-03 | [5 empty] | 1 |  | 0 |  | 0
Due milestones
Due | Milestone |  |  |  | Due date |  | Before go-live |  | Why this date
D1 | Drafts with the Drop 0 sign-off |  |  |  | 1-Dec-2026 |  | T-56 weeks |  | Sign-off of BRD-11 on 1-Dec-2026, the last of the three Drop 0 sets
D2 | Platform set-up for Drop 1 SIT |  |  |  | 4-Jan-2027 |  | T-52 weeks |  | Drop 1 SIT runs Jan - Jul 2027 on the BDOI organisation, chart of accounts and banks
D3 | Reference data for Trial migration 1 (M4) |  |  |  | 9-Apr-2027 |  | T-38 weeks |  | Extracts for Trial migration 1; reference data and clients first
D4 | Code maps approved (M5) |  |  |  | 18-Jun-2027 |  | T-28 weeks |  | Code maps approved for Trial migration 2, including the package code map
D5 | Values for UAT |  |  |  | 16-Jul-2027 |  | T-24 weeks |  | UAT plans and sign-off forms due 16-Jul-2027; UAT Aug - Dec 2027 runs on the production values
D6 | Production values before the dress rehearsal |  |  |  | 1-Nov-2027 |  | T-9 weeks |  | Dress rehearsal in November 2027; the values loaded for it are the go-live values
D7 | Map freeze (T-7) |  |  |  | 27-Dec-2027 |  | T-1 weeks |  | No change of a code map or reference value after the freeze except by change request
Other sheets
Sheet |  |  | What it holds
Lists of values |  |  | Every list of values of BIBS with its owner and its route: legacy values mapped through the Migration Console (R01), the others entered on Lists of Values
System parameters |  |  | Every system parameter of BIBS (other than the SLA and turnaround parameters and the numbering prefixes) with the value proposed and the value BDOI wants
SLA and turnaround |  |  | The SLA, turnaround, reminder, escalation and ageing parameters: days and hours of the work queues, insurer replies, reminders and alerts
Numbering prefixes |  |  | Prefixes of the numbered documents; receipt series come from R11, check numbers from D0-12
Notification events |  |  | Every notification event with its default channels and the unit mailbox that also receives it; users choose their own channels in Notification Settings
Document templates |  |  | Every generated document and letter with the unit that gives its BDOI wording and layout; the layout is uploaded as a Word file on Document Templates
Accounting events |  |  | The accounting events that need a rule of template D0-08 (accounting rules mapping); owner Head, Comptrollership
PM-04 Charges checklist |  |  | Premium charges billed to clients: one row per charge with the rule BIBS applies
D0-10 Tax checklist |  |  | BDOI's own taxes: one row per kind of tax, what BIBS does and what it does not hold
Configured on screens |  |  | Set-up decided in working sessions and entered on the screens (no template)
Gaps |  |  | Datasets without an upload route, and data BIBS does not hold (questions)
Coverage check |  |  | The datasets asked about and where each is, or why BIBS does not hold it
Reference lists |  |  | Every list of allowed values of the drop-downs, with code and label
Questions and comments |  |  | Questions and comments per template and column, with the answer
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## D0-02 Branches
D0-02 Branches | [11 empty] | Step 1 of 51
← Back to Start here | Step 1 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [10 empty] | Ask a question →
Purpose | Every BDOI branch and invoicing branch
Provided by | Head, Comptrollership
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Branches (Setup & Administration), before the first migration mock; the legacy branches are mapped to them by the code map BRANCH (object R02)
Source | BDOI branch list; EBIX branch codes for the code map BRANCH
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | No | Yes | Yes | Yes | No | No | No | No | No
Format | Up to 10 capitals | Up to 120 characters | Text | Text | dd-MMM-yyyy | Y or N | Y or N | Text | E-mail address | Name | SAT, SUN | EBIX codes separated by commas
Allowed values | Free entry, up to 10 characters | Free entry, up to 120 characters | Free entry | Free entry | A date, for example 15-Jan-2028 | Y or N | Y or N | Free entry | Free entry | Free entry | Free entry | Free entry
What to enter | Code of the branch; unique | Name shown on screens and documents | Region of the branch | Address printed on documents | Date the branch opened | Y for one branch only | May receive and pay in foreign currency | Branch telephone | Branch mailbox | Head of the branch | Days the branch is closed each week | For the code map BRANCH (R02)
Row | Branch code * | Branch name * | Region | Address | Opening date * | Head office * | Foreign currency authorised * | Contact phone | Contact e-mail | Branch manager | Weekly rest days | Legacy branch codes
Example – overwrite or delete | HO | Head Office | NCR | 7899 Makati Avenue, Makati City | 2010-01-01 | Y | Y | (02) 8888-0000 | ho@bdoi.example.ph |  | SAT,SUN | 001
Note on B16: Branch code Code of the branch; unique Mandatory: Yes Format: Up to 10 capitals Allowed values: Free entry, up to 10 characters Example: HO
Note on C16: Branch name Name shown on screens and documents Mandatory: Yes Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: Head Office
Note on D16: Region Region of the branch Mandatory: No Format: Text Allowed values: Free entry Example: NCR
Note on E16: Address Address printed on documents Mandatory: No Format: Text Allowed values: Free entry Example: 7899 Makati Avenue, Makati City
Note on F16: Opening date Date the branch opened Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Jan-2010
Note on G16: Head office Y for one branch only Mandatory: Yes Format: Y or N Allowed values: Y or N Example: Y
Note on H16: Foreign currency authorised May receive and pay in foreign currency Mandatory: Yes Format: Y or N Allowed values: Y or N Example: Y
Note on I16: Contact phone Branch telephone Mandatory: No Format: Text Allowed values: Free entry Example: (02) 8888-0000
Note on J16: Contact e-mail Branch mailbox Mandatory: No Format: E-mail address Allowed values: Free entry Example: ho@bdoi.example.ph
Note on K16: Branch manager Head of the branch Mandatory: No Format: Name Allowed values: Free entry
Note on L16: Weekly rest days Days the branch is closed each week Mandatory: No Format: SAT, SUN Allowed values: Free entry Example: SAT,SUN
Note on M16: Legacy branch codes For the code map BRANCH (R02) Mandatory: No Format: EBIX codes separated by commas Allowed values: Free entry Example: 001

## D0-04 Dimensions
D0-04 Cost centres and business lines |  |  |  |  | Step 2 of 51
← Back to Start here | Step 2 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  | Ask a question →
Purpose | The values of the dimensions of journal lines
Provided by | Head, Comptrollership
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Dimensions (Setup & Administration); the legacy cost centres are mapped by the code map COST_CENTER
Source | Current cost centre list of Comptrollership; the product lines for the business lines
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes
Format | COST_CENTER or BUSINESS_LINE | Up to 20 capitals or digits | Up to 120 characters | Y or N
Allowed values | COST_CENTER, BUSINESS_LINE (list Dimension) | Free entry, up to 20 characters | Free entry, up to 120 characters | Y or N
What to enter | Dimension of the value | Code of the value | Name shown on screens and reports | N keeps the value for history only
Row | Dimension * | Code * | Name * | Active *
Example – overwrite or delete | COST_CENTER | FIN | Finance and Accounting | Y
Note on B16: Dimension Dimension of the value Mandatory: Yes Format: COST_CENTER or BUSINESS_LINE Allowed values: COST_CENTER, BUSINESS_LINE (list Dimension) Example: COST_CENTER
Note on C16: Code Code of the value Mandatory: Yes Format: Up to 20 capitals or digits Allowed values: Free entry, up to 20 characters Example: FIN
Note on D16: Name Name shown on screens and reports Mandatory: Yes Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: Finance and Accounting
Note on E16: Active N keeps the value for history only Mandatory: Yes Format: Y or N Allowed values: Y or N Example: Y

## D0-07 Categories and numbering
D0-07 Account categories and numbering | [7 empty] | Step 3 of 51
← Back to Start here | Step 3 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | The GL categories and the numbering scheme under each parent account
Provided by | Head, Comptrollership
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Chart of Accounts (General Ledger)
Source | The BDOI chart of accounts
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Conditional: CATEGORY | Conditional: CATEGORY | Conditional: CATEGORY | Conditional: CATEGORY | Conditional: NUMBERING | Conditional: NUMBERING | Conditional: NUMBERING
Format | CATEGORY or NUMBERING | Up to 20 capitals | Text | ASSET, LIABILITY, EQUITY, INCOME, EXPENSE | Y or N | Account code of D0-06 | . or - or none | 1 to 6
Allowed values | CATEGORY, NUMBERING (list Category or numbering row) | Free entry, up to 20 characters | Free entry | ASSET, LIABILITY, EQUITY, INCOME, EXPENSE (list Account class) | Y or N | Free entry | Free entry | A whole number from 1 to 6
What to enter | What the row defines | GL category | Name of the category | Class of the accounts of the category | Y for the accounts of bank accounts (D0-11) | Parent whose children are numbered | Between the parent code and the running number | Digits of the running number
Row | Row * | Category code | Category name | Account class | Bank category | Parent account | Separator | Width
Example – overwrite or delete | CATEGORY | CASH_IN_BANK | Cash in bank | ASSET | Y | 1110 | . | 2
Note on B16: Row What the row defines Mandatory: Yes Format: CATEGORY or NUMBERING Allowed values: CATEGORY, NUMBERING (list Category or numbering row) Example: CATEGORY
Note on C16: Category code GL category Mandatory: Conditional: CATEGORY Format: Up to 20 capitals Allowed values: Free entry, up to 20 characters Example: CASH_IN_BANK
Note on D16: Category name Name of the category Mandatory: Conditional: CATEGORY Format: Text Allowed values: Free entry Example: Cash in bank
Note on E16: Account class Class of the accounts of the category Mandatory: Conditional: CATEGORY Format: ASSET, LIABILITY, EQUITY, INCOME, EXPENSE Allowed values: ASSET, LIABILITY, EQUITY, INCOME, EXPENSE (list Account class) Example: ASSET
Note on F16: Bank category Y for the accounts of bank accounts (D0-11) Mandatory: Conditional: CATEGORY Format: Y or N Allowed values: Y or N Example: Y
Note on G16: Parent account Parent whose children are numbered Mandatory: Conditional: NUMBERING Format: Account code of D0-06 Allowed values: Free entry Example: 1110
Note on H16: Separator Between the parent code and the running number Mandatory: Conditional: NUMBERING Format: . or - or none Allowed values: Free entry Example: .
Note on I16: Width Digits of the running number Mandatory: Conditional: NUMBERING Format: 1 to 6 Allowed values: A whole number from 1 to 6 Example: 2

## MD-02 Currencies
MD-02 Currencies | [5 empty] | Step 4 of 51
← Back to Start here | Step 4 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | One row per currency BIBS accepts on transactions and bank accounts: the base currency PHP and each foreign currency BDOI deals in.
Provided by | Head, Comptrollership (Treasury)
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Configuration screen: Setup & Administration › Setup › Currencies & Rates, authorised by a second user
Source | BDOI currency list
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | Yes | Yes
Format | ISO 4217, 3 capitals | Text, up to 60 | Up to 5 characters | Whole number 0 to 4 | Y or N
Allowed values | Free entry, up to 3 characters | Free entry, up to 60 characters | Free entry, up to 5 characters | A whole number from 0 to 4 | Y or N
What to enter | Code of the currency | Name of the currency | Symbol printed on documents | Decimals of the amounts in the currency | Y when the currency may be used
Row | Currency code * | Name * | Symbol | Decimal places * | Active *
Example – overwrite or delete | USD | US dollar | $ | 2 | Y
Note on B16: Currency code Code of the currency Mandatory: Yes Format: ISO 4217, 3 capitals Allowed values: Free entry, up to 3 characters Example: USD
Note on C16: Name Name of the currency Mandatory: Yes Format: Text, up to 60 Allowed values: Free entry, up to 60 characters Example: US dollar
Note on D16: Symbol Symbol printed on documents Mandatory: No Format: Up to 5 characters Allowed values: Free entry, up to 5 characters Example: $
Note on E16: Decimal places Decimals of the amounts in the currency Mandatory: Yes Format: Whole number 0 to 4 Allowed values: A whole number from 0 to 4 Example: 2
Note on F16: Active Y when the currency may be used Mandatory: Yes Format: Y or N Allowed values: Y or N Example: Y

## PM-09 Lists and parameters
PM-09 Lists of values and parameters | [5 empty] | Step 5 of 51
← Back to Start here | Step 5 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The values of the Product Maintenance lists (request reasons, response outcomes, advisory groups, not-proceeded reasons, incentive types, coverage kinds, clause kinds, document types, market segments) and the parameters (numbering, reply days, expiry notice, advisory groups, service levels)
Provided by | Product Owner, MBS; System Administrator (entry)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Data migration object R01 for the values used by migrated records; the other values on Lists of Values and System Parameters
Source | Delivered values (FRS chapter 9) confirmed or changed by BDOI
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Conditional: list | Yes | No | No
Format | Code of the list or parameter | Up to 40 capitals | Text; number for a parameter | Number; Y or N | dd-MMM-yyyy
Allowed values | List Product Maintenance list or parameter: 23 values, see Reference lists | Free entry, up to 40 characters | Free entry | Free entry | A date, for example 15-Jan-2028
What to enter | For example PKG_REQUEST_REASON, PKG_SLA_NEGOTIATION | Code of the value | Label shown to users, or the parameter value | Display order and status | From when the value applies
Row | List or parameter * | Value code | Label or value * | Order / Active | Effective from
Example – overwrite or delete | PKG_REQUEST_REASON | LOSS_EXPERIENCE | Loss experience | 50; Y | 2026-11-01
Note on B16: List or parameter For example PKG_REQUEST_REASON, PKG_SLA_NEGOTIATION Mandatory: Yes Format: Code of the list or parameter Allowed values: List Product Maintenance list or parameter: 23 values, see Reference lists Example: PKG_REQUEST_REASON
Note on C16: Value code Code of the value Mandatory: Conditional: list Format: Up to 40 capitals Allowed values: Free entry, up to 40 characters Example: LOSS_EXPERIENCE
Note on D16: Label or value Label shown to users, or the parameter value Mandatory: Yes Format: Text; number for a parameter Allowed values: Free entry Example: Loss experience
Note on E16: Order / Active Display order and status Mandatory: No Format: Number; Y or N Allowed values: Free entry Example: 50; Y
Note on F16: Effective from From when the value applies Mandatory: No Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Nov-2026

## R01 Lists of values and MIS val
R01 Lists of values and MIS values | [7 empty] | Step 6 of 51
← Back to Start here | Step 6 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | One row per record of Lists of values and MIS values as extracted from QPS, EBIX. Key list_type, code. Sent as the file R01_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | MBS data steward (to name); approved by Product Owner, Marketing Business System (MBS); extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Migration Console: the file R01_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object R01; lands in: Lists of Values (maker-checker); MIS field catalogue
Source | QPS, EBIX
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | Known list name | Unique per list_type | Not blank | Parent exists in the file | Y or N | Valid date | Not before effective_from | 0 or more
Mandatory | Yes | Yes | Yes | No | Yes | No | No | No
Format | Code, up to 40; Upper case | Code, up to 40; As stored in legacy | Text, up to 200; Free text | Code, up to 40 | Flag, up to 1; Y or N | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Integer, up to 9; Digits
Allowed values | Legacy list names; one code map set LOV:<list> or MIS:<field> per list | Free entry, up to 40 characters | Free entry, up to 200 characters | Codes of the same file | Y or N | Free entry | Free entry | A whole number
What to enter | Legacy name of the list (for example MARKET_SEGMENT, BUSINESS_ORIGIN, CUSTOMER_SEGMENT, REGION, AREA, DEPARTMENT, ACCOUNT_TYPE, ID_TYPE, NATIONALITY) | Legacy value code | Legacy value description | Code of the parent value for hierarchical lists (area under region) | Value in use in legacy | First day the value is valid | Last day the value is valid | Number of legacy records that use the value (helps the mapping)
Row | list_type * | code * | description * | parent_code | active_flag * | effective_from | effective_to | used_count
Example – overwrite or delete | MARKET_SEGMENT | CBG | Consumer Banking Group | NCR | Y | 2020-01-01 |  | 1520
Note on B17: list_type Legacy name of the list (for example MARKET_SEGMENT, BUSINESS_ORIGIN, CUSTOMER_SEGMENT, REGION, AREA, DEPARTMENT, ACCOUNT_TYPE, ID_TYPE, NATIONALITY) Mandatory: Yes Format: Code, up to 40; Upper case Allowed values: Legacy list names; one code map set LOV:<list> or MIS:<field> per list Example: MARKET_SEGMENT
Note on C17: code Legacy value code Mandatory: Yes Format: Code, up to 40; As stored in legacy Allowed values: Free entry, up to 40 characters Example: CBG
Note on D17: description Legacy value description Mandatory: Yes Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Consumer Banking Group
Note on E17: parent_code Code of the parent value for hierarchical lists (area under region) Mandatory: No Format: Code, up to 40 Allowed values: Codes of the same file Example: NCR
Note on F17: active_flag Value in use in legacy Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y
Note on G17: effective_from First day the value is valid Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2020-01-01
Note on H17: effective_to Last day the value is valid Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry
Note on I17: used_count Number of legacy records that use the value (helps the mapping) Mandatory: No Format: Integer, up to 9; Digits Allowed values: A whole number Example: 1520

## R04 Insurers
R04 Insurers | [9 empty] | Step 7 of 51
← Back to Start here | Step 7 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [8 empty] | Ask a question →
Purpose | One row per record of Insurers and insurer branches as extracted from QPS, EBIX. Key insurer_code. Sent as the file R04_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Migration Console: the file R04_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object R04; lands in: Insurers and insurer branches (insurer and party records)
Source | QPS, EBIX
Depends on | Nothing: this template can be filled in first
Tax profile | The insurer's registered TIN, VAT treatment and the ATC it withholds on BDOI's commission are kept in the party tax profile (template TX-01)
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | Unique | Not blank | - | 9 to 12 digits | - | - | Valid date | Valid e-mail addresses | 0 to 365 | Mapped
Mandatory | Yes | Yes | No | No | No | No | No | No | No | Yes
Format | Code, up to 30; As stored in legacy | Text, up to 200; Free text | Text, up to 40; Free text | Text, up to 20; 000-000-000-000 | Text, up to 300; Free text | Text, up to 40; Free text | Date, up to 10; yyyy-MM-dd | Text, up to 500; name@domain;name@domain | Integer, up to 3; Digits | Code, up to 20; As stored in legacy
Allowed values | Free entry, up to 30 characters | Free entry, up to 200 characters | Free entry, up to 40 characters | Free entry, up to 20 characters | Free entry, up to 300 characters | Free entry, up to 40 characters | Free entry | Free entry, up to 500 characters | A whole number | The legacy code; mapped by the code map STATUS:INSURER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13)
What to enter | Legacy insurer code | Registered name | Short name | Tax identification number | Registered address | Insurance Commission accreditation number | End of accreditation | E-mail address(es) for placement, separated by semicolons | Credit term in days | Insurer status in legacy
Row | insurer_code * | insurer_name * | short_name | tin | address | accreditation_no | accredited_until | placement_email | default_credit_days | status *
Example – overwrite or delete | MAL | Malayan Insurance Co., Inc. | Malayan | 000-123-456-000 | 500 Quintin Paredes St., Manila | IC-2025-0123 | 2028-06-30 | placement@insurer.example | 60 | ACTIVE
Note on B18: insurer_code Legacy insurer code Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: Free entry, up to 30 characters Example: MAL
Note on C18: insurer_name Registered name Mandatory: Yes Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Malayan Insurance Co., Inc.
Note on D18: short_name Short name Mandatory: No Format: Text, up to 40; Free text Allowed values: Free entry, up to 40 characters Example: Malayan
Note on E18: tin Tax identification number Mandatory: No Format: Text, up to 20; 000-000-000-000 Allowed values: Free entry, up to 20 characters Example: 000-123-456-000
Note on F18: address Registered address Mandatory: No Format: Text, up to 300; Free text Allowed values: Free entry, up to 300 characters Example: 500 Quintin Paredes St., Manila
Note on G18: accreditation_no Insurance Commission accreditation number Mandatory: No Format: Text, up to 40; Free text Allowed values: Free entry, up to 40 characters Example: IC-2025-0123
Note on H18: accredited_until End of accreditation Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2028-06-30
Note on I18: placement_email E-mail address(es) for placement, separated by semicolons Mandatory: No Format: Text, up to 500; name@domain;name@domain Allowed values: Free entry, up to 500 characters Example: placement@insurer.example
Note on J18: default_credit_days Credit term in days Mandatory: No Format: Integer, up to 3; Digits Allowed values: A whole number Example: 60
Note on K18: status Insurer status in legacy Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:INSURER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: ACTIVE

## UA-02 Role matrix
UA-02 Role-to-permission matrix | [7 empty] | Step 8 of 51
← Back to Start here | Step 8 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | The group profiles BDOI keeps, their privilege level and the permissions of each, starting from the User Access Matrix as delivered
Provided by | Business Administration with the unit heads; reviewed and signed by BDOI Information Security
Due | 9-Apr-2027 – Reference data for Trial migration 1 (M4)
How it is loaded | Group-profile requests (SCR-UA-12): one request per new or changed profile, approved in order and implemented by the System Administrator; checked with the User Group Profile Report
Source | The User Access Matrix export of this set (DO-06) and the menus by persona of FRS chapter 12
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | Yes | Yes | No | Yes | Yes
Format | Up to 40 capital letters, digits or _ | Up to 120 characters | Up to 500 characters | Low, Standard, High or Admin | Permission code of the User Access Matrix | View only, Create, Amend, Approve / Validate | KEEP, ADD or REMOVE | Name
Allowed values | Free entry, up to 40 characters | Free entry, up to 120 characters | Free entry, up to 500 characters | Low, Standard, High, Admin (list Privilege level) | Free entry | Free entry | KEEP, ADD, REMOVE (list Change against the matrix) | Free entry
What to enter | Code of the profile; an existing code changes the profile | Name shown on screens | What the profile is for | High and Admin need a second approval when given or raised | One row per permission of the profile | As shown by the matrix, for the review | Change against the matrix as delivered | Unit head who confirms the row
Row | Group profile code * | Name * | Description | Privilege level * | Permission * | Action class | Keep / Add / Remove * | Approved by unit head *
Example – overwrite or delete | MKT_AO | Marketing Account Officer | Marketing account officers of the Combank and Corbank units | Standard | QUOTE_MAINTAIN | Create, Amend | KEEP | Carla Reyes
Note on B16: Group profile code Code of the profile; an existing code changes the profile Mandatory: Yes Format: Up to 40 capital letters, digits or _ Allowed values: Free entry, up to 40 characters Example: MKT_AO
Note on C16: Name Name shown on screens Mandatory: Yes Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: Marketing Account Officer
Note on D16: Description What the profile is for Mandatory: No Format: Up to 500 characters Allowed values: Free entry, up to 500 characters Example: Marketing account officers of the Combank and Corbank units
Note on E16: Privilege level High and Admin need a second approval when given or raised Mandatory: Yes Format: Low, Standard, High or Admin Allowed values: Low, Standard, High, Admin (list Privilege level) Example: Standard
Note on F16: Permission One row per permission of the profile Mandatory: Yes Format: Permission code of the User Access Matrix Allowed values: Free entry Example: QUOTE_MAINTAIN
Note on G16: Action class As shown by the matrix, for the review Mandatory: No Format: View only, Create, Amend, Approve / Validate Allowed values: Free entry Example: Create, Amend
Note on H16: Keep / Add / Remove Change against the matrix as delivered Mandatory: Yes Format: KEEP, ADD or REMOVE Allowed values: KEEP, ADD, REMOVE (list Change against the matrix) Example: KEEP
Note on I16: Approved by unit head Unit head who confirms the row Mandatory: Yes Format: Name Allowed values: Free entry Example: Carla Reyes

## UA-06 Lists of values
UA-06 Lists of values | [5 empty] | Step 9 of 51
← Back to Start here | Step 9 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The values of the lists of user access (business unit groups and user levels, empty as delivered; deactivation reasons, to confirm with BDOI; the reason No sign-in for the dormancy period is used by the dormant-user job and stays)
Provided by | Business Administration
Due | 1-Nov-2027 – before the templates that use its codes
How it is loaded | Lists of Values (New Business set) under maker-checker; before the users of CI-01 are loaded
Source | BDOI organisation (UQ05)
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | No | Yes
Format | UAM_BUSINESS_UNIT, UAM_USER_LEVEL or UAM_DEACTIVATION_REASON | Up to 30 capitals, digits or _ | Up to 120 characters | Whole number | dd-MMM-yyyy
Allowed values | UAM_BUSINESS_UNIT, UAM_USER_LEVEL, UAM_DEACTIVATION_REASON (list User access list) | Free entry, up to 30 characters | Free entry, up to 120 characters | A whole number | A date, for example 15-Jan-2028
What to enter | The list | Code of the value | Label shown on screens | Order in the drop-down | Date the value may be used
Row | List * | Code * | Label * | Sort order | Effective from *
Example – overwrite or delete | UAM_BUSINESS_UNIT | COMBANK_MKT | Combank Marketing | 10 | 2027-01-04
Note on B16: List The list Mandatory: Yes Format: UAM_BUSINESS_UNIT, UAM_USER_LEVEL or UAM_DEACTIVATION_REASON Allowed values: UAM_BUSINESS_UNIT, UAM_USER_LEVEL, UAM_DEACTIVATION_REASON (list User access list) Example: UAM_BUSINESS_UNIT
Note on C16: Code Code of the value Mandatory: Yes Format: Up to 30 capitals, digits or _ Allowed values: Free entry, up to 30 characters Example: COMBANK_MKT
Note on D16: Label Label shown on screens Mandatory: Yes Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: Combank Marketing
Note on E16: Sort order Order in the drop-down Mandatory: No Format: Whole number Allowed values: A whole number Example: 10
Note on F16: Effective from Date the value may be used Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 04-Jan-2027

## D0-05 Employees
D0-05 Employees | [6 empty] | Step 10 of 51
← Back to Start here | Step 10 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [5 empty] | Ask a question →
Purpose | Employees used by the cost-centre rules, petty cash and staff advances
Provided by | Human Resources; Head, Comptrollership
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Employees (Setup & Administration)
Source | HR employee list
Depends on | D0-02 Branches → |  | D0-04 Cost centres and business lines →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | No | No | No
Format | HR number | Up to 120 characters | Code of D0-02 | Cost centre of D0-04 | Text | Company e-mail | dd-MMM-yyyy
Allowed values | Free entry | Free entry, up to 120 characters | A code of D0-02 Branches, column Branch code | A code of D0-04 Cost centres and business lines, column Code | Free entry | Free entry | A date, for example 15-Jan-2028
What to enter | Unique | Name of the employee | Home branch | Cost centre of the employee | Position title | For advices and statements | Date of hire
Row | Employee number * | Full name * | Branch code * | Cost centre * | Position | E-mail | Hired on
Example – overwrite or delete | 1203344 | Andrea Mercado | HO | FIN | Accounting Officer | andrea.mercado@bdoi.example.ph | 2019-03-03
Note on B16: Employee number Unique Mandatory: Yes Format: HR number Allowed values: Free entry Example: 1203344
Note on C16: Full name Name of the employee Mandatory: Yes Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: Andrea Mercado
Note on D16: Branch code Home branch Mandatory: Yes Format: Code of D0-02 Allowed values: A code of D0-02 Branches, column Branch code Example: HO
Note on E16: Cost centre Cost centre of the employee Mandatory: Yes Format: Cost centre of D0-04 Allowed values: A code of D0-04 Cost centres and business lines, column Code Example: FIN
Note on F16: Position Position title Mandatory: No Format: Text Allowed values: Free entry Example: Accounting Officer
Note on G16: E-mail For advices and statements Mandatory: No Format: Company e-mail Allowed values: Free entry Example: andrea.mercado@bdoi.example.ph
Note on H16: Hired on Date of hire Mandatory: No Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 03-Mar-2019

## D0-06 Chart of accounts
D0-06 Chart of accounts | [15 empty] | Step 11 of 51
← Back to Start here | Step 11 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [14 empty] | Ask a question →
Purpose | The production chart of accounts, in the columns of the chart upload. List every parent before its children. Accounts are created pending authorization.
Provided by | Head, Comptrollership
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Chart Upload (General Ledger): the file is checked row by row and every account is created pending authorisation by Comptrollership
Source | The BDOI chart of accounts in use, completed with the legacy control accounts (D0-09)
Depends on | D0-07 Account categories and numbering →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | No | No | Yes | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No
Format | Text | Text | Text | Text | Text | Text | Text | Y or N | Text | Text | Y or N | Y or N | Y or N | Text | yyyy-MM-dd | Text
Allowed values | A code of D0-06 Chart of accounts, column Account Code | Free entry | Free entry | Free entry | ASSET, LIABILITY, EQUITY, INCOME, EXPENSE, MEMORANDUM (list Account class of the chart) | GROUP, MAIN, SUB, MICRO (list Account level) | A code of D0-07 Account categories and numbering, column Category code | Y or N | Free entry | Free entry | Y or N | Y or N | Y or N | Free entry | Free entry | ALLOW, WARN, BLOCK (list Negative balance)
What to enter | Code of the parent account; blank for a top-level group | Account code; blank for the next number of the parent's scheme | Account name | Unique short code used on journal lines | Class of the account | Level of the account, one tier below the parent | GL category | Control account | Sub-ledger the account controls; blank for none | Currencies allowed on the account; blank for all | Manual journals allowed; blank for Y | Cost centre mandatory on journal lines | Revalued at month end | Financial statement line | Opening date; blank for today | What a negative balance does; blank for ALLOW
Row | Parent Code | Account Code | Account Name * | Short Code | Class * | Level * | Category | Control Account | Sub-ledger Type | Currencies | Manual Posting | Cost Centre Required | Revaluation Required | Report Group | Opened On | Negative Balance
Example – overwrite or delete |  | 1210.07 | Premium Receivable - Motor | PRMOTOR | ASSET | SUB |  | N | POLICYHOLDER | PHP | Y | N | N | Premium Receivable | 2026-01-01 | WARN
Note on B16: Parent Code Code of the parent account; blank for a top-level group Mandatory: No Format: Text Allowed values: A code of D0-06 Chart of accounts, column Account Code
Note on C16: Account Code Account code; blank for the next number of the parent's scheme Mandatory: No Format: Text Allowed values: Free entry Example: 1210.07
Note on D16: Account Name Account name Mandatory: Yes Format: Text Allowed values: Free entry Example: Premium Receivable - Motor
Note on E16: Short Code Unique short code used on journal lines Mandatory: No Format: Text Allowed values: Free entry Example: PRMOTOR
Note on F16: Class Class of the account Mandatory: Yes Format: Text Allowed values: ASSET, LIABILITY, EQUITY, INCOME, EXPENSE, MEMORANDUM (list Account class of the chart) Example: ASSET
Note on G16: Level Level of the account, one tier below the parent Mandatory: Yes Format: Text Allowed values: GROUP, MAIN, SUB, MICRO (list Account level) Example: SUB
Note on H16: Category GL category Mandatory: No Format: Text Allowed values: A code of D0-07 Account categories and numbering, column Category code
Note on I16: Control Account Control account Mandatory: No Format: Y or N Allowed values: Y or N Example: N
Note on J16: Sub-ledger Type Sub-ledger the account controls; blank for none Mandatory: No Format: Text Allowed values: Free entry Example: POLICYHOLDER
Note on K16: Currencies Currencies allowed on the account; blank for all Mandatory: No Format: Text Allowed values: Free entry Example: PHP
Note on L16: Manual Posting Manual journals allowed; blank for Y Mandatory: No Format: Y or N Allowed values: Y or N Example: Y
Note on M16: Cost Centre Required Cost centre mandatory on journal lines Mandatory: No Format: Y or N Allowed values: Y or N Example: N
Note on N16: Revaluation Required Revalued at month end Mandatory: No Format: Y or N Allowed values: Y or N Example: N
Note on O16: Report Group Financial statement line Mandatory: No Format: Text Allowed values: Free entry Example: Premium Receivable
Note on P16: Opened On Opening date; blank for today Mandatory: No Format: yyyy-MM-dd Allowed values: Free entry Example: 2026-01-01
Note on Q16: Negative Balance What a negative balance does; blank for ALLOW Mandatory: No Format: Text Allowed values: ALLOW, WARN, BLOCK (list Negative balance) Example: WARN

## MD-01 Business partners
MD-01 Business partners (reinsurers, intermediaries, suppliers) | [13 empty] | Step 12 of 51
← Back to Start here | Step 12 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [12 empty] | Ask a question →
Purpose | One row per business partner other than an insurer or a client: agents and brokers (intermediaries), reinsurers and reinsurance brokers, co-insurers, suppliers, garages, surveyors and banks. Insurers come from R04; clients from C01 and the client upload.
Provided by | Head, Comptrollership; Head, Operations for the reinsurers and intermediaries
Due | 9-Apr-2027 – Reference data for Trial migration 1 (M4)
How it is loaded | Configuration screen: Setup & Administration › Setup › Business Partners, one partner at a time, authorised by a second user
Source | BDOI partner lists; legacy supplier masters
Depends on | D0-02 Branches →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | No | No | No | No | Yes | No | No | Conditional: intermediaries (agent, broker, reinsurance broker) | No | No | No
Format | Text, up to 30; capitals, digits, - and . | Code of the list | Text, up to 200 | 000-000-000-000 | Text, up to 300 | E-mail address | Text, up to 40 | ISO currency code, 3 letters | Text, up to 120 | Text, up to 40 | Text, up to 40 | Whole number | Number, 0 to 100 | Number, 0 to 100
Allowed values | Free entry, up to 30 characters | List Business partner type: 12 values, see Reference lists | Free entry, up to 200 characters | Free entry, up to 30 characters | Free entry, up to 300 characters | Free entry, up to 120 characters | Free entry, up to 40 characters | List Currency: 9 values, see Reference lists | Free entry, up to 120 characters | Free entry, up to 40 characters | Free entry, up to 40 characters | A whole number from 0 to 365 | A number from 0 to 100 | A number from 0 to 100
What to enter | Code of the partner, unique | Kind of partner | Registered name | Tax identification number | Registered address | E-mail for advices and statements | Phone number | Currency of the partner's transactions | Bank of the partner's account | Account number for payments | Insurance Commission licence number of an intermediary | Credit days of the partner's items (0 when none) | Commission rate of an intermediary | Withholding tax rate applied to the partner
Row | Party code * | Party type * | Name * | TIN / tax id | Address | E-mail | Phone | Default currency * | Bank name | Bank account no. | Licence no. | Credit days | Commission rate % | Withholding tax rate %
Example – overwrite or delete | RI-0001 | REINSURER | Asia Pacific Reinsurance Corp. | 123-456-789-000 | Makati City | treaty@apre.example.ph | +63 2 8888 0000 | PHP | BDO Unibank | 001234567890 | IC-RB-2026-015 | 30 |  | 2
Note on B16: Party code Code of the partner, unique Mandatory: Yes Format: Text, up to 30; capitals, digits, - and . Allowed values: Free entry, up to 30 characters Example: RI-0001
Note on C16: Party type Kind of partner Mandatory: Yes Format: Code of the list Allowed values: List Business partner type: 12 values, see Reference lists Example: REINSURER
Note on D16: Name Registered name Mandatory: Yes Format: Text, up to 200 Allowed values: Free entry, up to 200 characters Example: Asia Pacific Reinsurance Corp.
Note on E16: TIN / tax id Tax identification number Mandatory: No Format: 000-000-000-000 Allowed values: Free entry, up to 30 characters Example: 123-456-789-000
Note on F16: Address Registered address Mandatory: No Format: Text, up to 300 Allowed values: Free entry, up to 300 characters Example: Makati City
Note on G16: E-mail E-mail for advices and statements Mandatory: No Format: E-mail address Allowed values: Free entry, up to 120 characters Example: treaty@apre.example.ph
Note on H16: Phone Phone number Mandatory: No Format: Text, up to 40 Allowed values: Free entry, up to 40 characters Example: +63 2 8888 0000
Note on I16: Default currency Currency of the partner's transactions Mandatory: Yes Format: ISO currency code, 3 letters Allowed values: List Currency: 9 values, see Reference lists Example: PHP
Note on J16: Bank name Bank of the partner's account Mandatory: No Format: Text, up to 120 Allowed values: Free entry, up to 120 characters Example: BDO Unibank
Note on K16: Bank account no. Account number for payments Mandatory: No Format: Text, up to 40 Allowed values: Free entry, up to 40 characters Example: 001234567890
Note on L16: Licence no. Insurance Commission licence number of an intermediary Mandatory: Conditional: intermediaries (agent, broker, reinsurance broker) Format: Text, up to 40 Allowed values: Free entry, up to 40 characters Example: IC-RB-2026-015
Note on M16: Credit days Credit days of the partner's items (0 when none) Mandatory: No Format: Whole number Allowed values: A whole number from 0 to 365 Example: 30
Note on N16: Commission rate % Commission rate of an intermediary Mandatory: No Format: Number, 0 to 100 Allowed values: A number from 0 to 100
Note on O16: Withholding tax rate % Withholding tax rate applied to the partner Mandatory: No Format: Number, 0 to 100 Allowed values: A number from 0 to 100 Example: 2

## R03 Sales organisation (units a
R03 Sales organisation (units and account officers) | [10 empty] | Step 13 of 51
← Back to Start here | Step 13 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [9 empty] | Ask a question →
Purpose | One row per record of Sales organisation (regions, departments, teams, unit heads, account officers) as extracted from QPS, EBIX. Key record_type, unit_code, ao_user_id. Sent as the file R03_template.csv (CSV, header row as below) with its control file (row count, row count).
Provided by | Marketing data steward (to name); approved by Heads, Retail and Corporate Marketing; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Migration Console: the file R03_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object R03; lands in: Sales organisation: sales units and account officers
Source | QPS, EBIX
Depends on | D0-02 Branches → |  | D0-04 Cost centres and business lines →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | In the list | Exists as a TEAM row for AO rows | Mandatory for REGION, DEPARTMENT, TEAM | Mandatory for DEPARTMENT and TEAM; parent exists | Mapped in USER | Mapped | Mandatory for AO rows; mapped in USER | Unique | Mandatory for AO rows | Mapped | Y or N
Mandatory | Yes | Yes | Conditional: Mandatory for REGION, DEPARTMENT, TEAM | Conditional: Mandatory for DEPARTMENT and TEAM; parent exists | No | No | Conditional: Mandatory for AO rows; mapped in USER | No | Conditional: Mandatory for AO rows | No | Yes
Format | Code, up to 12; Upper case | Code, up to 20; As stored in legacy | Text, up to 120; Free text | Code, up to 20; As stored in legacy | Code, up to 50; As stored in legacy | Code, up to 20; As stored in legacy | Code, up to 50; As stored in legacy | Code, up to 20; As stored in legacy | Text, up to 120; Free text | Code, up to 20; As stored in legacy | Flag, up to 1; Y or N
Allowed values | REGION, DEPARTMENT, TEAM, AO (list R03 record_type) | Free entry, up to 20 characters | Free entry, up to 120 characters | unit_code values of the file | The legacy code; mapped by the code map USER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map COST_CENTER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map USER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map AO (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | Free entry, up to 120 characters | The legacy code; mapped by the code map BRANCH (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | Y or N
What to enter | Kind of row | Legacy code of the unit (for an AO row, the team of the AO) | Unit name | Code of the parent unit (department of a team, region of a department) | Legacy user ID of the unit head | Cost centre of the unit | Legacy user ID of the account officer | Legacy AO code if different from the user ID | AO full name | Branch of the unit or AO | Unit or AO active
Row | record_type * | unit_code * | unit_name | parent_unit_code | unit_head_user_id | cost_center | ao_user_id | ao_code | ao_name | branch_code | active_flag *
Example – overwrite or delete | TEAM | T-RET-07 | Retail Team 7 | D-RET | jdelacruz | 4100 | mreyes | AO0457 | Maria Reyes | MKT01 | Y
Note on B17: record_type Kind of row Mandatory: Yes Format: Code, up to 12; Upper case Allowed values: REGION, DEPARTMENT, TEAM, AO (list R03 record_type) Example: TEAM
Note on C17: unit_code Legacy code of the unit (for an AO row, the team of the AO) Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: Free entry, up to 20 characters Example: T-RET-07
Note on D17: unit_name Unit name Mandatory: Conditional: Mandatory for REGION, DEPARTMENT, TEAM Format: Text, up to 120; Free text Allowed values: Free entry, up to 120 characters Example: Retail Team 7
Note on E17: parent_unit_code Code of the parent unit (department of a team, region of a department) Mandatory: Conditional: Mandatory for DEPARTMENT and TEAM; parent exists Format: Code, up to 20; As stored in legacy Allowed values: unit_code values of the file Example: D-RET
Note on F17: unit_head_user_id Legacy user ID of the unit head Mandatory: No Format: Code, up to 50; As stored in legacy Allowed values: The legacy code; mapped by the code map USER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: jdelacruz
Note on G17: cost_center Cost centre of the unit Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map COST_CENTER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: 4100
Note on H17: ao_user_id Legacy user ID of the account officer Mandatory: Conditional: Mandatory for AO rows; mapped in USER Format: Code, up to 50; As stored in legacy Allowed values: The legacy code; mapped by the code map USER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: mreyes
Note on I17: ao_code Legacy AO code if different from the user ID Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map AO (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: AO0457
Note on J17: ao_name AO full name Mandatory: Conditional: Mandatory for AO rows Format: Text, up to 120; Free text Allowed values: Free entry, up to 120 characters Example: Maria Reyes
Note on K17: branch_code Branch of the unit or AO Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map BRANCH (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: MKT01
Note on L17: active_flag Unit or AO active Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y

## R05 Product lines, cover types,
R05 Product lines, cover types, products and risk codes | [8 empty] | Step 14 of 51
← Back to Start here | Step 14 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [7 empty] | Ask a question →
Purpose | One row per record of Product lines, cover types, products and risk codes as extracted from QPS, EBIX. Key risk_code. Sent as the file R05_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | MBS data steward (to name); approved by Product Owner, MBS; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Migration Console: the file R05_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object R05; lands in: Product catalogue: product lines, cover types and products
Source | QPS, EBIX
Depends on | PM-09 Lists of values and parameters →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | Mapped | - | Mapped | Unique | Not blank | Y or N | Each mapped | Mapped | 0 or more
Mandatory | Yes | No | No | Yes | Yes | No | No | Yes | No
Format | Code, up to 30; As stored in legacy | Text, up to 120; Free text | Code, up to 30; As stored in legacy | Code, up to 20; As stored in legacy | Text, up to 200; Free text | Flag, up to 1; Y or N | Text, up to 300; CODE;CODE | Code, up to 20; As stored in legacy | Integer, up to 9; Digits
Allowed values | The legacy code; mapped by the code map LINE (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | Free entry, up to 120 characters | The legacy code; mapped by the code map COVER_TYPE (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | Free entry, up to 20 characters | Free entry, up to 200 characters | Y or N | The legacy code; mapped by the code map LOV:MARKET_SEGMENT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map STATUS:PRODUCT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | A whole number
What to enter | Legacy line of business | Line name | Legacy cover type | Legacy risk code / product code | Product / risk name | Sold as a package | Segments that may use the product, separated by semicolons | Status in legacy | Open invoices and in-force policies using the code (helps the mapping)
Row | line_code * | line_name | cover_type_code | risk_code * | risk_name * | packaged_flag | market_segments | status * | open_item_count
Example – overwrite or delete | MOTOR | Motor Car | COMP | MC-PC-COMP | Private Car Own Damage and Theft | N | CBG;RETAIL | ACTIVE | 4211
Note on B17: line_code Legacy line of business Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map LINE (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: MOTOR
Note on C17: line_name Line name Mandatory: No Format: Text, up to 120; Free text Allowed values: Free entry, up to 120 characters Example: Motor Car
Note on D17: cover_type_code Legacy cover type Mandatory: No Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map COVER_TYPE (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: COMP
Note on E17: risk_code Legacy risk code / product code Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: Free entry, up to 20 characters Example: MC-PC-COMP
Note on F17: risk_name Product / risk name Mandatory: Yes Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Private Car Own Damage and Theft
Note on G17: packaged_flag Sold as a package Mandatory: No Format: Flag, up to 1; Y or N Allowed values: Y or N Example: N
Note on H17: market_segments Segments that may use the product, separated by semicolons Mandatory: No Format: Text, up to 300; CODE;CODE Allowed values: The legacy code; mapped by the code map LOV:MARKET_SEGMENT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: CBG;RETAIL
Note on I17: status Status in legacy Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:PRODUCT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: ACTIVE
Note on J17: open_item_count Open invoices and in-force policies using the code (helps the mapping) Mandatory: No Format: Integer, up to 9; Digits Allowed values: A whole number Example: 4211

## UA-01 Users and roles
UA-01 Users and roles load | [10 empty] | Step 15 of 51
← Back to Start here | Step 15 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [9 empty] | Ask a question →
Purpose | Every BIBS user at go-live with the user data and the group profiles, in the columns of the Bulk Request template
Provided by | Business Administration, with the unit heads who name their users
Due | 1-Nov-2027 – Production values before the dress rehearsal
How it is loaded | Bulk Request (SCR-UA-09): the file of this template is uploaded as a bulk batch, checked row by row and approved by an approver like single requests; users are out of the data migration scope (DMQ30)
Source | The users of the legacy systems and the unit rosters; the HR list of employees for the full names and e-mails
Depends on | UA-06 Lists of values → |  | UA-02 Role-to-permission matrix →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Conditional: ENROL | No | No | No | No | No | Conditional: ENROL | No | Yes
Format | ENROL, MODIFY, DEACTIVATE or REACTIVATE | A letter and nine digits (BDOI format a999999999) | Up to 120 characters | Company e-mail address | Windows log-on name; unique | Branch code | Code of the list Business unit group (CI-06) | Code of the list User level (CI-06) | Profile codes of CI-02 separated by ';' | yyyy-MM-dd; blank = on approval | Up to 1,000 characters
Allowed values | ENROL, MODIFY, DEACTIVATE, REACTIVATE (list Bulk request action) | Free entry, up to 10 characters | Free entry, up to 120 characters | Free entry | Free entry | Free entry | Codes of UA-06 Lists of values, column Code (one or more) | Codes of UA-06 Lists of values, column Code (one or more) | Codes of UA-02 Role-to-permission matrix, column Group profile code (one or more) | Free entry | Free entry, up to 1000 characters
What to enter | ENROL for the go-live load | The BIBS user ID; unique | Name shown on screens and reports | Receives the access-changed notices and the reset links | Used for the BDO directory sign-in when it is enabled | Home branch of the user | Business unit group | User level | The group profiles of the user | Date the change applies | Justification of the line
Row | Action * | User ID * | Full Name | E-mail | Windows ID | Home Branch Code | Business Unit | User Level | Group Profiles | Effective Date | Remarks *
Example – overwrite or delete | ENROL | a013000201 | Andrea Mercado | andrea.mercado@brokerverse-seed.ph | AMERCADO | HO |  |  | MKT_AO |  | Joined Marketing
Note on B16: Action ENROL for the go-live load Mandatory: Yes Format: ENROL, MODIFY, DEACTIVATE or REACTIVATE Allowed values: ENROL, MODIFY, DEACTIVATE, REACTIVATE (list Bulk request action) Example: ENROL
Note on C16: User ID The BIBS user ID; unique Mandatory: Yes Format: A letter and nine digits (BDOI format a999999999) Allowed values: Free entry, up to 10 characters Example: a013000201
Note on D16: Full Name Name shown on screens and reports Mandatory: Conditional: ENROL Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: Andrea Mercado
Note on E16: E-mail Receives the access-changed notices and the reset links Mandatory: No Format: Company e-mail address Allowed values: Free entry Example: andrea.mercado@brokerverse-seed.ph
Note on F16: Windows ID Used for the BDO directory sign-in when it is enabled Mandatory: No Format: Windows log-on name; unique Allowed values: Free entry Example: AMERCADO
Note on G16: Home Branch Code Home branch of the user Mandatory: No Format: Branch code Allowed values: Free entry Example: HO
Note on H16: Business Unit Business unit group Mandatory: No Format: Code of the list Business unit group (CI-06) Allowed values: Codes of UA-06 Lists of values, column Code (one or more)
Note on I16: User Level User level Mandatory: No Format: Code of the list User level (CI-06) Allowed values: Codes of UA-06 Lists of values, column Code (one or more)
Note on J16: Group Profiles The group profiles of the user Mandatory: Conditional: ENROL Format: Profile codes of CI-02 separated by ';' Allowed values: Codes of UA-02 Role-to-permission matrix, column Group profile code (one or more) Example: MKT_AO
Note on K16: Effective Date Date the change applies Mandatory: No Format: yyyy-MM-dd; blank = on approval Allowed values: Free entry
Note on L16: Remarks Justification of the line Mandatory: Yes Format: Up to 1,000 characters Allowed values: Free entry, up to 1000 characters Example: Joined Marketing

## D0-03 Holiday calendar
D0-03 Holiday calendar |  |  |  | Step 16 of 51
← Back to Start here | Step 16 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  | Ask a question →
Purpose | Public and company holidays of 2027 and 2028
Provided by | Head, Comptrollership; Human Resources
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Holiday Calendar (Setup & Administration); 2028 before the dress rehearsal, later years each December
Source | Proclamations of the national holidays; BDOI company holidays
Depends on | D0-02 Branches →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | No | Yes | Yes
Format | Code of D0-02; blank = every branch | dd-MMM-yyyy | Up to 120 characters
Allowed values | A code of D0-02 Branches, column Branch code | A date, for example 15-Jan-2028 | Free entry, up to 120 characters
What to enter | Branch the holiday applies to | Date of the holiday | Name of the holiday
Row | Branch code | Date * | Description *
Example – overwrite or delete |  | 2028-01-01 | New Year's Day
Note on B16: Branch code Branch the holiday applies to Mandatory: No Format: Code of D0-02; blank = every branch Allowed values: A code of D0-02 Branches, column Branch code
Note on C16: Date Date of the holiday Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Jan-2028
Note on D16: Description Name of the holiday Mandatory: Yes Format: Up to 120 characters Allowed values: Free entry, up to 120 characters Example: New Year's Day

## MD-03 Exchange rates
MD-03 Exchange rates and their source |  |  |  |  | Step 17 of 51
← Back to Start here | Step 17 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  | Ask a question →
Purpose | The opening exchange rates of each foreign currency per rate type at go-live. BIBS keeps four rate types: SPOT (daily rate of postings), CLOSING (month-end revaluation), AVERAGE (period average) and BUDGET. The source of the daily rates (for example the BDO Treasury board rate or the BSP reference rate) and who enters them are asked in the BDOI requirements workbook.
Provided by | Head, Comptrollership (Treasury)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Configuration screen: Setup & Administration › Setup › Currencies & Rates, one rate per currency, type and date
Source | BDO Treasury or BSP reference rates
Depends on | MD-02 Currencies →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes
Format | Code of MD-02 | Code of the list | dd-mmm-yyyy | Number, PHP per unit of the currency
Allowed values | A code of MD-02 Currencies, column Currency code | SPOT, CLOSING, AVERAGE, BUDGET (list Exchange rate type) | A date, for example 15-Jan-2028 | A number from 0 to 1000000
What to enter | Currency of the rate (not PHP) | Kind of rate | Date from which the rate applies | Pesos for one unit of the currency
Row | Currency code * | Rate type * | Effective date * | Rate *
Example – overwrite or delete | USD | SPOT | 2028-01-03
Note on B16: Currency code Currency of the rate (not PHP) Mandatory: Yes Format: Code of MD-02 Allowed values: A code of MD-02 Currencies, column Currency code Example: USD
Note on C16: Rate type Kind of rate Mandatory: Yes Format: Code of the list Allowed values: SPOT, CLOSING, AVERAGE, BUDGET (list Exchange rate type) Example: SPOT
Note on D16: Effective date Date from which the rate applies Mandatory: Yes Format: dd-mmm-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 03-Jan-2028
Note on E16: Rate Pesos for one unit of the currency Mandatory: Yes Format: Number, PHP per unit of the currency Allowed values: A number from 0 to 1000000

## R02 Branches and invoicing bran
R02 Branches and invoicing branches | [5 empty] | Step 18 of 51
← Back to Start here | Step 18 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | One row per record of Branches and invoicing branches as extracted from EBIX. Key branch_code. Sent as the file R02_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | Comptrollership data steward (to name); approved by Head, Comptrollership; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Migration Console: the file R02_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object R02; lands in: Branches (check only, code map BRANCH)
Source | EBIX
Depends on | D0-02 Branches →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | Unique | Not blank | Y or N | - | Y or N
Mandatory | Yes | Yes | Yes | No | Yes
Format | Code, up to 20; As stored in legacy | Text, up to 120; Free text | Flag, up to 1; Y or N | Text, up to 80; Free text | Flag, up to 1; Y or N
Allowed values | Free entry, up to 20 characters | Free entry, up to 120 characters | Y or N | Free entry, up to 80 characters | Y or N
What to enter | Legacy branch code | Branch name | Branch issues invoices and receipts | City of the branch | Branch active in legacy
Row | branch_code * | branch_name * | invoicing_branch_flag * | city | active_flag *
Example – overwrite or delete | MKT01 | Makati Head Office | Y | Makati City | Y
Note on B17: branch_code Legacy branch code Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: Free entry, up to 20 characters Example: MKT01
Note on C17: branch_name Branch name Mandatory: Yes Format: Text, up to 120; Free text Allowed values: Free entry, up to 120 characters Example: Makati Head Office
Note on D17: invoicing_branch_flag Branch issues invoices and receipts Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y
Note on E17: city City of the branch Mandatory: No Format: Text, up to 80; Free text Allowed values: Free entry, up to 80 characters Example: Makati City
Note on F17: active_flag Branch active in legacy Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y

## R04B Insurer branches
R04B Insurer branches | [6 empty] | Step 19 of 51
← Back to Start here | Step 19 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [5 empty] | Ask a question →
Purpose | One row per record of Insurers and insurer branches as extracted from QPS, EBIX. Key insurer_code, branch_code. Sent as the file R04B_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Migration Console: the file R04B_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object R04; lands in: Insurers and insurer branches (insurer and party records)
Source | QPS, EBIX
Depends on | R04 Insurers →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | Exists in R04 | Unique per insurer | Not blank | - | 0 to 5 | Valid e-mail | Mapped
Mandatory | Yes | Yes | Yes | No | No | No | Yes
Format | Code, up to 30; As stored in legacy | Code, up to 20; As stored in legacy | Text, up to 120; Free text | Text, up to 80; Free text | Decimal, up to 9,4; Dot decimal | Text, up to 120; name@domain | Code, up to 20; As stored in legacy
Allowed values | The legacy code; mapped by the code map INSURER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | Free entry, up to 20 characters | Free entry, up to 120 characters | Free entry, up to 80 characters | A number | Free entry, up to 120 characters | The legacy code; mapped by the code map STATUS:INSURER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13)
What to enter | Legacy insurer code | Legacy insurer branch code | Branch name | City | Local government tax rate of the branch location, in percent | Branch placement e-mail | Branch status
Row | insurer_code * | branch_code * | branch_name * | city | lgt_rate | placement_email | status *
Example – overwrite or delete | MAL | MAL-CEB | Malayan Cebu | Cebu City | 0.75 | cebu@insurer.example | ACTIVE
Note on B17: insurer_code Legacy insurer code Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map INSURER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: MAL
Note on C17: branch_code Legacy insurer branch code Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: Free entry, up to 20 characters Example: MAL-CEB
Note on D17: branch_name Branch name Mandatory: Yes Format: Text, up to 120; Free text Allowed values: Free entry, up to 120 characters Example: Malayan Cebu
Note on E17: city City Mandatory: No Format: Text, up to 80; Free text Allowed values: Free entry, up to 80 characters Example: Cebu City
Note on F17: lgt_rate Local government tax rate of the branch location, in percent Mandatory: No Format: Decimal, up to 9,4; Dot decimal Allowed values: A number Example: 0.75
Note on G17: placement_email Branch placement e-mail Mandatory: No Format: Text, up to 120; name@domain Allowed values: Free entry, up to 120 characters Example: cebu@insurer.example
Note on H17: status Branch status Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:INSURER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: ACTIVE

## R11 Receipt series in use
R11 Receipt series in use | [7 empty] | Step 20 of 51
← Back to Start here | Step 20 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | One row per record of Receipt series in use (AR and OR, ATP and next number) as extracted from EBIX. Key branch_code, kind, prefix. Sent as the file R11_template.csv (CSV, header row as below) with its control file (row count, row count).
Provided by | Cashiering data steward (to name); approved by Operations - Financial Transactions; extracted by BDOI IT
Due | M3 (29 Jan 2027); final at T-3
How it is loaded | Migration Console: the file R11_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object R11; lands in: Receipt series of Cashiering
Source | EBIX
Depends on | D0-02 Branches →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | Mapped | In the list | Not blank | Unique per branch and kind | Less than to_no | More than from_no | Between from_no and to_no
Mandatory | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes
Format | Code, up to 20; As stored in legacy | Code, up to 2; Upper case | Text, up to 40; As printed | Text, up to 20; As printed | Integer, up to 12; Digits | Integer, up to 12; Digits | Integer, up to 12; Digits | Integer, up to 12; Digits
Allowed values | The legacy code; mapped by the code map BRANCH (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | AR, OR (list R11 kind) | Free entry, up to 40 characters | Free entry, up to 20 characters | A whole number | A whole number | A whole number | A whole number
What to enter | Issuing branch | Receipt kind | BIR Authority to Print number | Series prefix | First number of the series | Last number of the series | Last number issued in legacy at the freeze | Next number BIBS issues
Row | branch_code * | kind * | atp_no * | prefix | from_no * | to_no * | last_used_no * | next_no *
Example – overwrite or delete | MKT01 | AR | ATP-OCN-2025-000123 | AR-MKT | 100001 | 150000 | 131245 | 131246
Note on B17: branch_code Issuing branch Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map BRANCH (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: MKT01
Note on C17: kind Receipt kind Mandatory: Yes Format: Code, up to 2; Upper case Allowed values: AR, OR (list R11 kind) Example: AR
Note on D17: atp_no BIR Authority to Print number Mandatory: Yes Format: Text, up to 40; As printed Allowed values: Free entry, up to 40 characters Example: ATP-OCN-2025-000123
Note on E17: prefix Series prefix Mandatory: No Format: Text, up to 20; As printed Allowed values: Free entry, up to 20 characters Example: AR-MKT
Note on F17: from_no First number of the series Mandatory: Yes Format: Integer, up to 12; Digits Allowed values: A whole number Example: 100001
Note on G17: to_no Last number of the series Mandatory: Yes Format: Integer, up to 12; Digits Allowed values: A whole number Example: 150000
Note on H17: last_used_no Last number issued in legacy at the freeze Mandatory: Yes Format: Integer, up to 12; Digits Allowed values: A whole number Example: 131245
Note on I17: next_no Next number BIBS issues Mandatory: Yes Format: Integer, up to 12; Digits Allowed values: A whole number Example: 131246

## UA-04 SoD rules
UA-04 Separation-of-duties rules | [6 empty] | Step 21 of 51
← Back to Start here | Step 21 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [5 empty] | Ask a question →
Purpose | The rules BIBS enforces, for confirmation, and the combinations of profiles or permissions that BDOI Information Security does not allow one user to hold
Provided by | BDOI Information Security
Due | 16-Jul-2027 – Values for UAT
How it is loaded | The rules marked Enforced are fixed in BIBS; the privileged profiles are set by the privilege level of CI-02. Each combination of two profiles is entered on Separation of Duties (SCR-UA-19) by the Business Administrator and authorised by Information Security; BIBS then refuses every request and bulk line that breaks it. A combination of permissions is reviewed with the reports
Source | BDOI information security policy; the separation-of-duties rules of FRS chapter 13
Depends on | UA-02 Role-to-permission matrix →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Conditional: combination rule | Conditional: combination rule | Yes | Conditional: Detect by review
Format | SOD-nn | Text | Enforced, To confirm, New | Profile or permission of CI-02 | Profile or permission of CI-02 | Prevent (a rule of Separation of Duties, for two profiles), Detect by review, Second approval | Monthly, Quarterly
Allowed values | Free entry | Free entry | Enforced, To confirm, New (list Separation-of-duties rule status) | Codes of UA-02 Role-to-permission matrix, column Group profile code (one or more) | Codes of UA-02 Role-to-permission matrix, column Group profile code (one or more) | Prevent, Detect by review, Second approval (list Separation-of-duties control) | Monthly, Quarterly (list Review frequency)
What to enter | Identifier of the rule | The rule | Enforced = a fixed rule of BIBS | First profile or permission of a combination | Profile or permission that may not be held with A | How the rule is controlled | How often the reports are reviewed
Row | Rule ID * | Rule * | Status * | Profile or permission A | Profile or permission B | Control * | Review frequency
Example – overwrite or delete | SOD-01 | The requester never decides his own request | Enforced | User Access Requestor | User Access Approver | Prevent | Quarterly
Note on B16: Rule ID Identifier of the rule Mandatory: Yes Format: SOD-nn Allowed values: Free entry Example: SOD-01
Note on C16: Rule The rule Mandatory: Yes Format: Text Allowed values: Free entry Example: The requester never decides his own request
Note on D16: Status Enforced = a fixed rule of BIBS Mandatory: Yes Format: Enforced, To confirm, New Allowed values: Enforced, To confirm, New (list Separation-of-duties rule status) Example: Enforced
Note on E16: Profile or permission A First profile or permission of a combination Mandatory: Conditional: combination rule Format: Profile or permission of CI-02 Allowed values: Codes of UA-02 Role-to-permission matrix, column Group profile code (one or more) Example: User Access Requestor
Note on F16: Profile or permission B Profile or permission that may not be held with A Mandatory: Conditional: combination rule Format: Profile or permission of CI-02 Allowed values: Codes of UA-02 Role-to-permission matrix, column Group profile code (one or more) Example: User Access Approver
Note on G16: Control How the rule is controlled Mandatory: Yes Format: Prevent (a rule of Separation of Duties, for two profiles), Detect by review, Second approval Allowed values: Prevent, Detect by review, Second approval (list Separation-of-duties control) Example: Prevent
Note on H16: Review frequency How often the reports are reviewed Mandatory: Conditional: Detect by review Format: Monthly, Quarterly Allowed values: Monthly, Quarterly (list Review frequency) Example: Quarterly

## UP-01 Clients (upload)
UP-01 Clients not held in the legacy systems | [21 empty] | Step 22 of 51
← Back to Start here | Step 22 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [20 empty] | Ask a question →
Purpose | One row per individual or corporate client that is not in the legacy client master (for example a bank-referred prospect), with the KYC values BIBS keeps on the client: ID type and number, nationality, source of funds and risk rating. The legacy clients come through the Migration Console (C01 to C03); this upload also updates a client found by code, TIN, ID or name and birth date.
Provided by | Heads, Retail and Corporate Marketing; Product Owner, MBS
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Screen upload: Client & Policy › Clients › Clients, button Bulk Upload (upload type Bulk client creation and update); every row is checked and the result is shown per row
Source | Platform upload definition (column layout as the screen loads it)
Depends on | R01 Lists of values and MIS values →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | No | Yes | Conditional: Client Type is INDIVIDUAL | Conditional: Client Type is INDIVIDUAL | No | Conditional: Client Type is CORPORATE | No | No | No | Conditional: ID Type is given | No | No | No | No | No | No | No | No | Conditional: Bank Client is Y | No | No | No
Format | Text | Text | Text | Text | Text | Text | Date (dd-mmm-yyyy or yyyy-mm-dd) | 000-000-000-000 | Text | Text | Text | 09xxxxxxxxx or +639xxxxxxxxx | Text | Text | Text | Text | Text | Y or N | Text | Text | Text | Text
Allowed values | Free entry | INDIVIDUAL, CORPORATE (list Client Type (UP-01)) | Free entry | Free entry | Free entry | Free entry | A date, for example 15-Jan-2028 | Free entry | List Identification document: 10 values, see Reference lists | Free entry | Free entry | Free entry | Free entry | Free entry | Free entry | Free entry | CBG, COMBANK, CORBANK, RETAIL, INSTITUTIONAL (list Market segment) | Y or N | Free entry | FILIPINO, AMERICAN, CHINESE, JAPANESE, KOREAN, OTHERS (list Nationality) | SALARY, BUSINESS, REMITTANCE, INVESTMENT, PENSION, OTHERS (list Source of funds) | LOW, STANDARD, HIGH (list KYC risk rating)
What to enter | Prospect or client code to update; blank to create or match (a client or prospect known to BIBS) | Individual or corporate client | Last name of an individual | First name of an individual | Middle name | Registered name of a corporate client | Birth date of an individual | Tax identification number | Type of the identity document | Number of the identity document | E-mail address | Mobile number | Street address | City / municipality | Province | Postal code | Market segment | Client of the group's bank | Customer information file number at the group's bank | Nationality | Source of funds | Know-your-client risk rating
Row | Client Code | Client Type * | Last Name | First Name | Middle Name | Corporate Name | Birth Date | TIN | ID Type | ID Number | E-mail | Mobile | Address | City | Province | Postal Code | Market Segment | Bank Client | Bank CIF | Nationality | Source of Funds | Risk Rating
Example – overwrite or delete |  | INDIVIDUAL | Reyes | Ana | Cruz |  | 1990-04-15 | 123-456-789-000 | PASSPORT | P1234567A | ana.reyes@example.ph | 09171234567 | 12 Rizal St. | Pasig | Metro Manila | 1600 | CBG | Y |  | FILIPINO | SALARY | STANDARD
Note on B16: Client Code Prospect or client code to update; blank to create or match (a client or prospect known to BIBS) Mandatory: No Format: Text Allowed values: Free entry
Note on C16: Client Type Individual or corporate client Mandatory: Yes Format: Text Allowed values: INDIVIDUAL, CORPORATE (list Client Type (UP-01)) Example: INDIVIDUAL
Note on D16: Last Name Last name of an individual Mandatory: Conditional: Client Type is INDIVIDUAL Format: Text Allowed values: Free entry Example: Reyes
Note on E16: First Name First name of an individual Mandatory: Conditional: Client Type is INDIVIDUAL Format: Text Allowed values: Free entry Example: Ana
Note on F16: Middle Name Middle name Mandatory: No Format: Text Allowed values: Free entry Example: Cruz
Note on G16: Corporate Name Registered name of a corporate client Mandatory: Conditional: Client Type is CORPORATE Format: Text Allowed values: Free entry
Note on H16: Birth Date Birth date of an individual Mandatory: No Format: Date (dd-mmm-yyyy or yyyy-mm-dd) Allowed values: A date, for example 15-Jan-2028 Example: 15-Apr-1990
Note on I16: TIN Tax identification number Mandatory: No Format: 000-000-000-000 Allowed values: Free entry Example: 123-456-789-000
Note on J16: ID Type Type of the identity document Mandatory: No Format: Text Allowed values: List Identification document: 10 values, see Reference lists Example: PASSPORT
Note on K16: ID Number Number of the identity document Mandatory: Conditional: ID Type is given Format: Text Allowed values: Free entry Example: P1234567A
Note on L16: E-mail E-mail address Mandatory: No Format: Text Allowed values: Free entry Example: ana.reyes@example.ph
Note on M16: Mobile Mobile number Mandatory: No Format: 09xxxxxxxxx or +639xxxxxxxxx Allowed values: Free entry Example: 09171234567
Note on N16: Address Street address Mandatory: No Format: Text Allowed values: Free entry Example: 12 Rizal St.
Note on O16: City City / municipality Mandatory: No Format: Text Allowed values: Free entry Example: Pasig
Note on P16: Province Province Mandatory: No Format: Text Allowed values: Free entry Example: Metro Manila
Note on Q16: Postal Code Postal code Mandatory: No Format: Text Allowed values: Free entry Example: 1600
Note on R16: Market Segment Market segment Mandatory: No Format: Text Allowed values: CBG, COMBANK, CORBANK, RETAIL, INSTITUTIONAL (list Market segment) Example: CBG
Note on S16: Bank Client Client of the group's bank Mandatory: No Format: Y or N Allowed values: Y or N Example: Y
Note on T16: Bank CIF Customer information file number at the group's bank Mandatory: Conditional: Bank Client is Y Format: Text Allowed values: Free entry
Note on U16: Nationality Nationality Mandatory: No Format: Text Allowed values: FILIPINO, AMERICAN, CHINESE, JAPANESE, KOREAN, OTHERS (list Nationality) Example: FILIPINO
Note on V16: Source of Funds Source of funds Mandatory: No Format: Text Allowed values: SALARY, BUSINESS, REMITTANCE, INVESTMENT, PENSION, OTHERS (list Source of funds) Example: SALARY
Note on W16: Risk Rating Know-your-client risk rating Mandatory: No Format: Text Allowed values: LOW, STANDARD, HIGH (list KYC risk rating) Example: STANDARD

## C01 Client master
C01 Client master | [35 empty] | Step 23 of 51
← Back to Start here | Step 23 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [34 empty] | Ask a question →
Purpose | One row per record of Client master (individual and corporate) as extracted from QPS, EBIX, CMS. Key legacy_client_no. Sent as the file C01_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | Marketing data steward (to name); approved by Product Owner, MBS; Heads, Retail and Corporate Marketing; extracted by BDOI IT
Due | M3 (29 Jan 2027); deltas daily from T-14 days
How it is loaded | Migration Console: the file C01_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object C01; lands in: Client master, registered as migrated clients
Source | QPS, EBIX, CMS
Depends on | R01 Lists of values and MIS values → |  | R03 Sales organisation (units and account officers) → |  | D0-02 Branches →
Tax profile | The client's VAT treatment and default withholding code are kept in the party tax profile (template TX-01), not in the client master
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | Unique in the file | In the list | Mandatory for I | Mandatory for I | - | - | Mandatory for C | - | Mandatory for I; not in the future; age 0 to 120 | 9 to 12 digits; duplicate key K1 | Mapped | Mandatory when id_type is given; duplicate key K2 | Y or N | Duplicate key K5 if agreed | Mapped | Mapped | Mapped | Mapped | Mapped | Mapped in USER | Mapped | Mapped | Valid e-mail; soft key K6 | PH mobile format; soft key K6 | - | - | - | - | 4 digits | Mapped | Not in the future | Valid date | Mapped | Mapped | Valid date | Valid timestamp
Mandatory | Yes | Yes | Conditional: Mandatory for I | Conditional: Mandatory for I | No | No | Conditional: Mandatory for C | No | Conditional: Mandatory for I; not in the future; age 0 to 120 | No | No | Conditional: Mandatory when id_type is given; duplicate key K2 | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes
Format | Code, up to 30; As stored in legacy | Code, up to 1; Upper case | Text, up to 100; Free text | Text, up to 100; Free text | Text, up to 100; Free text | Text, up to 20; Free text | Text, up to 200; Free text | Text, up to 60; As registered | Date, up to 10; yyyy-MM-dd | Text, up to 20; 000-000-000-000 | Code, up to 40; As stored in legacy | Text, up to 60; As printed | Flag, up to 1; Y or N | Text, up to 40; Digits | Code, up to 40; As stored in legacy | Code, up to 40; As stored in legacy | Code, up to 40; As stored in legacy | Code, up to 40; As stored in legacy | Code, up to 40; As stored in legacy | Code, up to 50; As stored in legacy | Code, up to 20; As stored in legacy | Code, up to 20; As stored in legacy | Text, up to 120; name@domain | Text, up to 30; 09xxxxxxxxx or +639xxxxxxxxx | Text, up to 30; Free text | Text, up to 300; Free text | Text, up to 80; Free text | Text, up to 80; Free text | Text, up to 10; 4 digits | Code, up to 20; As stored in legacy | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd | Code, up to 20; As stored in legacy | Code, up to 20; As stored in legacy | Date, up to 10; yyyy-MM-dd | Timestamp, up to 19; yyyy-MM-dd HH:mm:ss
Allowed values | Free entry, up to 30 characters | I, C (list C01 client_type) | Free entry, up to 100 characters | Free entry, up to 100 characters | Free entry, up to 100 characters | Free entry, up to 20 characters | Free entry, up to 200 characters | Free entry, up to 60 characters | Free entry | Free entry, up to 20 characters | The legacy code; mapped by the code map LOV:ID_TYPE (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | Free entry, up to 60 characters | Y or N | Free entry, up to 40 characters | The legacy code; mapped by the code map LOV:NATIONALITY (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map LOV:SOURCE_OF_FUNDS (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map LOV:MARKET_SEGMENT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map MIS:CUSTOMER_SEGMENT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map MIS:BUSINESS_ORIGIN (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map USER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map SALES_UNIT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map BRANCH (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | Free entry, up to 120 characters | Free entry, up to 30 characters | Free entry, up to 30 characters | Free entry, up to 300 characters | Free entry, up to 80 characters | Free entry, up to 80 characters | Free entry, up to 10 characters | The legacy code; mapped by the code map STATUS:KYC (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | Free entry | Free entry | The legacy code; mapped by the code map LOV:KYC_RISK_RATING (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map STATUS:CLIENT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | Free entry | Free entry
What to enter | Client number in the source system | Individual or corporate | Last name (individual) | First name (individual) | Middle name | Name suffix | Registered name (corporate) | SEC or DTI registration number (corporate) | Birth date (individual) | Tax identification number | Government ID type | Government ID number | BDO bank client | BDO customer information file number | Nationality | Source of funds | Market segment | Customer segment (MIS) | Business origin (MIS) | Account officer | Sales unit of the client | Servicing branch | Primary e-mail | Primary mobile number | Landline | Primary street address | City / municipality | Province | Postal code | KYC status in legacy | Date KYC was verified | Next KYC review date | KYC risk rating | Client status in legacy | Date the client was created in legacy | Last change in legacy (survivorship and deltas)
Row | legacy_client_no * | client_type * | last_name | first_name | middle_name | suffix | corporate_name | registration_no | birth_date | tin | id_type | id_number | bank_client_flag | bank_cif | nationality | source_of_funds | market_segment * | customer_segment | business_origin | ao_user_id | sales_unit_code | branch_code | email | mobile | phone | address_line | city | province | postal_code | kyc_status | kyc_verified_date | kyc_review_due | risk_rating | client_status * | created_date * | last_updated *
Example – overwrite or delete | Q-0012345 | I | Reyes | Ana | Cruz | Jr. | Acme Trading Corp. | CS201912345 | 1990-04-15 | 123-456-789-000 | PASSPORT | P1234567A | Y | 1234567890 | FILIPINO | SALARY | CBG | AFFLUENT | BANK_REFERRAL | mreyes | T-RET-07 | MKT01 | ana.reyes@example.ph | 09171234567 | (02) 8123 4567 | 12 Rizal St., Brgy. San Antonio | Pasig | Metro Manila | 1600 | COMPLETE | 2024-03-11 | 2028-03-11 | STANDARD | ACTIVE | 2021-07-02 | 2026-08-30 14:22:05
Note on B18: legacy_client_no Client number in the source system Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: Free entry, up to 30 characters Example: Q-0012345
Note on C18: client_type Individual or corporate Mandatory: Yes Format: Code, up to 1; Upper case Allowed values: I, C (list C01 client_type) Example: I
Note on D18: last_name Last name (individual) Mandatory: Conditional: Mandatory for I Format: Text, up to 100; Free text Allowed values: Free entry, up to 100 characters Example: Reyes
Note on E18: first_name First name (individual) Mandatory: Conditional: Mandatory for I Format: Text, up to 100; Free text Allowed values: Free entry, up to 100 characters Example: Ana
Note on F18: middle_name Middle name Mandatory: No Format: Text, up to 100; Free text Allowed values: Free entry, up to 100 characters Example: Cruz
Note on G18: suffix Name suffix Mandatory: No Format: Text, up to 20; Free text Allowed values: Free entry, up to 20 characters Example: Jr.
Note on H18: corporate_name Registered name (corporate) Mandatory: Conditional: Mandatory for C Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Acme Trading Corp.
Note on I18: registration_no SEC or DTI registration number (corporate) Mandatory: No Format: Text, up to 60; As registered Allowed values: Free entry, up to 60 characters Example: CS201912345
Note on J18: birth_date Birth date (individual) Mandatory: Conditional: Mandatory for I; not in the future; age 0 to 120 Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 1990-04-15
Note on K18: tin Tax identification number Mandatory: No Format: Text, up to 20; 000-000-000-000 Allowed values: Free entry, up to 20 characters Example: 123-456-789-000
Note on L18: id_type Government ID type Mandatory: No Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map LOV:ID_TYPE (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: PASSPORT
Note on M18: id_number Government ID number Mandatory: Conditional: Mandatory when id_type is given; duplicate key K2 Format: Text, up to 60; As printed Allowed values: Free entry, up to 60 characters Example: P1234567A
Note on N18: bank_client_flag BDO bank client Mandatory: No Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y
Note on O18: bank_cif BDO customer information file number Mandatory: No Format: Text, up to 40; Digits Allowed values: Free entry, up to 40 characters Example: 1234567890
Note on P18: nationality Nationality Mandatory: No Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map LOV:NATIONALITY (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: FILIPINO
Note on Q18: source_of_funds Source of funds Mandatory: No Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map LOV:SOURCE_OF_FUNDS (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: SALARY
Note on R18: market_segment Market segment Mandatory: Yes Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map LOV:MARKET_SEGMENT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: CBG
Note on S18: customer_segment Customer segment (MIS) Mandatory: No Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map MIS:CUSTOMER_SEGMENT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: AFFLUENT
Note on T18: business_origin Business origin (MIS) Mandatory: No Format: Code, up to 40; As stored in legacy Allowed values: The legacy code; mapped by the code map MIS:BUSINESS_ORIGIN (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: BANK_REFERRAL
Note on U18: ao_user_id Account officer Mandatory: No Format: Code, up to 50; As stored in legacy Allowed values: The legacy code; mapped by the code map USER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: mreyes
Note on V18: sales_unit_code Sales unit of the client Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map SALES_UNIT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: T-RET-07
Note on W18: branch_code Servicing branch Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map BRANCH (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: MKT01
Note on X18: email Primary e-mail Mandatory: No Format: Text, up to 120; name@domain Allowed values: Free entry, up to 120 characters Example: ana.reyes@example.ph
Note on Y18: mobile Primary mobile number Mandatory: No Format: Text, up to 30; 09xxxxxxxxx or +639xxxxxxxxx Allowed values: Free entry, up to 30 characters Example: 09171234567
Note on Z18: phone Landline Mandatory: No Format: Text, up to 30; Free text Allowed values: Free entry, up to 30 characters Example: (02) 8123 4567
Note on AA18: address_line Primary street address Mandatory: No Format: Text, up to 300; Free text Allowed values: Free entry, up to 300 characters Example: 12 Rizal St., Brgy. San Antonio
Note on AB18: city City / municipality Mandatory: No Format: Text, up to 80; Free text Allowed values: Free entry, up to 80 characters Example: Pasig
Note on AC18: province Province Mandatory: No Format: Text, up to 80; Free text Allowed values: Free entry, up to 80 characters Example: Metro Manila
Note on AD18: postal_code Postal code Mandatory: No Format: Text, up to 10; 4 digits Allowed values: Free entry, up to 10 characters Example: 1600
Note on AE18: kyc_status KYC status in legacy Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:KYC (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: COMPLETE
Note on AF18: kyc_verified_date Date KYC was verified Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2024-03-11
Note on AG18: kyc_review_due Next KYC review date Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2028-03-11
Note on AH18: risk_rating KYC risk rating Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map LOV:KYC_RISK_RATING (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: STANDARD
Note on AI18: client_status Client status in legacy Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map STATUS:CLIENT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: ACTIVE
Note on AJ18: created_date Date the client was created in legacy Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2021-07-02
Note on AK18: last_updated Last change in legacy (survivorship and deltas) Mandatory: Yes Format: Timestamp, up to 19; yyyy-MM-dd HH:mm:ss Allowed values: Free entry Example: 2026-08-30 14:22:05

## D0-10 Tax codes
D0-10 Tax codes | [9 empty] | Step 24 of 51
← Back to Start here | Step 24 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [8 empty] | Ask a question →
Purpose | The tax codes with their ATC, rate and GL account
Provided by | Head, Comptrollership (Tax)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Tax Codes & Forms (Tax & Statutory), authorised by Comptrollership
Source | BIR ATC list; current tax set-up
Depends on | D0-06 Chart of accounts →
Checklist | One row per kind of tax is written below the header; give the code, the ATC, the rate, the GL account and the dates of each (rates and ATCs as BDOI's tax adviser confirms them), and add one row per ATC. The sheet D0-10 Tax checklist says what each covers and what BIBS does not hold
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Conditional: withholding | No | Yes | Yes | No | Yes | No
Format | Up to 20 capitals | Text | EWT, FWT, VAT, PT | BIR ATC | List PAYEE_CLASS | 0 to 100 | Account of D0-06 | Text | dd-MMM-yyyy | dd-MMM-yyyy
Allowed values | Free entry, up to 20 characters | Free entry | List Tax type (BIBS): 9 values, see Reference lists | Free entry | INDIVIDUAL, CORPORATE (list Payee class (BIR)) | A number from 0 to 100 | A code of D0-06 Chart of accounts, column Account Code | Free entry | A date, for example 15-Jan-2028 | A date, for example 15-Jan-2028
What to enter | Code of the tax | Name shown on screens | Kind of tax | Alphanumeric tax code | Payees it applies to | Rate of the tax | Account of the tax | Nature of the income payment | First date of the rate | Last date of the rate
Row | Tax code * | Name * | Tax type * | ATC | Payee class | Rate % * | GL account * | Income nature | Effective from * | Effective to
Example – overwrite or delete | EWT_WC158 | EWT 1% - goods | EWT | WC158 | CORPORATE | 1 | 2150.02 | Purchase of goods | 2028-01-01
|  | Output VAT on commission and service fees | VAT_OUTPUT
|  | Zero-rated sales (commission and fees on zero-rated clients) | VAT_ZERO_RATED
|  | VAT-exempt sales | VAT_EXEMPT
|  | Input VAT on purchases | VAT_INPUT
|  | Creditable withholding tax withheld by insurers on BDOI's commission (2307 received) | EWT
|  | Creditable withholding tax withheld by government and top withholding agent clients on service fees | EWT
|  | EWT BDOI withholds on suppliers: one row per ATC (professional fees, rentals, contractors, goods, services, commissions) | EWT
Note on B17: Tax code Code of the tax Mandatory: Yes Format: Up to 20 capitals Allowed values: Free entry, up to 20 characters Example: EWT_WC158
Note on C17: Name Name shown on screens Mandatory: Yes Format: Text Allowed values: Free entry Example: EWT 1% - goods
Note on D17: Tax type Kind of tax Mandatory: Yes Format: EWT, FWT, VAT, PT Allowed values: List Tax type (BIBS): 9 values, see Reference lists Example: EWT
Note on E17: ATC Alphanumeric tax code Mandatory: Conditional: withholding Format: BIR ATC Allowed values: Free entry Example: WC158
Note on F17: Payee class Payees it applies to Mandatory: No Format: List PAYEE_CLASS Allowed values: INDIVIDUAL, CORPORATE (list Payee class (BIR)) Example: CORPORATE
Note on G17: Rate % Rate of the tax Mandatory: Yes Format: 0 to 100 Allowed values: A number from 0 to 100 Example: 1
Note on H17: GL account Account of the tax Mandatory: Yes Format: Account of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 2150.02
Note on I17: Income nature Nature of the income payment Mandatory: No Format: Text Allowed values: Free entry Example: Purchase of goods
Note on J17: Effective from First date of the rate Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Jan-2028
Note on K17: Effective to Last date of the rate Mandatory: No Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028

## D0-10 Tax checklist
D0-10 Tax checklist: BDOI's own taxes
← Back to Start here | One row per kind of tax: what BIBS does, where it is set up (D0-10 tax codes, TX-01 party tax profiles, TX-02 tax forms) and what BIBS does not hold
Tax | What BIBS does | Where it is set up | What BDOI provides or confirms | Held by BIBS | Question | Rule confirmed | BDOI comments | Status
Output VAT on commission and service fees | Tax type VAT_OUTPUT; the VAT worksheet prepares the quarterly VAT return (2550Q) from the sales. | D0-10 (code, rate, GL account); TX-02 form 2550Q | Code, rate and GL account of output VAT | Yes | TX-Q05 |  |  | Not started
Zero-rated and VAT-exempt sales | Tax types VAT_ZERO_RATED and VAT_EXEMPT; a client's VAT treatment (TX-01) classifies a sale without VAT. | D0-10; TX-01 VAT treatment | The zero-rated and exempt cases and the clients concerned | Yes | TX-Q05 |  |  | Not started
Input VAT | Tax type VAT_INPUT; credited against output VAT on the VAT return. | D0-10; TX-02 credit account | Code, rate and GL account of input VAT | Yes | TX-Q05 |  |  | Not started
Creditable withholding tax withheld by insurers on BDOI's commission | The 2307 certificates received are recorded on Certificates Received (ATC, income, tax) and posted against the receivable. | D0-10 EWT codes; TX-01 default ATC of each insurer | The ATCs and rates the insurers withhold on commission | Yes | TX-Q05 |  |  | Not started
EWT BDOI withholds on suppliers | Tax type EWT, one code per ATC; withheld on payments, 2307 issued, monthly 0619-E, quarterly 1601-EQ, QAP and alphalists. | D0-10 (one row per ATC); TX-01 default ATC of each supplier; TX-02 forms | The ATC list with rates, income nature and GL account | Yes | TX-Q05 |  |  | Not started
Government payors (final VAT and EWT withheld) | BIBS has no final VAT or final withholding tax type and no government-payor flag on the client. | Not held (sheet Gaps) | How government withholding is to be recorded | No | TX-Q06 |  |  | Not started
Top withholding agent clients | Withholding by a client is recorded as a 2307 received; BIBS has no top withholding agent flag on the client. | Not held (sheet Gaps) | Whether a flag is needed and what it must do | No | TX-Q09 |  |  | Not started
Final tax on bank interest | BIBS has no final withholding tax type; bank interest is posted by journal. | Not held (sheet Gaps) | Whether BIBS must record it as a tax | No | TX-Q06 |  |  | Not started
Percentage tax on BDOI's own receipts | The premium tax type is a charge on premiums; BIBS has no percentage tax on BDOI's own receipts. | Not held (sheet Gaps) | Whether any BDOI income is subject to percentage tax | No | TX-Q06 |  |  | Not started
Tax returns and the filing calendar | BIBS knows the forms 2550Q, 0619-E, 1601-EQ, 1601-C (prepared outside BIBS, reminder only) and the premium-levy returns 2000 (DST), 2551Q (premium tax), local business tax and FST, which the insurers file. | TX-02 | The forms BDOI files, their due dates and accounts | Yes | TX-Q07 |  |  | Not started
Tax exemption certificates of clients | BIBS keeps no exemption certificate number or validity. | Not held (sheet Gaps) | Whether they must be kept and checked | No | TX-Q09 |  |  | Not started
Company tax registration | BIBS keeps the TIN with its branch code (D0-01) only; no RDO, VAT registration, CAS or e-invoicing permit. | D0-01; not held (sheet Gaps) | The registration details needed on the forms and receipts | No | TX-Q08 |  |  | Not started
Note on A4: Tax: Item
Note on B4: What BIBS does: The rule of the platform
Note on C4: Where it is set up: Template, column or list
Note on D4: What BDOI provides or confirms: Input asked from BDOI
Note on E4: Held by BIBS: Yes, or No (sheet Gaps)
Note on F4: Question: Ref of the question in the BDOI Requirements and Inputs workbook
Note on G4: Rule confirmed: Agree, or Change (describe in BDOI comments)
Note on H4: BDOI comments: Decision, value or comment of the owner
Note on I4: Status: Status of the item

## D0-11 Bank accounts
D0-11 Company bank accounts | [8 empty] | Step 25 of 51
← Back to Start here | Step 25 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [7 empty] | Ask a question →
Purpose | The bank accounts of BDOI used for collections and disbursements
Provided by | Head, Comptrollership; Treasury
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Bank Accounts and Checks (Disbursement), authorised by Comptrollership
Source | BDOI bank account list
Depends on | D0-06 Chart of accounts → |  | D0-02 Branches →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes
Format | Up to 20 capitals | Text | Bank name | As printed by the bank | ISO 4217 | Account of D0-06 with a bank category | Account of D0-06 | Code of D0-02 | Format of the bank advice
Allowed values | Free entry, up to 20 characters | Free entry | Free entry | Free entry | Free entry, up to 3 characters | A code of D0-06 Chart of accounts, column Account Code | A code of D0-06 Chart of accounts, column Account Code | A code of D0-02 Branches, column Branch code | Free entry
What to enter | Code of the account in BIBS | Name shown on screens | Bank of the account | Account number | Currency of the account | Cash-in-bank account | Account of issued post-dated checks | Branch that uses the account | Format of the notification to the payee
Row | Bank account code * | Name * | Bank * | Account number * | Currency * | GL account * | PDC clearing account | Branch code | Payment notification format *
Example – overwrite or delete | BDO-CA-001 | BDO Makati current account | BDO Unibank, Inc. | 000123456789 | PHP | 1110.01 | 2241 | HO | EMAIL
Note on B16: Bank account code Code of the account in BIBS Mandatory: Yes Format: Up to 20 capitals Allowed values: Free entry, up to 20 characters Example: BDO-CA-001
Note on C16: Name Name shown on screens Mandatory: Yes Format: Text Allowed values: Free entry Example: BDO Makati current account
Note on D16: Bank Bank of the account Mandatory: Yes Format: Bank name Allowed values: Free entry Example: BDO Unibank, Inc.
Note on E16: Account number Account number Mandatory: Yes Format: As printed by the bank Allowed values: Free entry Example: 000123456789
Note on F16: Currency Currency of the account Mandatory: Yes Format: ISO 4217 Allowed values: Free entry, up to 3 characters Example: PHP
Note on G16: GL account Cash-in-bank account Mandatory: Yes Format: Account of D0-06 with a bank category Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 1110.01
Note on H16: PDC clearing account Account of issued post-dated checks Mandatory: No Format: Account of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 2241
Note on I16: Branch code Branch that uses the account Mandatory: No Format: Code of D0-02 Allowed values: A code of D0-02 Branches, column Branch code Example: HO
Note on J16: Payment notification format Format of the notification to the payee Mandatory: Yes Format: Format of the bank advice Allowed values: Free entry Example: EMAIL

## PM-01 Product catalogue
PM-01 Product catalogue | [21 empty] | Step 26 of 51
← Back to Start here | Step 26 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [20 empty] | Ask a question →
Purpose | Product lines, cover types and subtypes, and every product (risk code) with its features
Provided by | Product Owner, Marketing Business System (MBS)
Due | 9-Apr-2027 – Reference data for Trial migration 1 (M4)
How it is loaded | Data migration object R05 (product lines, cover types, products) through the catalogue services, pending authorisation; after go-live on Products (SCR-PM-11)
Source | Legacy QPS and EBIX product lists, completed by MBS
Depends on | PM-09 Lists of values and parameters → |  | R05 Product lines, cover types, products and risk codes →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | Conditional: package products | Conditional: with the code | No | Yes | Yes | No | Yes | No | Yes | No | No | Yes | Yes | No | No | No | No | No | No
Format | Up to 30 capitals | Text | Regular expression | Up to 30 capitals | Text | Cover type code | 1 to 20 capitals or digits | Up to 200 characters | Text | Y or N | Codes separated by commas; blank = all | PAID or CLIENT_CONFIRMATION | BY_RULES, ALWAYS or NEVER | Up to four decimals | Percentage | Amount in PHP | Amount in PHP | Y or N | Y or N | Y or N | Y or N; 2 to 10 years | Y or N
Allowed values | Free entry, up to 30 characters | Free entry | Free entry | Free entry, up to 30 characters | Free entry | A code of PM-01 Product catalogue, column Cover type code | Free entry, up to 20 characters | Free entry, up to 200 characters | Free entry | Y or N | One or more codes of the list Market segment (Reference lists), separated by commas | PAID, CLIENT_CONFIRMATION (list Placement after) | BY_RULES, ALWAYS, NEVER (list TSU review) | A number from 0 to 100 | A number from 0 to 100 | A number | A number | Y or N | Y or N | Y or N | Free entry | Y or N
What to enter | Product line (level 1), for example MOTOR, PROPERTY | Name shown in the drop-downs | Naming convention of the risk codes of the line, when BDOI states one | Cover type (level 2) of the line | Name of the cover type | Only for a subtype (one level below a cover type) | Product code (level 3); unique | Name shown to users | Code of the product in QPS or EBIX, for the migration map | Y for a package product (terms change through versions) | Segments the product is offered to (list MARKET_SEGMENT) | Payment gate before placement | When TSU reviews an account of the product | Rate of a non-package product; for a package, of version 1 | Commission when no insurer rate applies | Minimum premium of the product | Above it the account goes to TSU | Several vehicles on one account | Mortgage or loan related | Premium may be paid directly to the insurer | Multi-year term and its maximum | Free First Year eligible
Row | Line code * | Line name * | Risk-code pattern | Cover type code | Cover type name | Parent cover type | Risk code * | Product name * | Legacy code | Package * | Market segments | Placement after * | TSU review | Default rate % | Default commission % * | Minimum premium * | Package TSI limit | Fleet | Mortgage related | Direct payment allowed | Multi-year / Maximum term | Free First Year
Example – overwrite or delete | MOTOR | Motor | MTR[0-9]{2} | COMPREHENSIVE | Comprehensive |  | MTR30 | Motor Fleet Plus | QPS-MFP | Y | COMBANK | PAID | BY_RULES | 1.2 | 15 | 5000 | 5000000 | Y | N | N | N | N
Note on B16: Line code Product line (level 1), for example MOTOR, PROPERTY Mandatory: Yes Format: Up to 30 capitals Allowed values: Free entry, up to 30 characters Example: MOTOR
Note on C16: Line name Name shown in the drop-downs Mandatory: Yes Format: Text Allowed values: Free entry Example: Motor
Note on D16: Risk-code pattern Naming convention of the risk codes of the line, when BDOI states one Mandatory: No Format: Regular expression Allowed values: Free entry Example: MTR[0-9]{2}
Note on E16: Cover type code Cover type (level 2) of the line Mandatory: Conditional: package products Format: Up to 30 capitals Allowed values: Free entry, up to 30 characters Example: COMPREHENSIVE
Note on F16: Cover type name Name of the cover type Mandatory: Conditional: with the code Format: Text Allowed values: Free entry Example: Comprehensive
Note on G16: Parent cover type Only for a subtype (one level below a cover type) Mandatory: No Format: Cover type code Allowed values: A code of PM-01 Product catalogue, column Cover type code
Note on H16: Risk code Product code (level 3); unique Mandatory: Yes Format: 1 to 20 capitals or digits Allowed values: Free entry, up to 20 characters Example: MTR30
Note on I16: Product name Name shown to users Mandatory: Yes Format: Up to 200 characters Allowed values: Free entry, up to 200 characters Example: Motor Fleet Plus
Note on J16: Legacy code Code of the product in QPS or EBIX, for the migration map Mandatory: No Format: Text Allowed values: Free entry Example: QPS-MFP
Note on K16: Package Y for a package product (terms change through versions) Mandatory: Yes Format: Y or N Allowed values: Y or N Example: Y
Note on L16: Market segments Segments the product is offered to (list MARKET_SEGMENT) Mandatory: No Format: Codes separated by commas; blank = all Allowed values: One or more codes of the list Market segment (Reference lists), separated by commas Example: COMBANK
Note on M16: Placement after Payment gate before placement Mandatory: Yes Format: PAID or CLIENT_CONFIRMATION Allowed values: PAID, CLIENT_CONFIRMATION (list Placement after) Example: PAID
Note on N16: TSU review When TSU reviews an account of the product Mandatory: No Format: BY_RULES, ALWAYS or NEVER Allowed values: BY_RULES, ALWAYS, NEVER (list TSU review) Example: BY_RULES
Note on O16: Default rate % Rate of a non-package product; for a package, of version 1 Mandatory: No Format: Up to four decimals Allowed values: A number from 0 to 100 Example: 1.2000
Note on P16: Default commission % Commission when no insurer rate applies Mandatory: Yes Format: Percentage Allowed values: A number from 0 to 100 Example: 15
Note on Q16: Minimum premium Minimum premium of the product Mandatory: Yes Format: Amount in PHP Allowed values: A number Example: 5000.00
Note on R16: Package TSI limit Above it the account goes to TSU Mandatory: No Format: Amount in PHP Allowed values: A number Example: 5000000.00
Note on S16: Fleet Several vehicles on one account Mandatory: No Format: Y or N Allowed values: Y or N Example: Y
Note on T16: Mortgage related Mortgage or loan related Mandatory: No Format: Y or N Allowed values: Y or N Example: N
Note on U16: Direct payment allowed Premium may be paid directly to the insurer Mandatory: No Format: Y or N Allowed values: Y or N Example: N
Note on V16: Multi-year / Maximum term Multi-year term and its maximum Mandatory: No Format: Y or N; 2 to 10 years Allowed values: Free entry Example: N
Note on W16: Free First Year Free First Year eligible Mandatory: No Format: Y or N Allowed values: Y or N Example: N

## R08 Chart of accounts mapping
R08 Chart of accounts mapping | [7 empty] | Step 27 of 51
← Back to Start here | Step 27 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | One row per record of Chart of accounts mapping (legacy GL account to BIBS account) as extracted from EBIX, ISYS GL. Key legacy_account_code. Sent as the file R08_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | Comptrollership data steward (to name); approved by Head, Comptrollership; Product Owner FRBS and ACSL; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Migration Console: the file R08_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object R08; lands in: GL account code map to the BIBS chart of accounts (chart configured by Comptrollership)
Source | EBIX, ISYS GL
Depends on | D0-06 Chart of accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | Unique | Not blank | In the list | In the list | In the list | Mandatory when legacy_control_type is NONE; exists and active in BIBS | Y or N | -
Mandatory | Yes | Yes | Yes | Yes | No | Conditional: Mandatory when legacy_control_type is NONE; exists and active in BIBS | No | No
Format | Code, up to 30; As stored in legacy | Text, up to 200; Free text | Code, up to 12; Upper case | Code, up to 2; Upper case | Code, up to 20; Upper case | Code, up to 30; As in the BIBS chart | Flag, up to 1; Y or N | Text, up to 300; Free text
Allowed values | Free entry, up to 30 characters | Free entry, up to 200 characters | ASSET, LIABILITY, EQUITY, INCOME, EXPENSE (list R08 account_type) | DR, CR (list R08 normal_balance) | List R08 legacy_control_type: 8 values, see Reference lists | Account codes of the BIBS chart of accounts | Y or N | Free entry, up to 300 characters
What to enter | Legacy GL account code | Legacy account name | Account type | Normal balance side | Marks the legacy control accounts whose balance F01 or F02 carries in detail | BIBS account the legacy account maps to (filled by Comptrollership) | Balances are kept per branch | Mapping remarks
Row | legacy_account_code * | legacy_account_name * | account_type * | normal_balance * | legacy_control_type | bibs_account_code | branch_specific_flag | remarks
Example – overwrite or delete | 1101-02 | Cash in Bank - BDO Makati | ASSET | DR | NONE | X102.03 (illustrative code, not in use) | Y | Merged with 1201-01
Note on B17: legacy_account_code Legacy GL account code Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: Free entry, up to 30 characters Example: 1101-02
Note on C17: legacy_account_name Legacy account name Mandatory: Yes Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Cash in Bank - BDO Makati
Note on D17: account_type Account type Mandatory: Yes Format: Code, up to 12; Upper case Allowed values: ASSET, LIABILITY, EQUITY, INCOME, EXPENSE (list R08 account_type) Example: ASSET
Note on E17: normal_balance Normal balance side Mandatory: Yes Format: Code, up to 2; Upper case Allowed values: DR, CR (list R08 normal_balance) Example: DR
Note on F17: legacy_control_type Marks the legacy control accounts whose balance F01 or F02 carries in detail Mandatory: No Format: Code, up to 20; Upper case Allowed values: List R08 legacy_control_type: 8 values, see Reference lists Example: NONE
Note on G17: bibs_account_code BIBS account the legacy account maps to (filled by Comptrollership) Mandatory: Conditional: Mandatory when legacy_control_type is NONE; exists and active in BIBS Format: Code, up to 30; As in the BIBS chart Allowed values: Account codes of the BIBS chart of accounts Example: X102.03 (illustrative code, not in use)
Note on H17: branch_specific_flag Balances are kept per branch Mandatory: No Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y
Note on I17: remarks Mapping remarks Mandatory: No Format: Text, up to 300; Free text Allowed values: Free entry, up to 300 characters Example: Merged with 1201-01

## UP-02 Payees (upload)
UP-02 Payees | [10 empty] | Step 28 of 51
← Back to Start here | Step 28 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [9 empty] | Ask a question →
Purpose | One row per payee of Disbursement (suppliers, service providers, employees, government agencies and other payees) with the payment modes, currency and bank account. This is also the layout of the payees of the legacy systems (migration object R09, in scope if BDOI confirms it).
Provided by | Product Owner, Comptrollership - Disbursement
Due | 9-Apr-2027 – Reference data for Trial migration 1 (M4)
How it is loaded | Screen upload: Finance › Disbursement › Disbursement Uploads, upload type Payee Migration; the payees and their bank accounts come in for authorisation
Source | Platform upload definition (column layout as the screen loads it)
Depends on | MD-01 Business partners (reinsurers, intermediaries, suppliers) →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | No | No | No | Yes | Yes | Yes | No | Conditional: a mode crediting an account (CTA, TT, online banking) is allowed
Format | Text | Text | Text | Text | Text | Text | Text | Mode codes separated by ¦, e.g. CHECK¦CTA | ISO currency code, 3 letters | Text | Text
Allowed values | Free entry | SUPPLIER, INSURER, EMPLOYEE, CLIENT, GOVERNMENT, OTHER (list Payee class) | Free entry | Free entry | Free entry | Free entry | List Default mode (UP-02): 7 values, see Reference lists | Codes of the Default mode list | Free entry | Free entry | Free entry
What to enter | Party code of the payee (a party known to BIBS) | Class of the payee | Payee name | Address | E-mail for payment advices | Tax identification number | Mode of payment used by default | Modes of payment allowed for the payee | Currency of payment (a currency known to BIBS) | Bank of the payee account | Account number of the payee at the bank
Row | Payee code * | Payee class * | Name * | Address | Email | TIN | Default mode * | Allowed modes * | Currency * | Bank | Account no
Example – overwrite or delete | SUP-0001 | SUPPLIER | Acme Office Supply | Makati City | ap@acme.example | 123-456-789-000 | CHECK | CHECK¦CTA | PHP | Philippine National Bank | 001234567890
Note on B16: Payee code Party code of the payee (a party known to BIBS) Mandatory: Yes Format: Text Allowed values: Free entry Example: SUP-0001
Note on C16: Payee class Class of the payee Mandatory: Yes Format: Text Allowed values: SUPPLIER, INSURER, EMPLOYEE, CLIENT, GOVERNMENT, OTHER (list Payee class) Example: SUPPLIER
Note on D16: Name Payee name Mandatory: Yes Format: Text Allowed values: Free entry Example: Acme Office Supply
Note on E16: Address Address Mandatory: No Format: Text Allowed values: Free entry Example: Makati City
Note on F16: Email E-mail for payment advices Mandatory: No Format: Text Allowed values: Free entry Example: ap@acme.example
Note on G16: TIN Tax identification number Mandatory: No Format: Text Allowed values: Free entry Example: 123-456-789-000
Note on H16: Default mode Mode of payment used by default Mandatory: Yes Format: Text Allowed values: List Default mode (UP-02): 7 values, see Reference lists Example: CHECK
Note on I16: Allowed modes Modes of payment allowed for the payee Mandatory: Yes Format: Mode codes separated by ¦, e.g. CHECK¦CTA Allowed values: Codes of the Default mode list Example: CHECK¦CTA
Note on J16: Currency Currency of payment (a currency known to BIBS) Mandatory: Yes Format: ISO currency code, 3 letters Allowed values: Free entry Example: PHP
Note on K16: Bank Bank of the payee account Mandatory: No Format: Text Allowed values: Free entry Example: Philippine National Bank
Note on L16: Account no Account number of the payee at the bank Mandatory: Conditional: a mode crediting an account (CTA, TT, online banking) is allowed Format: Text Allowed values: Free entry Example: 001234567890

## D0-01 Company
D0-01 Company | [8 empty] | Step 29 of 51
← Back to Start here | Step 29 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [7 empty] | Ask a question →
Purpose | The company record of BDOI
Provided by | Head, Comptrollership
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Companies (Setup & Administration), entered by the System Administrator and authorised by Comptrollership
Source | BDOI registration documents and the current chart of accounts
Depends on | D0-06 Chart of accounts →
Tax registration | The TIN with its branch code is the only BIR registration detail BIBS keeps; the RDO, VAT registration, CAS / e-invoicing permit are asked as questions (sheet Gaps). The receipt series in use come from R11
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Format | Up to 10 capitals | Up to 200 characters | 000-000-000-00000 | Text | ISO 4217 | 1 to 12 | Whole number | Whole number | Account code of D0-06
Allowed values | Free entry, up to 10 characters | Free entry, up to 200 characters | Free entry | Free entry | Free entry, up to 3 characters | A whole number from 1 to 12 | A whole number from 0 to 365 | A whole number from 0 to 365 | A code of D0-06 Chart of accounts, column Account Code
What to enter | Code of the company on every record | Name as registered with the SEC | Tax identification number with branch code | Address printed on receipts and BIR forms | Currency of the books | First month of the financial year | How many days before today a posting may be dated | How many days after today a posting may be dated | Account that receives the year-end result
Row | Company code * | Registered name * | TIN * | Registered address * | Base currency * | Fiscal year start month * | Back-value days * | Forward-value days * | Retained earnings account *
Example – overwrite or delete | BDOI | BDO Insurance and Reinsurance Brokers, Inc. | 000-000-000-00000 | 7899 Makati Avenue, Makati City | PHP | 1 | 5 | 0 | 3200
Note on B17: Company code Code of the company on every record Mandatory: Yes Format: Up to 10 capitals Allowed values: Free entry, up to 10 characters Example: BDOI
Note on C17: Registered name Name as registered with the SEC Mandatory: Yes Format: Up to 200 characters Allowed values: Free entry, up to 200 characters Example: BDO Insurance and Reinsurance Brokers, Inc.
Note on D17: TIN Tax identification number with branch code Mandatory: Yes Format: 000-000-000-00000 Allowed values: Free entry Example: 000-000-000-00000
Note on E17: Registered address Address printed on receipts and BIR forms Mandatory: Yes Format: Text Allowed values: Free entry Example: 7899 Makati Avenue, Makati City
Note on F17: Base currency Currency of the books Mandatory: Yes Format: ISO 4217 Allowed values: Free entry, up to 3 characters Example: PHP
Note on G17: Fiscal year start month First month of the financial year Mandatory: Yes Format: 1 to 12 Allowed values: A whole number from 1 to 12 Example: 1
Note on H17: Back-value days How many days before today a posting may be dated Mandatory: Yes Format: Whole number Allowed values: A whole number from 0 to 365 Example: 5
Note on I17: Forward-value days How many days after today a posting may be dated Mandatory: Yes Format: Whole number Allowed values: A whole number from 0 to 365 Example: 0
Note on J17: Retained earnings account Account that receives the year-end result Mandatory: Yes Format: Account code of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 3200

## D0-08 Accounting rules
D0-08 Accounting rules | [9 empty] | Step 30 of 51
← Back to Start here | Step 30 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [8 empty] | Ask a question →
Purpose | The debit and credit accounts of each accounting event of the platform
Provided by | Head, Comptrollership
Due | 4-Jan-2027 – Platform set-up for Drop 1 SIT
How it is loaded | Accounting Rules (Accounting Engine), checked with the Rule Simulator and authorised by Comptrollership
Source | The posting rules of EBIX and ISYS; the accounting events listed on the sheet Ref Accounting events
Depends on | D0-04 Cost centres and business lines → |  | D0-06 Chart of accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | No | Yes | Yes | Yes | Yes | Yes | No
Format | Code of the sheet Ref Accounting events | Text | Code of D0-04; blank = every line | ISO 4217; blank = every currency | dd-MMM-yyyy | 1, 2, 3 | DEBIT or CREDIT | Account of D0-06 | Component of the event | Text
Allowed values | List Accounting event: 65 values, see Reference lists | Free entry | A code of D0-04 Cost centres and business lines, column Code | Free entry | A date, for example 15-Jan-2028 | A whole number from 1 to 99 | DEBIT, CREDIT (list Debit or credit) | A code of D0-06 Chart of accounts, column Account Code | Free entry | Free entry
What to enter | Event that the rule posts | Name of the rule | Line the rule applies to | Currency the rule applies to | First posting date of the rule | Order of the line in the entry | Side of the line | Account posted | Amount the line posts | Text of the journal line
Row | Event type * | Rule name * | Business line | Currency | Effective from * | Line * | Debit or credit * | Account code * | Amount component * | Narration
Example – overwrite or delete | PREMIUM_BOOKED | Premium booked - non-life |  |  | 2028-01-01 | 1 | DEBIT | 1210.07 | GROSS_PREMIUM | Premium receivable
Note on B16: Event type Event that the rule posts Mandatory: Yes Format: Code of the sheet Ref Accounting events Allowed values: List Accounting event: 65 values, see Reference lists Example: PREMIUM_BOOKED
Note on C16: Rule name Name of the rule Mandatory: Yes Format: Text Allowed values: Free entry Example: Premium booked - non-life
Note on D16: Business line Line the rule applies to Mandatory: No Format: Code of D0-04; blank = every line Allowed values: A code of D0-04 Cost centres and business lines, column Code
Note on E16: Currency Currency the rule applies to Mandatory: No Format: ISO 4217; blank = every currency Allowed values: Free entry
Note on F16: Effective from First posting date of the rule Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Jan-2028
Note on G16: Line Order of the line in the entry Mandatory: Yes Format: 1, 2, 3 Allowed values: A whole number from 1 to 99 Example: 1
Note on H16: Debit or credit Side of the line Mandatory: Yes Format: DEBIT or CREDIT Allowed values: DEBIT, CREDIT (list Debit or credit) Example: DEBIT
Note on I16: Account code Account posted Mandatory: Yes Format: Account of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 1210.07
Note on J16: Amount component Amount the line posts Mandatory: Yes Format: Component of the event Allowed values: Free entry Example: GROSS_PREMIUM
Note on K16: Narration Text of the journal line Mandatory: No Format: Text Allowed values: Free entry Example: Premium receivable

## D0-09 Legacy accounts
D0-09 Legacy control accounts | [5 empty] | Step 31 of 51
← Back to Start here | Step 31 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The accounts that carry the migrated invoices and unapplied payments until they run off, and Migration Clearing
Provided by | Head, Comptrollership
Due | 1-Dec-2026 – Drafts with the Drop 0 sign-off
How it is loaded | Created with the chart of accounts (D0-06); named in the accounting rules of the legacy items
Source | Proposed rule PR-DM-02 of the Data Migration set
Depends on | D0-06 Chart of accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Conditional: Premium Receivable - Legacy | Yes | No | No
Format | Premium Receivable - Legacy (per component), PR 2307 - Legacy, Due to Insurers - Legacy, Commission Receivable - Legacy, Unrealised Commission - Legacy, Deferred Output VAT - Legacy, Unapplied Collections - Legacy, Migration Clearing | Basic premium, DST, premium tax or VAT, LGT, FST, other charges | Account of D0-06 | EBIX and ISYS account codes separated by commas | Text
Allowed values | List Legacy control account: 8 values, see Reference lists | Free entry | A code of D0-06 Chart of accounts, column Account Code | Free entry | Free entry
What to enter | One row per account | Component the account holds | Account in the production chart | The legacy accounts it replaces (for the code map GL_ACCOUNT, R08) | End state after the run-off
Row | Legacy account * | Component | BIBS account code * | Legacy GL accounts | Remarks
Example – overwrite or delete | Migration Clearing |  | 1990.01 | 1210-01 | Nets to 0.00 after the opening
Note on B16: Legacy account One row per account Mandatory: Yes Format: Premium Receivable - Legacy (per component), PR 2307 - Legacy, Due to Insurers - Legacy, Commission Receivable - Legacy, Unrealised Commission - Legacy, Deferred Output VAT - Legacy, Unapplied Collections - Legacy, Migration Clearing Allowed values: List Legacy control account: 8 values, see Reference lists Example: Migration Clearing
Note on C16: Component Component the account holds Mandatory: Conditional: Premium Receivable - Legacy Format: Basic premium, DST, premium tax or VAT, LGT, FST, other charges Allowed values: Free entry
Note on D16: BIBS account code Account in the production chart Mandatory: Yes Format: Account of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 1990.01
Note on E16: Legacy GL accounts The legacy accounts it replaces (for the code map GL_ACCOUNT, R08) Mandatory: No Format: EBIX and ISYS account codes separated by commas Allowed values: Free entry Example: 1210-01
Note on F16: Remarks End state after the run-off Mandatory: No Format: Text Allowed values: Free entry Example: Nets to 0.00 after the opening

## D0-15 Approval limits
D0-15 Approval limits and matrices | [8 empty] | Step 32 of 51
← Back to Start here | Step 32 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [7 empty] | Ask a question →
Purpose | The approval levels by amount, sum insured or segment of the modules that approve by level
Provided by | Owners of the modules; Head, Comptrollership for the amounts
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Submitted Policies Setup, EB Setup, Compliance Setup (Configuration Versions) and Disbursement approver routing; the authorisation limit of a user is in UA-03
Source | BDOI approval matrix and signing authorities
Depends on | UA-02 Role-to-permission matrix → | UA-01 Users and roles load →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | No | No | Yes | Yes | No | No
Format | Submitted Policies, Employee Benefits, Sanction Screening, Disbursement | Text | Segment, benefit line or case type | PHP | PHP; blank = no limit | 1, 2, 3 | Group profile of UA-02 | User ID of UA-01 | Text
Allowed values | Submitted Policies, Employee Benefits, Sanction Screening, Disbursement (list Module of an approval matrix) | Free entry | Free entry | A number | A number | A whole number from 1 to 9 | A code of UA-02 Role-to-permission matrix, column Group profile code | A code of UA-01 Users and roles load, column User ID | Free entry
What to enter | Module of the approval | What is approved | Scope of the row | Lower bound (sum insured, premium or amount) | Upper bound | Order of the approval | Profile that approves | Only when one person approves | Title printed on the document
Row | Module * | Document or transaction * | Segment or case type | From amount | To amount | Approval level * | Approver role * | Named approver | Signatory title
Example – overwrite or delete | Submitted Policies | Terms of reference | CBG | 0 | 10000000 | 1 | SBM_APPROVER |  | Unit Head, Combank
Note on B16: Module Module of the approval Mandatory: Yes Format: Submitted Policies, Employee Benefits, Sanction Screening, Disbursement Allowed values: Submitted Policies, Employee Benefits, Sanction Screening, Disbursement (list Module of an approval matrix) Example: Submitted Policies
Note on C16: Document or transaction What is approved Mandatory: Yes Format: Text Allowed values: Free entry Example: Terms of reference
Note on D16: Segment or case type Scope of the row Mandatory: No Format: Segment, benefit line or case type Allowed values: Free entry Example: CBG
Note on E16: From amount Lower bound (sum insured, premium or amount) Mandatory: No Format: PHP Allowed values: A number Example: 0.00
Note on F16: To amount Upper bound Mandatory: No Format: PHP; blank = no limit Allowed values: A number Example: 10000000.00
Note on G16: Approval level Order of the approval Mandatory: Yes Format: 1, 2, 3 Allowed values: A whole number from 1 to 9 Example: 1
Note on H16: Approver role Profile that approves Mandatory: Yes Format: Group profile of UA-02 Allowed values: A code of UA-02 Role-to-permission matrix, column Group profile code Example: SBM_APPROVER
Note on I16: Named approver Only when one person approves Mandatory: No Format: User ID of UA-01 Allowed values: A code of UA-01 Users and roles load, column User ID
Note on J16: Signatory title Title printed on the document Mandatory: No Format: Text Allowed values: Free entry Example: Unit Head, Combank

## R07 Commission rates by insurer
R07 Commission rates by insurer and product | [5 empty] | Step 33 of 51
← Back to Start here | Step 33 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | One row per record of Commission rates by insurer and product as extracted from QPS, EBIX. Key insurer_code, risk_code, effective_from. Sent as the file R07_template.csv (CSV, header row as below) with its control file (row count, row count).
Provided by | Operations data steward (to name); approved by Head, Operations; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Migration Console: the file R07_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object R07; lands in: Commission rates of the product catalogue
Source | QPS, EBIX
Depends on | R04 Insurers → |  | R05 Product lines, cover types, products and risk codes →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | Mapped | Mapped | 0 to 100 | Valid date | No overlap for the same insurer and product
Mandatory | Yes | Yes | Yes | Yes | No
Format | Code, up to 30; As stored in legacy | Code, up to 20; As stored in legacy | Decimal, up to 9,4; Dot decimal | Date, up to 10; yyyy-MM-dd | Date, up to 10; yyyy-MM-dd
Allowed values | The legacy code; mapped by the code map INSURER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map PRODUCT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | A number | Free entry | Free entry
What to enter | Legacy insurer code | Legacy product / risk code | Commission rate in percent | Rate valid from | Rate valid to
Row | insurer_code * | risk_code * | rate_pct * | effective_from * | effective_to
Example – overwrite or delete | MAL | MC-PC-COMP | 20 | 2026-01-01
Note on B17: insurer_code Legacy insurer code Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map INSURER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: MAL
Note on C17: risk_code Legacy product / risk code Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map PRODUCT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: MC-PC-COMP
Note on D17: rate_pct Commission rate in percent Mandatory: Yes Format: Decimal, up to 9,4; Dot decimal Allowed values: A number Example: 20.0000
Note on E17: effective_from Rate valid from Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2026-01-01
Note on F17: effective_to Rate valid to Mandatory: No Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry

## TX-02 Tax forms
TX-02 Tax forms and filing calendar | [9 empty] | Step 34 of 51
← Back to Start here | Step 34 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [8 empty] | Ask a question →
Purpose | One row per tax return or remittance form BDOI files, with its frequency and due date, so that the tax calendar warns before each deadline and the return worksheets post to the right accounts. The forms BIBS knows are listed on the sheet D0-10 Tax checklist; BDOI confirms which apply to it as a broker.
Provided by | Head, Comptrollership (Tax)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Configuration screen: Finance › Tax & Statutory › Tax Codes & Forms (Forms panel), authorised by a second user
Source | BDOI tax calendar
Depends on | D0-06 Chart of accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | Yes
Format | Up to 20 characters | Text, up to 150 | Code of the list | Code of the list | Code of the list | Whole number | 1 to 31 (31 = month end) | Account of D0-06 | Account of D0-06 | dd-mmm-yyyy
Allowed values | Free entry, up to 20 characters | Free entry, up to 150 characters | BIR, LGU, BFP (list Tax authority) | MONTHLY, QUARTERLY, MONTHLY_EXCEPT_QUARTER_END, ANNUAL (list Filing frequency) | List Tax worksheet: 7 values, see Reference lists | A whole number from 0 to 12 | A whole number from 1 to 31 | A code of D0-06 Chart of accounts, column Account Code | A code of D0-06 Chart of accounts, column Account Code | A date, for example 15-Jan-2028
What to enter | BIR or local form number | Name of the return | Who the form is filed with | How often the form is filed | Computation worksheet behind the form (NONE: prepared outside BIBS, reminder only) | Months after the end of the period in which the form is due | Day of the month the form is due | Account the tax payable is posted to | Input VAT account credited against the output VAT (VAT return only) | First period the filing is tracked
Row | Form code * | Name * | Authority * | Frequency * | Worksheet * | Months after period end * | Due day * | Tax payable account | Credit account | Tracked from *
Example – overwrite or delete | 2550Q | Quarterly VAT return | BIR | QUARTERLY | VAT | 0 | 25 |  |  | 2028-01-01
Note on B16: Form code BIR or local form number Mandatory: Yes Format: Up to 20 characters Allowed values: Free entry, up to 20 characters Example: 2550Q
Note on C16: Name Name of the return Mandatory: Yes Format: Text, up to 150 Allowed values: Free entry, up to 150 characters Example: Quarterly VAT return
Note on D16: Authority Who the form is filed with Mandatory: Yes Format: Code of the list Allowed values: BIR, LGU, BFP (list Tax authority) Example: BIR
Note on E16: Frequency How often the form is filed Mandatory: Yes Format: Code of the list Allowed values: MONTHLY, QUARTERLY, MONTHLY_EXCEPT_QUARTER_END, ANNUAL (list Filing frequency) Example: QUARTERLY
Note on F16: Worksheet Computation worksheet behind the form (NONE: prepared outside BIBS, reminder only) Mandatory: Yes Format: Code of the list Allowed values: List Tax worksheet: 7 values, see Reference lists Example: VAT
Note on G16: Months after period end Months after the end of the period in which the form is due Mandatory: Yes Format: Whole number Allowed values: A whole number from 0 to 12 Example: 0
Note on H16: Due day Day of the month the form is due Mandatory: Yes Format: 1 to 31 (31 = month end) Allowed values: A whole number from 1 to 31 Example: 25
Note on I16: Tax payable account Account the tax payable is posted to Mandatory: No Format: Account of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code
Note on J16: Credit account Input VAT account credited against the output VAT (VAT return only) Mandatory: No Format: Account of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code
Note on K16: Tracked from First period the filing is tracked Mandatory: Yes Format: dd-mmm-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Jan-2028

## UA-03 Approval rules
UA-03 Approvers, approval rules and limits | [5 empty] | Step 35 of 51
← Back to Start here | Step 35 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | Who requests and who approves user access, the order of the approvers of group-profile requests, the second approvers, the implementers, and the authorisation limits of the users whose work other modules approve by amount
Provided by | Business Administration; BDOI Information Security for the second approval; Comptrollership for the authorisation limits
Due | 16-Jul-2027 – Values for UAT
How it is loaded | The users are given the Requestor, Approver, Second Approver and System Administrator profiles by requests (CI-01); the approvers are chosen on each request; UAM_ANY_APPROVER is set on System Parameters. The authorisation limit is set by an Enrol new user or Modify user request (field Authorisation Limit) decided by an approver; the bulk file has no limit column, so the limits are requested after the users are loaded
Source | BDOI's approval matrix (UQ01, UQ02)
Depends on | UA-01 Users and roles load →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Conditional: Approver | No | No
Format | Requestor, Approver, Second Approver, Group-profile requester, Implementer | User ID of CI-01 | Business unit | 1, 2, 3 | Y or N | Amount in PHP; blank = unlimited
Allowed values | Requestor, Approver, Second Approver, Group-profile requester, Implementer (list Role in user access) | A code of UA-01 Users and roles load, column User ID | Free entry | A whole number from 1 to 9 | Y or N | A number
What to enter | The user access role of the user | The user who holds the role | Unit the user requests or approves for | Usual order of the approvers of a group-profile request | Y sets UAM_ANY_APPROVER: any approver decides any request, not only the chosen one | Limit of the user's approvals by amount in the modules that use it (journals, payables)
Row | Role in user access * | User ID * | Unit * | Approver order for group profiles | Any approver may decide | Authorisation limit
Example – overwrite or delete | Approver | a013000205 | Combank Marketing | 1 | N | 500000
Note on B16: Role in user access The user access role of the user Mandatory: Yes Format: Requestor, Approver, Second Approver, Group-profile requester, Implementer Allowed values: Requestor, Approver, Second Approver, Group-profile requester, Implementer (list Role in user access) Example: Approver
Note on C16: User ID The user who holds the role Mandatory: Yes Format: User ID of CI-01 Allowed values: A code of UA-01 Users and roles load, column User ID Example: a013000205
Note on D16: Unit Unit the user requests or approves for Mandatory: Yes Format: Business unit Allowed values: Free entry Example: Combank Marketing
Note on E16: Approver order for group profiles Usual order of the approvers of a group-profile request Mandatory: Conditional: Approver Format: 1, 2, 3 Allowed values: A whole number from 1 to 9 Example: 1
Note on F16: Any approver may decide Y sets UAM_ANY_APPROVER: any approver decides any request, not only the chosen one Mandatory: No Format: Y or N Allowed values: Y or N Example: N
Note on G16: Authorisation limit Limit of the user's approvals by amount in the modules that use it (journals, payables) Mandatory: No Format: Amount in PHP; blank = unlimited Allowed values: A number Example: 500000.00

## PM-02 Coverages and rules
PM-02 Coverages, perils and field rules | [8 empty] | Step 36 of 51
← Back to Start here | Step 36 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [7 empty] | Ask a question →
Purpose | The coverage and peril level of each line, and the fields and documents each product needs on an account
Provided by | MBS
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Entered on Coverages & Clauses (SCR-PM-15) and on the rule tabs of Products (SCR-PM-11, SCR-PM-12) before UAT; not migrated
Source | MBS and TSU (product matrix, PQ02)
Depends on | PM-09 Lists of values and parameters → |  | PM-01 Product catalogue →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | Yes | Conditional: coverage | Conditional: list, range or format rules | Conditional: document rule | Yes
Format | COVERAGE, FIELD_RULE or DOCUMENT_RULE | Line or product the row applies to; * = every product | A-Z, 0-9 and _ (coverage); field key (rule) | Text | Coverage kind (Section, Coverage, Peril, Extension); check (Presence, List of values, Number range, Format) | Y or N | List code; minimum and maximum; pattern | List DOCUMENT_TYPE | Y or N
Allowed values | COVERAGE, FIELD_RULE, DOCUMENT_RULE (list Coverage and rule record) | Codes of PM-01 Product catalogue, column Risk code (one or more) | Free entry | Free entry | Free entry | Y or N | Free entry | List Document type: 61 values, see Reference lists | Y or N
What to enter | What the row defines | Scope of the row | Coverage code or the account field checked | Coverage name or field label | Coverage kind or rule check | A package needs at least one basic coverage | Parameters of the check | Document an account needs before submission | Required or optional
Row | Record * | Line code / Risk code * | Code or field key * | Name or label * | Kind or check * | Basic | Parameters | Document type | Mandatory *
Example – overwrite or delete | COVERAGE | MOTOR | OD_THEFT | Own damage and theft | Coverage | Y |  |  | Y
Note on B16: Record What the row defines Mandatory: Yes Format: COVERAGE, FIELD_RULE or DOCUMENT_RULE Allowed values: COVERAGE, FIELD_RULE, DOCUMENT_RULE (list Coverage and rule record) Example: COVERAGE
Note on C16: Line code / Risk code Scope of the row Mandatory: Yes Format: Line or product the row applies to; * = every product Allowed values: Codes of PM-01 Product catalogue, column Risk code (one or more) Example: MOTOR
Note on D16: Code or field key Coverage code or the account field checked Mandatory: Yes Format: A-Z, 0-9 and _ (coverage); field key (rule) Allowed values: Free entry Example: OD_THEFT
Note on E16: Name or label Coverage name or field label Mandatory: Yes Format: Text Allowed values: Free entry Example: Own damage and theft
Note on F16: Kind or check Coverage kind or rule check Mandatory: Yes Format: Coverage kind (Section, Coverage, Peril, Extension); check (Presence, List of values, Number range, Format) Allowed values: Free entry Example: Coverage
Note on G16: Basic A package needs at least one basic coverage Mandatory: Conditional: coverage Format: Y or N Allowed values: Y or N Example: Y
Note on H16: Parameters Parameters of the check Mandatory: Conditional: list, range or format rules Format: List code; minimum and maximum; pattern Allowed values: Free entry
Note on I16: Document type Document an account needs before submission Mandatory: Conditional: document rule Format: List DOCUMENT_TYPE Allowed values: List Document type: 61 values, see Reference lists
Note on J16: Mandatory Required or optional Mandatory: Yes Format: Y or N Allowed values: Y or N Example: Y

## PM-03 Clause library
PM-03 Clause library | [5 empty] | Step 37 of 51
← Back to Start here | Step 37 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | Warranties, clauses, exclusions and deductible wordings used in the insurer terms of package versions
Provided by | TSU (wordings); MBS (maintenance)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Entered on Coverages & Clauses › Clause Library (SCR-PM-15); not migrated
Source | Current package slips and insurer wordings
Depends on | PM-09 Lists of values and parameters → |  | PM-01 Product catalogue →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | Yes | Yes | Yes (from)
Format | A-Z, 0-9 and _ | WARRANTY, CLAUSE, EXCLUSION or DEDUCTIBLE_WORDING | Line code; blank = every line | Text | Full text | dd-MMM-yyyy
Allowed values | Free entry | WARRANTY, CLAUSE, EXCLUSION, DEDUCTIBLE_WORDING (list Clause kind) | A code of PM-01 Product catalogue, column Line code | Free entry | Free entry | Free entry
What to enter | Unique code | Code of the list CLAUSE_KIND | Lines the clause is offered for | Title shown in the pickers | Wording printed on the package documents | Validity of the wording
Row | Clause code * | Kind * | Line code | Title * | Wording * | Effective from / to *
Example – overwrite or delete | FLEET_REPAIR | CLAUSE | MOTOR | Accredited repair shops for fleets | Repairs are made at the accredited shops of the insurer... | 01-Jan-2027
Note on B16: Clause code Unique code Mandatory: Yes Format: A-Z, 0-9 and _ Allowed values: Free entry Example: FLEET_REPAIR
Note on C16: Kind Code of the list CLAUSE_KIND Mandatory: Yes Format: WARRANTY, CLAUSE, EXCLUSION or DEDUCTIBLE_WORDING Allowed values: WARRANTY, CLAUSE, EXCLUSION, DEDUCTIBLE_WORDING (list Clause kind) Example: CLAUSE
Note on D16: Line code Lines the clause is offered for Mandatory: No Format: Line code; blank = every line Allowed values: A code of PM-01 Product catalogue, column Line code Example: MOTOR
Note on E16: Title Title shown in the pickers Mandatory: Yes Format: Text Allowed values: Free entry Example: Accredited repair shops for fleets
Note on F16: Wording Wording printed on the package documents Mandatory: Yes Format: Full text Allowed values: Free entry Example: Repairs are made at the accredited shops of the insurer...
Note on G16: Effective from / to Validity of the wording Mandatory: Yes (from) Format: dd-MMM-yyyy Allowed values: Free entry Example: 01-Jan-2027

## C02 Client addresses and contac
C02 Client addresses and contacts | [12 empty] | Step 38 of 51
← Back to Start here | Step 38 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [11 empty] | Ask a question →
Purpose | One row per record of Client master (individual and corporate) as extracted from QPS, EBIX, CMS. Key legacy_client_no, record_type, seq_no. Sent as the file C02_template.csv (CSV, header row as below) with its control file (row count, row count).
Provided by | Marketing data steward (to name); approved by Product Owner, MBS; Heads, Retail and Corporate Marketing; extracted by BDOI IT
Due | M3 (29 Jan 2027); deltas daily from T-14 days
How it is loaded | Migration Console: the file C02_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object C01; lands in: Client master, registered as migrated clients
Source | QPS, EBIX, CMS
Depends on | C01 Client master →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | Exists in C01 of the same source | In the list | Unique per client and record type | Mandatory for ADDRESS | Mandatory for ADDRESS | - | - | 4 digits | Mandatory for CONTACT | - | Valid e-mail | PH mobile format | One primary ADDRESS per client
Mandatory | Yes | Yes | Yes | Conditional: Mandatory for ADDRESS | Conditional: Mandatory for ADDRESS | No | No | No | Conditional: Mandatory for CONTACT | No | No | No | Yes
Format | Code, up to 30; As stored in legacy | Code, up to 10; Upper case | Integer, up to 3; Digits | Code, up to 12; Upper case | Text, up to 300; Free text | Text, up to 80; Free text | Text, up to 80; Free text | Text, up to 10; 4 digits | Text, up to 200; Free text | Text, up to 60; Free text | Text, up to 120; name@domain | Text, up to 30; 09xxxxxxxxx | Flag, up to 1; Y or N
Allowed values | legacy_client_no of C01 | ADDRESS, CONTACT (list C02 record_type) | A whole number | HOME, BUSINESS, MAILING, BILLING (list C02 address_type) | Free entry, up to 300 characters | Free entry, up to 80 characters | Free entry, up to 80 characters | Free entry, up to 10 characters | Free entry, up to 200 characters | Free entry, up to 60 characters | Free entry, up to 120 characters | Free entry, up to 30 characters | Y or N
What to enter | Client number in the source system | Address or contact person | Sequence within the client and record type | Kind of address | Street address | City / municipality | Province | Postal code | Contact person (corporate clients) | Role of the contact | E-mail | Mobile number | Primary address or contact
Row | legacy_client_no * | record_type * | seq_no * | address_type | address_line | city | province | postal_code | contact_name | contact_role | email | mobile | primary_flag *
Example – overwrite or delete | Q-0012345 | ADDRESS | 1 | MAILING | 12 Rizal St., Brgy. San Antonio | Pasig | Metro Manila | 1600 | Jose Santos | HR Manager | jose.santos@acme.example | 09181234567 | Y
Note on B17: legacy_client_no Client number in the source system Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: legacy_client_no of C01 Example: Q-0012345
Note on C17: record_type Address or contact person Mandatory: Yes Format: Code, up to 10; Upper case Allowed values: ADDRESS, CONTACT (list C02 record_type) Example: ADDRESS
Note on D17: seq_no Sequence within the client and record type Mandatory: Yes Format: Integer, up to 3; Digits Allowed values: A whole number Example: 1
Note on E17: address_type Kind of address Mandatory: Conditional: Mandatory for ADDRESS Format: Code, up to 12; Upper case Allowed values: HOME, BUSINESS, MAILING, BILLING (list C02 address_type) Example: MAILING
Note on F17: address_line Street address Mandatory: Conditional: Mandatory for ADDRESS Format: Text, up to 300; Free text Allowed values: Free entry, up to 300 characters Example: 12 Rizal St., Brgy. San Antonio
Note on G17: city City / municipality Mandatory: No Format: Text, up to 80; Free text Allowed values: Free entry, up to 80 characters Example: Pasig
Note on H17: province Province Mandatory: No Format: Text, up to 80; Free text Allowed values: Free entry, up to 80 characters Example: Metro Manila
Note on I17: postal_code Postal code Mandatory: No Format: Text, up to 10; 4 digits Allowed values: Free entry, up to 10 characters Example: 1600
Note on J17: contact_name Contact person (corporate clients) Mandatory: Conditional: Mandatory for CONTACT Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Jose Santos
Note on K17: contact_role Role of the contact Mandatory: No Format: Text, up to 60; Free text Allowed values: Free entry, up to 60 characters Example: HR Manager
Note on L17: email E-mail Mandatory: No Format: Text, up to 120; name@domain Allowed values: Free entry, up to 120 characters Example: jose.santos@acme.example
Note on M17: mobile Mobile number Mandatory: No Format: Text, up to 30; 09xxxxxxxxx Allowed values: Free entry, up to 30 characters Example: 09181234567
Note on N17: primary_flag Primary address or contact Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y

## C03 Client payout accounts
C03 Client payout accounts | [5 empty] | Step 39 of 51
← Back to Start here | Step 39 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | One row per record of Client payout accounts (for refunds) as extracted from EBIX. Key legacy_client_no, account_no. Sent as the file C03_template.csv (CSV, header row as below) with its control file (row count, row count).
Provided by | Disbursement data steward (to name); approved by Product Owner, Comptrollership - Disbursement; extracted by BDOI IT
Due | M3 (29 Jan 2027)
How it is loaded | Migration Console: the file C03_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object C03; lands in: Client payout accounts
Source | EBIX
Depends on | C01 Client master →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | Client loaded | In the list | Not blank | Mandatory for CTA; mapped | Mandatory for CTA | Y or N
Mandatory | Yes | Yes | Yes | Conditional: Mandatory for CTA; mapped | Conditional: Mandatory for CTA | Yes
Format | Code, up to 30; As stored in legacy | Code, up to 10; Upper case | Text, up to 250; Free text | Code, up to 30; As stored in legacy | Text, up to 40; Digits | Flag, up to 1; Y or N
Allowed values | legacy_client_no of C01 | CTA, CHECK (list C03 mode) | Free entry, up to 250 characters | The legacy code; mapped by the code map BANK (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | Free entry, up to 40 characters | Y or N
What to enter | Client number in the source system | Payout mode | Name on the account or check | Bank of the account | Account number | Account in use
Row | legacy_client_no * | mode * | payee_name * | bank_code | account_no | active_flag *
Example – overwrite or delete | E-0098765 | CTA | Ana C. Reyes | BDO | 001234567890 | Y
Note on B17: legacy_client_no Client number in the source system Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: legacy_client_no of C01 Example: E-0098765
Note on C17: mode Payout mode Mandatory: Yes Format: Code, up to 10; Upper case Allowed values: CTA, CHECK (list C03 mode) Example: CTA
Note on D17: payee_name Name on the account or check Mandatory: Yes Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Ana C. Reyes
Note on E17: bank_code Bank of the account Mandatory: Conditional: Mandatory for CTA; mapped Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map BANK (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: BDO
Note on F17: account_no Account number Mandatory: Conditional: Mandatory for CTA Format: Text, up to 40; Digits Allowed values: Free entry, up to 40 characters Example: 001234567890
Note on G17: active_flag Account in use Mandatory: Yes Format: Flag, up to 1; Y or N Allowed values: Y or N Example: Y

## D0-12 Check books
D0-12 Check books | [5 empty] | Step 40 of 51
← Back to Start here | Step 40 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The check books in stock per bank account at go-live
Provided by | Treasury; Product Owner, Comptrollership - Disbursement
Due | 1-Nov-2027 – Production values before the dress rehearsal
How it is loaded | Bank Accounts and Checks (Disbursement)
Source | Check book register of Treasury
Depends on | D0-11 Company bank accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | Yes
Format | Code of D0-11 | Digits | Digits | Digits | dd-MMM-yyyy
Allowed values | A code of D0-11 Company bank accounts, column Bank account code | Free entry | Free entry | Free entry | A date, for example 15-Jan-2028
What to enter | Account of the check book | First number of the book | Last number of the book | Next number to issue at go-live | Date the book was received
Row | Bank account code * | First check number * | Last check number * | Next check number * | Received on *
Example – overwrite or delete | BDO-CA-001 | 0001001 | 0001100 | 0001001 | 2027-12-01
Note on B16: Bank account code Account of the check book Mandatory: Yes Format: Code of D0-11 Allowed values: A code of D0-11 Company bank accounts, column Bank account code Example: BDO-CA-001
Note on C16: First check number First number of the book Mandatory: Yes Format: Digits Allowed values: Free entry Example: 0001001
Note on D16: Last check number Last number of the book Mandatory: Yes Format: Digits Allowed values: Free entry Example: 0001100
Note on E16: Next check number Next number to issue at go-live Mandatory: Yes Format: Digits Allowed values: Free entry Example: 0001001
Note on F16: Received on Date the book was received Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Dec-2027

## D0-13 Petty cash funds
D0-13 Petty cash funds | [7 empty] | Step 41 of 51
← Back to Start here | Step 41 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | The petty cash funds of the branches
Provided by | Head, Comptrollership
Due | 1-Nov-2027 – Production values before the dress rehearsal
How it is loaded | Petty Cash (Payables & Cash)
Source | Petty cash register
Depends on | D0-02 Branches → |  | D0-05 Employees → | D0-06 Chart of accounts → |  | D0-11 Company bank accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Format | Code of D0-02 | Up to 20 capitals | Text | Employee of D0-05 | Account of D0-06 | Code of D0-11 | ISO 4217 | Amount
Allowed values | A code of D0-02 Branches, column Branch code | Free entry, up to 20 characters | Free entry | A code of D0-05 Employees, column Employee number | A code of D0-06 Chart of accounts, column Account Code | A code of D0-11 Company bank accounts, column Bank account code | Free entry, up to 3 characters | A number
What to enter | Branch of the fund | Code of the fund | Name of the fund | Custodian of the fund | Petty cash account | Account that replenishes the fund | Currency of the fund | Amount of the fund
Row | Branch code * | Fund code * | Name * | Custodian * | GL account * | Replenishment bank account * | Currency * | Imprest amount *
Example – overwrite or delete | HO | PCF-HO | Head Office petty cash | 1203344 | 1101.01 | BDO-CA-001 | PHP | 20000
Note on B16: Branch code Branch of the fund Mandatory: Yes Format: Code of D0-02 Allowed values: A code of D0-02 Branches, column Branch code Example: HO
Note on C16: Fund code Code of the fund Mandatory: Yes Format: Up to 20 capitals Allowed values: Free entry, up to 20 characters Example: PCF-HO
Note on D16: Name Name of the fund Mandatory: Yes Format: Text Allowed values: Free entry Example: Head Office petty cash
Note on E16: Custodian Custodian of the fund Mandatory: Yes Format: Employee of D0-05 Allowed values: A code of D0-05 Employees, column Employee number Example: 1203344
Note on F16: GL account Petty cash account Mandatory: Yes Format: Account of D0-06 Allowed values: A code of D0-06 Chart of accounts, column Account Code Example: 1101.01
Note on G16: Replenishment bank account Account that replenishes the fund Mandatory: Yes Format: Code of D0-11 Allowed values: A code of D0-11 Company bank accounts, column Bank account code Example: BDO-CA-001
Note on H16: Currency Currency of the fund Mandatory: Yes Format: ISO 4217 Allowed values: Free entry, up to 3 characters Example: PHP
Note on I16: Imprest amount Amount of the fund Mandatory: Yes Format: Amount Allowed values: A number Example: 20000.00

## D0-14 Statement layouts
D0-14 Bank statement layouts | [9 empty] | Step 42 of 51
← Back to Start here | Step 42 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [8 empty] | Ask a question →
Purpose | The columns of the statement file of each bank account
Provided by | Head, Comptrollership; Treasury
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Bank Statement Layouts (Setup & Administration)
Source | Statement files of the banks
Depends on | D0-11 Company bank accounts →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Yes | No | Conditional: separate columns | Conditional: separate columns | Conditional: one signed column | No | Yes
Format | Code of D0-11 | Text | Column header or number | Column header or number | Column header or number | Column header or number | Column header or number | Column header or number | Column header or number | For example dd/MM/yyyy
Allowed values | A code of D0-11 Company bank accounts, column Bank account code | Free entry | Free entry | Free entry | Free entry | Free entry | Free entry | Free entry | Free entry | Free entry
What to enter | Account of the statement | Name of the layout | Column of the transaction date | Column of the description | Column of the reference | Column of the debits | Column of the credits | Column of a signed amount | Column of the running balance | Format of the dates in the file
Row | Bank account code * | Layout name * | Date column * | Description column * | Reference column | Debit column | Credit column | Amount column | Balance column | Date format *
Example – overwrite or delete | BDO-CA-001 | BDO CSV statement | Posting Date | Description | Reference No. | Debit | Credit |  | Balance | MM/dd/yyyy
Note on B16: Bank account code Account of the statement Mandatory: Yes Format: Code of D0-11 Allowed values: A code of D0-11 Company bank accounts, column Bank account code Example: BDO-CA-001
Note on C16: Layout name Name of the layout Mandatory: Yes Format: Text Allowed values: Free entry Example: BDO CSV statement
Note on D16: Date column Column of the transaction date Mandatory: Yes Format: Column header or number Allowed values: Free entry Example: Posting Date
Note on E16: Description column Column of the description Mandatory: Yes Format: Column header or number Allowed values: Free entry Example: Description
Note on F16: Reference column Column of the reference Mandatory: No Format: Column header or number Allowed values: Free entry Example: Reference No.
Note on G16: Debit column Column of the debits Mandatory: Conditional: separate columns Format: Column header or number Allowed values: Free entry Example: Debit
Note on H16: Credit column Column of the credits Mandatory: Conditional: separate columns Format: Column header or number Allowed values: Free entry Example: Credit
Note on I16: Amount column Column of a signed amount Mandatory: Conditional: one signed column Format: Column header or number Allowed values: Free entry
Note on J16: Balance column Column of the running balance Mandatory: No Format: Column header or number Allowed values: Free entry Example: Balance
Note on K16: Date format Format of the dates in the file Mandatory: Yes Format: For example dd/MM/yyyy Allowed values: Free entry Example: MM/dd/yyyy

## G01 GL opening trial balance
G01 GL opening trial balance | [10 empty] | Step 43 of 51
← Back to Start here | Step 43 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [9 empty] | Ask a question →
Purpose | One row per record of GL trial balance per account, branch and currency (provisional opening; legacy TB at each true-up) as extracted from EBIX GL, ISYS GL. Key tb_version, branch_code, currency, legacy_account_code, cost_center. Sent as the file G01_template.csv (CSV, header row as below) with its control file (row count, row count; amount totals per currency: debit_fc, credit_fc, debit_php, credit_php).
Provided by | Comptrollership data steward (to name); approved by Head, Comptrollership; extracted by BDOI IT
Due | M3 (29 Jan 2027); final at T-2; at each true-up
How it is loaded | Migration Console: the file G01_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object G01; lands in: General ledger journals of type OPENING (value date 1-Jan-2028); at a true-up, reconciliation input only
Source | EBIX GL, ISYS GL
Depends on | R08 Chart of accounts mapping → |  | D0-02 Branches →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | In the list; one version per file | One date in the file | Mapped | Valid code | Mapped | Mapped | 0 or more; debit or credit, not both | 0 or more | 0 or more | 0 or more | Mandatory when currency is not PHP
Mandatory | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Conditional: Mandatory when currency is not PHP
Format | Code, up to 12; Upper case | Date, up to 10; yyyy-MM-dd | Code, up to 20; As stored in legacy | Code, up to 3; Upper case | Code, up to 30; As stored in legacy | Code, up to 20; As stored in legacy | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Amount, up to 19,2; Dot decimal, 2 decimals | Decimal, up to 12,6; Dot decimal
Allowed values | PROVISIONAL, TU1, TU2, TU3, FINAL (list G01 tb_version) | Free entry | The legacy code; mapped by the code map BRANCH (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | ISO 4217 | The legacy code; mapped by the code map GL_ACCOUNT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | The legacy code; mapped by the code map COST_CENTER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) | A number | A number | A number | A number | A number
What to enter | Version of the trial balance - PROVISIONAL at cut-over (preliminary December TB), then TU1, TU2... and FINAL (audited) at the true-ups | Trial balance date - 31-Dec-2027 for every version; the version says which adjustments it includes | Branch | Account currency | Legacy account | Cost centre | Debit balance in the account currency | Credit balance in the account currency | Debit balance in PHP | Credit balance in PHP | Rate used for the PHP amount
Row | tb_version * | as_of_date * | branch_code * | currency * | legacy_account_code * | cost_center | debit_fc * | credit_fc * | debit_php * | credit_php * | fx_rate
Example – overwrite or delete | PROVISIONAL | 2027-12-31 | MKT01 | USD | 1101-02 | 4100 | 12500 | 0 | 701562.5 | 0 | 56.125
Note on B17: tb_version Version of the trial balance - PROVISIONAL at cut-over (preliminary December TB), then TU1, TU2... and FINAL (audited) at the true-ups Mandatory: Yes Format: Code, up to 12; Upper case Allowed values: PROVISIONAL, TU1, TU2, TU3, FINAL (list G01 tb_version) Example: PROVISIONAL
Note on C17: as_of_date Trial balance date - 31-Dec-2027 for every version; the version says which adjustments it includes Mandatory: Yes Format: Date, up to 10; yyyy-MM-dd Allowed values: Free entry Example: 2027-12-31
Note on D17: branch_code Branch Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map BRANCH (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: MKT01
Note on E17: currency Account currency Mandatory: Yes Format: Code, up to 3; Upper case Allowed values: ISO 4217 Example: USD
Note on F17: legacy_account_code Legacy account Mandatory: Yes Format: Code, up to 30; As stored in legacy Allowed values: The legacy code; mapped by the code map GL_ACCOUNT (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: 1101-02
Note on G17: cost_center Cost centre Mandatory: No Format: Code, up to 20; As stored in legacy Allowed values: The legacy code; mapped by the code map COST_CENTER (Code Maps screen of the Data Migration Console; maps prepared in the Migration Workbook of BRD-13) Example: 4100
Note on H17: debit_fc Debit balance in the account currency Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 12500.00
Note on I17: credit_fc Credit balance in the account currency Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 0.00
Note on J17: debit_php Debit balance in PHP Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 701562.50
Note on K17: credit_php Credit balance in PHP Mandatory: Yes Format: Amount, up to 19,2; Dot decimal, 2 decimals Allowed values: A number Example: 0.00
Note on L17: fx_rate Rate used for the PHP amount Mandatory: Conditional: Mandatory when currency is not PHP Format: Decimal, up to 12,6; Dot decimal Allowed values: A number Example: 56.125000

## PM-04 Rate tables
PM-04 Rate tables | [6 empty] | Step 44 of 51
← Back to Start here | Step 44 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [5 empty] | Ask a question →
Purpose | Statutory charges and rating factors, the short-period table and the motor BI / PD limit premiums
Provided by | Product Owner, MBS; Comptrollership (taxes)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Entered on Rates & Taxes (SCR-PM-19), pending authorisation; not migrated (effective-dated from go-live)
Source | BIR and LGU rates; current rating tables
Depends on | PM-01 Product catalogue →
Checklist | One row per premium charge is written below the header (DST, premium tax, VAT on premium, fire service tax, VAT on commission and the motor factors); complete the rate per line and the dates, and add a row per line where the rate differs. The rules BIBS applies are on the sheet PM-04 Charges checklist
LGT | The local government tax is not kept here: it is the rate of each insurer branch, column lgt_rate of template R04B
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Conditional: TAX | No | Conditional: TAX, SHORT_PERIOD | Conditional: SHORT_PERIOD | Conditional: MOTOR_LIMIT | Yes (from)
Format | TAX, SHORT_PERIOD or MOTOR_LIMIT | DST, premium tax, VAT, fire service tax, motor factors | Line; blank = every line | Up to four decimals, 0 to 100 | 1 to 12 | BI or PD; amounts in PHP | dd-MMM-yyyy
Allowed values | TAX, SHORT_PERIOD, MOTOR_LIMIT (list Rate table) | List Premium charge or rating factor (BIBS): 7 values, see Reference lists | A code of PM-01 Product catalogue, column Line code | A number from 0 to 100 | A whole number from 1 to 12 | Free entry | Free entry
What to enter | Table of the row | Charge or factor | Line the rate applies to | Rate, or % of the annual premium | Months covered, up to | Limit and its premium | Validity of the row
Row | Table * | Rate | Line code | Rate % | Months covered | Coverage / Limit / Premium | Effective from / to *
Example – overwrite or delete | TAX | DST |  | 12.5 | 6 | BI; 100000.00; 350.00 | 01-Jan-2028
| TAX | DST
| TAX | PREMIUM_TAX
| TAX | VAT_PREMIUM
| TAX | FIRE_SERVICE_TAX
| TAX | VAT_COMMISSION
| TAX | MOTOR_OD_ANNUAL
| TAX | MOTOR_OD_MULTI_YEAR
Note on B18: Table Table of the row Mandatory: Yes Format: TAX, SHORT_PERIOD or MOTOR_LIMIT Allowed values: TAX, SHORT_PERIOD, MOTOR_LIMIT (list Rate table) Example: TAX
Note on C18: Rate Charge or factor Mandatory: Conditional: TAX Format: DST, premium tax, VAT, fire service tax, motor factors Allowed values: List Premium charge or rating factor (BIBS): 7 values, see Reference lists Example: DST
Note on D18: Line code Line the rate applies to Mandatory: No Format: Line; blank = every line Allowed values: A code of PM-01 Product catalogue, column Line code
Note on E18: Rate % Rate, or % of the annual premium Mandatory: Conditional: TAX, SHORT_PERIOD Format: Up to four decimals, 0 to 100 Allowed values: A number from 0 to 100 Example: 12.5000
Note on F18: Months covered Months covered, up to Mandatory: Conditional: SHORT_PERIOD Format: 1 to 12 Allowed values: A whole number from 1 to 12 Example: 6
Note on G18: Coverage / Limit / Premium Limit and its premium Mandatory: Conditional: MOTOR_LIMIT Format: BI or PD; amounts in PHP Allowed values: Free entry Example: BI; 100000.00; 350.00
Note on H18: Effective from / to Validity of the row Mandatory: Yes (from) Format: dd-MMM-yyyy Allowed values: Free entry Example: 01-Jan-2028

## PM-04 Charges checklist
PM-04 Charges checklist: premium charges billed to clients
← Back to Start here | One row per charge: how BIBS computes it, where its rate is given and what BDOI confirms (rates per line in PM-04, LGT per insurer branch in R04B)
Charge | What BIBS does | Where it is set up | What BDOI provides or confirms | Held by BIBS | Question | Rule confirmed | BDOI comments | Status
Documentary stamp tax (DST) | Rate % of the net (basic) premium of the line. The tax is rounded to centavos and then up to the next half peso: .01 to .49 becomes .50, .51 to .99 the next peso, .00 and .50 stay; a refund is rounded the same way. | PM-04, Rate DST (per line, or blank line = every line) | The DST rate per line, confirmation of the net premium as the basis and of the half-peso rounding, and the lines or clients exempt from DST | Yes | TX-Q01 |  |  | Not started
Premium tax | Rate % of the net premium of the line, rounded to centavos. BIBS applies it per product line, not by the VAT or non-VAT registration of the insurer. | PM-04, Rate PREMIUM_TAX (per line) | The lines on which premium tax is billed instead of VAT, and the rate | Yes | TX-Q02 |  |  | Not started
VAT on premium | Rate % of the net premium of the line, rounded to centavos. The charge follows the line; a zero-rated or exempt client is classified on the VAT worksheet by its VAT treatment (TX-01). | PM-04, Rate VAT_PREMIUM (per line) | The VAT rate per line, the lines that are VAT-exempt or zero-rated, and whether the insurer's VAT registration must decide VAT or premium tax | Yes | TX-Q02 |  |  | Not started
Fire service tax (FST) | Rate % of the net premium of the lines it is set for, rounded to centavos. | PM-04, Rate FIRE_SERVICE_TAX (fire lines) | The fire lines that carry FST, the rate and the basis | Yes | TX-Q01 |  |  | Not started
Local government tax (LGT) | Rate % of the net premium at the rate of the insurer branch that places the policy, rounded to centavos. BIBS keeps no rate per local government unit. | R04B, column lgt_rate of each insurer branch | The LGT rate of each insurer branch and the ordinance basis of the LGU behind it | Yes | TX-Q03 |  |  | Not started
VAT on BDOI's commission | Rate % of the commission (commission rate x net premium), rounded to centavos. | PM-04, Rate VAT_COMMISSION | The VAT rate on commission and the cases where it is zero-rated or exempt | Yes | TX-Q05 |  |  | Not started
Motor own damage / theft coverage factors | Percent of the sum insured taken as the own damage / theft coverage: one factor for annual cover, one for multi-year cover. | PM-04, Rates MOTOR_OD_ANNUAL and MOTOR_OD_MULTI_YEAR | The two factors | Yes | TX-Q01 |  |  | Not started
Short-period table and motor BI / PD limit premiums | Short period: percent of the annual premium by months covered; motor BI / PD: premium per limit. | PM-04, Tables SHORT_PERIOD and MOTOR_LIMIT | The short-period table and the limit premiums | Yes | TX-Q01 |  |  | Not started
Order | basis | minimum and rounding of the charges | Every charge is computed on the net premium after the minimum premium, independently of the others (no charge on another charge); gross premium = net premium + all charges; no minimum amount per charge; every amount rounded to centavos half-up except DST (half peso). | Fixed in BIBS (no column) | Confirmation of the rules, or the basis, order, minimum or rounding BDOI applies |  |  | Not started
CTPL COCAF / LTO authentication fee | No field: BIBS has no charge other than the taxes above. | Not held (sheet Gaps) | Whether BIBS must bill it, its amount and who receives it | No | TX-Q04 |  |  | Not started
Notarial fee | No field. | Not held (sheet Gaps) | Whether BIBS must bill it and its amount | No | TX-Q04 |  |  | Not started
Policy or documentation fee | No field. | Not held (sheet Gaps) | Whether BIBS must bill it and its amount | No | TX-Q04 |  |  | Not started
Any other charge BDOI bills | No field. | Not held (sheet Gaps) | The charge, its basis and amount | No | TX-Q04 |  |  | Not started
Note on A4: Charge: Item
Note on B4: What BIBS does: The rule of the platform
Note on C4: Where it is set up: Template, column or list
Note on D4: What BDOI provides or confirms: Input asked from BDOI
Note on E4: Held by BIBS: Yes, or No (sheet Gaps)
Note on F4: Question: Ref of the question in the BDOI Requirements and Inputs workbook
Note on G4: Rule confirmed: Agree, or Change (describe in BDOI comments)
Note on H4: BDOI comments: Decision, value or comment of the owner
Note on I4: Status: Status of the item

## PM-10 Incentive criteria
PM-10 Incentive criteria | [5 empty] | Step 45 of 51
← Back to Start here | Step 45 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The incentive criteria (for example CPC2) with their value, the products matrix and the effective dates
Provided by | Incentive Maintenance user (MBS); Comptrollership (CPC2 definition, PQ04)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Entered on Incentive Criteria (SCR-PM-16), pending authorisation; the copied booking rules are reviewed there
Source | Current incentive programmes; the booking incentive rules copied into the catalogue
Depends on | PM-09 Lists of values and parameters → | PM-01 Product catalogue →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes (basis) | No | Yes (one product) | Yes (from)
Format | A-Z, 0-9, _ and -; text | List INCENTIVE_TYPE | Rate (%), Fixed amount or Rule; number | Parameter and value pairs separated by semicolons | Active risk codes; segment or blank | dd-MMM-yyyy
Allowed values | Free entry | OTHERS, MIGRATED (list Incentive type) | Free entry | Free entry | Codes of PM-01 Product catalogue, column Risk code (one or more) | Free entry
What to enter | Criterion | Type of criterion | Value of the criterion | Parameters of a rule criterion, as agreed with Comptrollership | Products and segments the criterion applies to | Validity; no overlap with another row of the code
Row | Code / Name * | Incentive type * | Value basis / Value * | Rule parameters | Products matrix: risk code / segment * | Effective from / to *
Example – overwrite or delete | CPC2; CPC2 campaign 2028 | CAMPAIGN | Rate (%); 1.00 | Minimum premium 5000 | MTR30; COMBANK | 01-Jan-2028
Note on B16: Code / Name Criterion Mandatory: Yes Format: A-Z, 0-9, _ and -; text Allowed values: Free entry Example: CPC2; CPC2 campaign 2028
Note on C16: Incentive type Type of criterion Mandatory: Yes Format: List INCENTIVE_TYPE Allowed values: OTHERS, MIGRATED (list Incentive type) Example: CAMPAIGN
Note on D16: Value basis / Value Value of the criterion Mandatory: Yes (basis) Format: Rate (%), Fixed amount or Rule; number Allowed values: Free entry Example: Rate (%); 1.00
Note on E16: Rule parameters Parameters of a rule criterion, as agreed with Comptrollership Mandatory: No Format: Parameter and value pairs separated by semicolons Allowed values: Free entry Example: Minimum premium 5000
Note on F16: Products matrix: risk code / segment Products and segments the criterion applies to Mandatory: Yes (one product) Format: Active risk codes; segment or blank Allowed values: Codes of PM-01 Product catalogue, column Risk code (one or more) Example: MTR30; COMBANK
Note on G16: Effective from / to Validity; no overlap with another row of the code Mandatory: Yes (from) Format: dd-MMM-yyyy Allowed values: Free entry Example: 01-Jan-2028

## TX-01 Party tax profiles
TX-01 Party tax profiles (clients, insurers, payees) | [11 empty] | Step 46 of 51
← Back to Start here | Step 46 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [10 empty] | Ask a question →
Purpose | One row per client, insurer, intermediary or payee whose tax details BIBS uses on the BIR forms, the 2307 certificates, the alphalists and the VAT classification of sales: the registered TIN and branch code, the payee class, the registered name and address, the VAT treatment and the default ATC withheld. The party code is the code of the client (C01 or the client upload), insurer (R04), business partner (MD-01) or payee (UP-02).
Provided by | Head, Comptrollership (Tax)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Configuration screen: Finance › Tax & Statutory › Party Tax Profiles, authorised by a second user
Source | BIR registrations (COR) of the parties; client KYC files
Depends on | D0-10 Tax codes → |  | R04 Insurers → |  | C01 Client master → | MD-01 Business partners (reinsurers, intermediaries, suppliers) → |  | UP-02 Payees →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | No | Yes | Yes | Conditional: individuals | Conditional: individuals | No | No | No | No | No
Format | Text, up to 30 | Digits and dashes, up to 20 | Up to 5 digits | Code of the list | Text, up to 200 | Text, up to 60 | Text, up to 60 | Text, up to 60 | Text, up to 300 | Up to 10 characters | Code of the list | Tax code of D0-10
Allowed values | Free entry, up to 30 characters | Free entry, up to 20 characters | Free entry, up to 5 characters | INDIVIDUAL, CORPORATE (list Payee class (BIR)) | Free entry, up to 200 characters | Free entry, up to 60 characters | Free entry, up to 60 characters | Free entry, up to 60 characters | Free entry, up to 300 characters | Free entry, up to 10 characters | REGULAR, ZERO_RATED, EXEMPT (list VAT treatment) | Free entry, up to 20 characters
What to enter | Code of the client, insurer, partner or payee | Taxpayer identification number as registered | TIN branch code (000 or 00000 for the head office) | Individual or corporate (decides the WI or WC ATC and the alphalist name) | Name as registered with the BIR | Last name of an individual | First name of an individual | Middle name of an individual | Address as registered with the BIR | ZIP code of the registered address | How a premium without VAT is classified on the VAT return | Withholding tax code applied by default to payments to or from the party
Row | Party code * | TIN * | Branch code | Payee class * | Registered name * | Last name | First name | Middle name | Registered address | ZIP code | VAT treatment | Default ATC
Example – overwrite or delete | C-000101 | 123-456-789 | 00000 | CORPORATE | Juan Dela Cruz Trading Corp. |  |  |  | Makati City | 1226 | REGULAR
Note on B16: Party code Code of the client, insurer, partner or payee Mandatory: Yes Format: Text, up to 30 Allowed values: Free entry, up to 30 characters Example: C-000101
Note on C16: TIN Taxpayer identification number as registered Mandatory: Yes Format: Digits and dashes, up to 20 Allowed values: Free entry, up to 20 characters Example: 123-456-789
Note on D16: Branch code TIN branch code (000 or 00000 for the head office) Mandatory: No Format: Up to 5 digits Allowed values: Free entry, up to 5 characters Example: 00000
Note on E16: Payee class Individual or corporate (decides the WI or WC ATC and the alphalist name) Mandatory: Yes Format: Code of the list Allowed values: INDIVIDUAL, CORPORATE (list Payee class (BIR)) Example: CORPORATE
Note on F16: Registered name Name as registered with the BIR Mandatory: Yes Format: Text, up to 200 Allowed values: Free entry, up to 200 characters Example: Juan Dela Cruz Trading Corp.
Note on G16: Last name Last name of an individual Mandatory: Conditional: individuals Format: Text, up to 60 Allowed values: Free entry, up to 60 characters
Note on H16: First name First name of an individual Mandatory: Conditional: individuals Format: Text, up to 60 Allowed values: Free entry, up to 60 characters
Note on I16: Middle name Middle name of an individual Mandatory: No Format: Text, up to 60 Allowed values: Free entry, up to 60 characters
Note on J16: Registered address Address as registered with the BIR Mandatory: No Format: Text, up to 300 Allowed values: Free entry, up to 300 characters Example: Makati City
Note on K16: ZIP code ZIP code of the registered address Mandatory: No Format: Up to 10 characters Allowed values: Free entry, up to 10 characters Example: 1226
Note on L16: VAT treatment How a premium without VAT is classified on the VAT return Mandatory: No Format: Code of the list Allowed values: REGULAR, ZERO_RATED, EXEMPT (list VAT treatment) Example: REGULAR
Note on M16: Default ATC Withholding tax code applied by default to payments to or from the party Mandatory: No Format: Tax code of D0-10 Allowed values: Free entry, up to 20 characters

## PM-06 Packages
PM-06 Packages in force at go-live | [8 empty] | Step 47 of 51
← Back to Start here | Step 47 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [7 empty] | Ask a question →
Purpose | For every package sold at go-live: its terms as they will be set up in BIBS through a package request (TSU) and a package version (MBS): rate scheme, dates, coverages, panel insurers and their terms
Provided by | TSU (prepares); Product Owner, MBS (approves)
Due | 1-Nov-2027 – Production values before the dress rehearsal
How it is loaded | Not migrated: TSU raises a package request per package (type New package, or Update for an existing risk code) and MBS sets up and validates the version before the map freeze; the Package Request Form accepts the same fields
Source | Signed package slips and ManCom sign-offs in force
Depends on | PM-01 Product catalogue → |  | PM-02 Coverages, perils and field rules → | R04 Insurers → | PM-03 Clause library →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes (name, scope) | Yes (effective from, package end) | Yes (minimum, commission; rate or insurer rates) | Yes | Yes (one basic coverage) | Yes (the panel) | Yes (every insurer and included coverage) | Yes
Format | Code of CI-01 | Text; Generic or Client-specific; client code | dd-MMM-yyyy | Percentages and PHP amounts | Text | Codes of CI-02; Y or N; PHP | Codes of CI-05; Panel, Lead or Participant; shares total 100 | Codes of CI-03 separated by commas | Reference; the signed slip file
Allowed values | A code of PM-01 Product catalogue, column Risk code | Free entry | Free entry | Free entry | Free entry | Codes of PM-02 Coverages, perils and field rules, column Code or field key (one or more) | Codes of R04 Insurers, column insurer_code (one or more) | Codes of PM-03 Clause library, column Clause code (one or more) | Free entry
What to enter | Package product | As on the Package Request Form | Dates of the version | Rate scheme of the version | How the premium is computed | Coverages of the version | Panel insurers | Terms per insurer and coverage | Evidence kept on the request
Row | Risk code * | Package name / Scope / Client code * | Effective from / Package start / Package end / Anniversary * | Package rate % / Minimum premium / Commission % / Package TSI limit * | Computation basis * | Coverage code / Included / Optional / Limit / Deductible * | Insurer code / Role / Share % / Rate % / Minimum premium * | Insurer terms: insurer / coverage / limit / deductible / clauses * | ManCom sign-off reference / Signed package slip *
Example – overwrite or delete | MTR30 | Motor Fleet Plus; Generic | 01-Jan-2028; 01-Jan-2028; 31-Dec-2028; - | 1.2000; 5000.00; 15; 5000000.00 | Comprehensive rate on the vehicle value | OD_THEFT; Y; N; -; 2000.00 | INS-MGIC; Panel; -; 1.2000; - | INS-MGIC; OD_THEFT; -; 2000.00; FLEET_REPAIR | MC-2026-017
Note on B16: Risk code Package product Mandatory: Yes Format: Code of CI-01 Allowed values: A code of PM-01 Product catalogue, column Risk code Example: MTR30
Note on C16: Package name / Scope / Client code As on the Package Request Form Mandatory: Yes (name, scope) Format: Text; Generic or Client-specific; client code Allowed values: Free entry Example: Motor Fleet Plus; Generic
Note on D16: Effective from / Package start / Package end / Anniversary Dates of the version Mandatory: Yes (effective from, package end) Format: dd-MMM-yyyy Allowed values: Free entry Example: 01-Jan-2028; 01-Jan-2028; 31-Dec-2028; -
Note on E16: Package rate % / Minimum premium / Commission % / Package TSI limit Rate scheme of the version Mandatory: Yes (minimum, commission; rate or insurer rates) Format: Percentages and PHP amounts Allowed values: Free entry Example: 1.2000; 5000.00; 15; 5000000.00
Note on F16: Computation basis How the premium is computed Mandatory: Yes Format: Text Allowed values: Free entry Example: Comprehensive rate on the vehicle value
Note on G16: Coverage code / Included / Optional / Limit / Deductible Coverages of the version Mandatory: Yes (one basic coverage) Format: Codes of CI-02; Y or N; PHP Allowed values: Codes of PM-02 Coverages, perils and field rules, column Code or field key (one or more) Example: OD_THEFT; Y; N; -; 2000.00
Note on H16: Insurer code / Role / Share % / Rate % / Minimum premium Panel insurers Mandatory: Yes (the panel) Format: Codes of CI-05; Panel, Lead or Participant; shares total 100 Allowed values: Codes of R04 Insurers, column insurer_code (one or more) Example: INS-MGIC; Panel; -; 1.2000; -
Note on I16: Insurer terms: insurer / coverage / limit / deductible / clauses Terms per insurer and coverage Mandatory: Yes (every insurer and included coverage) Format: Codes of CI-03 separated by commas Allowed values: Codes of PM-03 Clause library, column Clause code (one or more) Example: INS-MGIC; OD_THEFT; -; 2000.00; FLEET_REPAIR
Note on J16: ManCom sign-off reference / Signed package slip Evidence kept on the request Mandatory: Yes Format: Reference; the signed slip file Allowed values: Free entry Example: MC-2026-017

## R06 Package code map (legacy pa
R06 Package code map (legacy package to BIBS package version) | [7 empty] | Step 48 of 51
← Back to Start here | Step 48 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [6 empty] | Ask a question →
Purpose | One row per record of Package code map (legacy package and version to BIBS package version) as extracted from QPS (legacy packages); TSU (BIBS package versions). Key legacy_package_code, legacy_package_version, qualifier, qualifier_value. Sent as the file R06_template.csv (CSV, header row as below) with its control file (row count, count of distinct keys).
Provided by | TSU (to name); approved by Product Owner, MBS (approves); TSU (prepares); extracted by BDOI IT
Due | M5 (18 Jun 2027); final at T-7
How it is loaded | Migration Console: the file R06_template.csv (the header row as below) and its control file are received on Data Migration › Data Migration › Extracts and loaded by a batch of object R06; lands in: Renewal package map, used by the package check of the Renewal sanitation
Source | QPS (legacy packages); TSU (BIBS package versions)
Depends on | R05 Product lines, cover types, products and risk codes → | PM-06 Packages in force at go-live →
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Check when loaded | Exists in the legacy package list | 0 or more | Not blank | In the list; one qualifier per entry | Mandatory with a qualifier; bands of one legacy package do not overlap | In the list | Mandatory for MAP; active in Product Maintenance | -
Mandatory | Yes | Yes | Yes | No | Conditional: Mandatory with a qualifier; bands of one legacy package do not overlap | Yes | Conditional: Mandatory for MAP; active in Product Maintenance | No
Format | Code, up to 20; As stored in legacy | Integer, up to 4; Digits | Text, up to 200; Free text | Code, up to 20; Upper case | Text, up to 60; Code, or from-to amounts with a dot decimal | Code, up to 6; Upper case | Code, up to 40; As in BIBS | Text, up to 250; Free text
Allowed values | Free entry, up to 20 characters | A whole number | Free entry, up to 200 characters | RISK_CODE, INSURER, SI_BAND (list R06 qualifier) | Free entry, up to 60 characters | MAP, REJECT (list R06 action) | Active package versions in Product Maintenance | Free entry, up to 250 characters
What to enter | Legacy package code | Version of the legacy package | Package name in legacy | Attribute that splits one legacy package into several BIBS packages | Value of the qualifier (risk code, insurer code, or sum-insured band as from-to) | MAP to a BIBS package version, or REJECT (no BIBS package) | BIBS package version maintained by TSU | Why the entry maps as it does
Row | legacy_package_code * | legacy_package_version * | legacy_package_name * | qualifier | qualifier_value | action * | bibs_package_version | remarks
Example – overwrite or delete | PKG-MC-PRIV | 3 | Private Car Package 2027 | SI_BAND | 0.00-2000000.00 | MAP | MC-PRIVATE-STD v1 | Sum insured up to 2,000,000.00
Note on B17: legacy_package_code Legacy package code Mandatory: Yes Format: Code, up to 20; As stored in legacy Allowed values: Free entry, up to 20 characters Example: PKG-MC-PRIV
Note on C17: legacy_package_version Version of the legacy package Mandatory: Yes Format: Integer, up to 4; Digits Allowed values: A whole number Example: 3
Note on D17: legacy_package_name Package name in legacy Mandatory: Yes Format: Text, up to 200; Free text Allowed values: Free entry, up to 200 characters Example: Private Car Package 2027
Note on E17: qualifier Attribute that splits one legacy package into several BIBS packages Mandatory: No Format: Code, up to 20; Upper case Allowed values: RISK_CODE, INSURER, SI_BAND (list R06 qualifier) Example: SI_BAND
Note on F17: qualifier_value Value of the qualifier (risk code, insurer code, or sum-insured band as from-to) Mandatory: Conditional: Mandatory with a qualifier; bands of one legacy package do not overlap Format: Text, up to 60; Code, or from-to amounts with a dot decimal Allowed values: Free entry, up to 60 characters Example: 0.00-2000000.00
Note on G17: action MAP to a BIBS package version, or REJECT (no BIBS package) Mandatory: Yes Format: Code, up to 6; Upper case Allowed values: MAP, REJECT (list R06 action) Example: MAP
Note on H17: bibs_package_version BIBS package version maintained by TSU Mandatory: Conditional: Mandatory for MAP; active in Product Maintenance Format: Code, up to 40; As in BIBS Allowed values: Active package versions in Product Maintenance Example: MC-PRIVATE-STD v1
Note on I17: remarks Why the entry maps as it does Mandatory: No Format: Text, up to 250; Free text Allowed values: Free entry, up to 250 characters Example: Sum insured up to 2,000,000.00

## PM-08 Document templates
PM-08 Document templates | [5 empty] | Step 49 of 51
← Back to Start here | Step 49 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The texts of the package documents: Package Request Form, quotation slip, comparative table, package slip, package advisory and package renewal advisory, with the merge fields each may use
Provided by | TSU and MBS (texts); Business Administrator (maintenance)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Entered on Document Templates (New Business set, SCR-NB-44) as a new template version effective from a date; not migrated
Source | BDOI layouts of the current documents (Q03)
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | No | Yes
Format | PKG_REQUEST_FORM, PKG_QUOTATION_SLIP, PKG_COMPARATIVE, PKG_SLIP, PKG_ADVISORY, PKG_RENEWAL_ADVISORY | Text | Text with merge fields in double braces | PKG_REQUEST_FORM: reference, requestType, title; PKG_QUOTATION_SLIP: reference, roundNo, replyBy; PKG_COMPARATIVE: reference, roundNo, variant; PKG_SLIP: reference, title; advisories: productCode, productName, versionNo, effectiveFrom, reference | dd-MMM-yyyy
Allowed values | List Package document template: 6 values, see Reference lists | Free entry | Free entry | Free entry | A date, for example 15-Jan-2028
What to enter | Template code | Title of the template version | Opening text of the document | Fields filled in by BIBS | Date from which the version is used
Row | Template * | Title * | Text * | Merge fields used | Effective from *
Example – overwrite or delete | PKG_ADVISORY | Package advisory | This is to advise that the package {{productCode}} - {{productName}} ... | productCode, productName, versionNo, effectiveFrom, reference | 2026-11-01
Note on B16: Template Template code Mandatory: Yes Format: PKG_REQUEST_FORM, PKG_QUOTATION_SLIP, PKG_COMPARATIVE, PKG_SLIP, PKG_ADVISORY, PKG_RENEWAL_ADVISORY Allowed values: List Package document template: 6 values, see Reference lists Example: PKG_ADVISORY
Note on C16: Title Title of the template version Mandatory: Yes Format: Text Allowed values: Free entry Example: Package advisory
Note on D16: Text Opening text of the document Mandatory: Yes Format: Text with merge fields in double braces Allowed values: Free entry Example: This is to advise that the package {{productCode}} - {{productName}} ...
Note on E16: Merge fields used Fields filled in by BIBS Mandatory: No Format: PKG_REQUEST_FORM: reference, requestType, title; PKG_QUOTATION_SLIP: reference, roundNo, replyBy; PKG_COMPARATIVE: reference, roundNo, variant; PKG_SLIP: reference, title; advisories: productCode, productName, versionNo, effectiveFrom, reference Allowed values: Free entry Example: productCode, productName, versionNo, effectiveFrom, reference
Note on F16: Effective from Date from which the version is used Mandatory: Yes Format: dd-MMM-yyyy Allowed values: A date, for example 15-Jan-2028 Example: 01-Nov-2026

## UA-05 Parameters
UA-05 Password, session and sign-in parameters | [5 empty] | Step 50 of 51
← Back to Start here | Step 50 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. |  |  |  |  | Ask a question →
Purpose | The values of the sign-in, password, session and access-request parameters, as delivered and as BDOI Information Security wants them
Provided by | BDOI Information Security; BDOI IT for the sign-in mode
Due | 16-Jul-2027 – Values for UAT
How it is loaded | System Parameters (SCR-UA-18): entered by the System Administrator and approved by the Information Security Officer, audited; checked in SIT with the test plan
Source | BDOI security policy (UQ07, UQ08); the values delivered (FRS section 9.1)
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | Conditional: value changed | Yes
Format | LOGIN_MAX_FAILED_ATTEMPTS, SESSION_IDLE_WARNING_MINUTES, SESSION_TIMEOUT_MINUTES, SESSION_EXPIRY_WARNING_MINUTES, AUTH_MODE, USER_ID_PATTERN, USER_ID_FORMAT_TEXT, PASSWORD_HISTORY_COUNT, PASSWORD_MAX_AGE_DAYS, PASSWORD_MIN_AGE_DAYS, UAM_WORKING_HOURS, UAM_ANY_APPROVER, UAM_ROLE_APPLY_ON_APPROVAL, UAM_EXTERNAL_USERS, UAM_DORMANT_DAYS, UAM_DORMANT_NOTICE_DAYS, JOB_FAILURE_RECIPIENTS | As on System Parameters | Same type and range | Text | Name
Allowed values | List Sign-in: 17 values, see Reference lists | Free entry | Free entry | Free entry | Free entry
What to enter | One row per parameter | The value proposed with the system | The value BDOI wants | Policy reference or reason | Information Security or BDOI IT approver of the value
Row | Parameter * | Value as delivered * | Value wanted * | Reason | Approved by *
Example – overwrite or delete | PASSWORD_MAX_AGE_DAYS | 90 | 90 | BDO password policy | Ramon Dizon
Note on B16: Parameter One row per parameter Mandatory: Yes Format: LOGIN_MAX_FAILED_ATTEMPTS, SESSION_IDLE_WARNING_MINUTES, SESSION_TIMEOUT_MINUTES, SESSION_EXPIRY_WARNING_MINUTES, AUTH_MODE, USER_ID_PATTERN, USER_ID_FORMAT_TEXT, PASSWORD_HISTORY_COUNT, PASSWORD_MAX_AGE_DAYS, PASSWORD_MIN_AGE_DAYS, UAM_WORKING_HOURS, UAM_ANY_APPROVER, UAM_ROLE_APPLY_ON_APPROVAL, UAM_EXTERNAL_USERS, UAM_DORMANT_DAYS, UAM_DORMANT_NOTICE_DAYS, JOB_FAILURE_RECIPIENTS Allowed values: List Sign-in: 17 values, see Reference lists Example: PASSWORD_MAX_AGE_DAYS
Note on C16: Value as delivered The value proposed with the system Mandatory: Yes Format: As on System Parameters Allowed values: Free entry Example: 90
Note on D16: Value wanted The value BDOI wants Mandatory: Yes Format: Same type and range Allowed values: Free entry Example: 90
Note on E16: Reason Policy reference or reason Mandatory: Conditional: value changed Format: Text Allowed values: Free entry Example: BDO password policy
Note on F16: Approved by Information Security or BDOI IT approver of the value Mandatory: Yes Format: Name Allowed values: Free entry Example: Ramon Dizon

## UP-03 Watchlist entries (upload
UP-03 Watchlist entries (sanctions, PEP and internal lists) | [11 empty] | Step 51 of 51
← Back to Start here | Step 51 of 51. Fill in one row per record below the column headers; the guide above each column says what to enter. | [10 empty] | Ask a question →
Purpose | One row per listed person or entity of a sanctions, PEP or internal list that BIBS screens clients against; the BDO negative list and the lists BDOI keeps itself. A known reference changes the entry, a new one adds it; aliases are separated by semicolons.
Provided by | Compliance (Chief Compliance Officer)
Due | 16-Jul-2027 – Values for UAT
How it is loaded | Screen upload: Setup & Administration › Compliance Setup › List Sources and Runs, action Upload List File for the list source; the changes wait for a Compliance checker before screening uses them
Source | Platform upload definition (column layout as the screen loads it)
Depends on | Nothing: this template can be filled in first
Progress | Rows entered |  | Mandatory cells missing
Confirmed by (BDOI owner) |  |  | Date
Mandatory | Yes | Yes | Yes | No | No | No | No | No | No | No | No | No
Format | Text | Text | Text | Text | Text | Text; several names separated by ; | Date yyyy-MM-dd, e.g. 1970-02-28, or an Excel date | Text | Text | Date yyyy-MM-dd, e.g. 2026-01-15, or an Excel date | Text | Text
Allowed values | Free entry | INDIVIDUAL, ENTITY (list Entity Type (UP-03)) | Free entry | Free entry | Free entry | Free entry | Free entry | Free entry | Free entry | Free entry | SANCTION, PEP, INTERNAL (list List Type (UP-03)) | Free entry
What to enter | Reference of the record in the source list | A listed person or an entity | Name as listed | First name of a person | Last name of a person | Other names of the record | Birth date of a person | Nationality | Identification numbers | Date the record was listed | Kind of list; blank for the source's kind | Remarks
Row | Reference * | Entity Type * | Primary Name * | First Name | Last Name | Aliases | Birth Date | Nationality | ID Numbers | Listed On | List Type | Remarks
Example – overwrite or delete | UNSC-0001 | INDIVIDUAL | Dela Cruz, Juan Listed | Juan | Dela Cruz | Juanito DC; J. D. Cruz | 1970-02-28 | Filipino | P1234567 | 2026-01-15 |  | Advisory 2026-01
Note on B16: Reference Reference of the record in the source list Mandatory: Yes Format: Text Allowed values: Free entry Example: UNSC-0001
Note on C16: Entity Type A listed person or an entity Mandatory: Yes Format: Text Allowed values: INDIVIDUAL, ENTITY (list Entity Type (UP-03)) Example: INDIVIDUAL
Note on D16: Primary Name Name as listed Mandatory: Yes Format: Text Allowed values: Free entry Example: Dela Cruz, Juan Listed
Note on E16: First Name First name of a person Mandatory: No Format: Text Allowed values: Free entry Example: Juan
Note on F16: Last Name Last name of a person Mandatory: No Format: Text Allowed values: Free entry Example: Dela Cruz
Note on G16: Aliases Other names of the record Mandatory: No Format: Text; several names separated by ; Allowed values: Free entry Example: Juanito DC; J. D. Cruz
Note on H16: Birth Date Birth date of a person Mandatory: No Format: Date yyyy-MM-dd, e.g. 1970-02-28, or an Excel date Allowed values: Free entry Example: 1970-02-28
Note on I16: Nationality Nationality Mandatory: No Format: Text Allowed values: Free entry Example: Filipino
Note on J16: ID Numbers Identification numbers Mandatory: No Format: Text Allowed values: Free entry Example: P1234567
Note on K16: Listed On Date the record was listed Mandatory: No Format: Date yyyy-MM-dd, e.g. 2026-01-15, or an Excel date Allowed values: Free entry Example: 2026-01-15
Note on L16: List Type Kind of list; blank for the source's kind Mandatory: No Format: Text Allowed values: SANCTION, PEP, INTERNAL (list List Type (UP-03))
Note on M16: Remarks Remarks Mandatory: No Format: Text Allowed values: Free entry Example: Advisory 2026-01

## Lists of values
Review list: lists of values
← Back to Start here | Every list of values of BIBS with its owner and its route: legacy values mapped through the Migration Console (R01), the others entered on Lists of Values
List | Name | Module | Owner (BDOI unit) | Values proposed | Route | Given in | Due | Values to keep, add or retire | Status | BDOI comments
ACSL_CASE_TYPE | ACSL case type | Accounting, Disbursement and ACSL | Head, Comptrollership | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
ACSL_CORRECTION_KIND | ACSL correction kind | Accounting, Disbursement and ACSL | Head, Comptrollership | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
ADJ_RETURN_REASON | Endorsement return reason | Operations | Head, Operations Services | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
AR_CLASS | Acknowledgement receipt class | Operations | Head, Operations Services | 11 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_ADJUSTER | Adjuster / appraiser | Claims | Product Owner, Claims | 25 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_CATASTROPHE | Catastrophe code | Claims | Product Owner, Claims | 7 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_CLAIM_STATUS | Claim status | Claims | Product Owner, Claims | 18 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_CLAIM_TYPE | Claim type | Claims | Product Owner, Claims | 10 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_DIARY_TYPE | Claim diary entry type | Claims | Product Owner, Claims | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_DOCUMENT_TYPE | Claim document type | Claims | Product Owner, Claims | 9 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_LOSS_NATURE | Nature of loss | Claims | Product Owner, Claims | 10 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_OVERRIDE_REASON | Claim override reason | Claims | Product Owner, Claims | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_REOPEN_REASON | Claim reopen reason | Claims | Product Owner, Claims | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_SETTLEMENT_TYPE | Requested type of settlement | Claims | Product Owner, Claims | 10 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_UNIT | Claims unit | Claims | Product Owner, Claims | 7 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
BCL_UPDATE_SOURCE | Insurer update source | Claims | Product Owner, Claims | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
BRANCH_EMAIL | Branch e-mail address | Operations | Head, Operations Services | 0 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CANCELLATION_REASON | Cancellation reason | Operations | Head, Operations Services | 36 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CIVIL_STATUS | Civil status | New Business | Product Owner, BDOI (New Business) | 4 | Migration Console | Template R01 (legacy values mapped by code map LOV:CIVIL_STATUS); new values on Lists of Values | 18-Jun-2027 (T-28 weeks) |  | Not started
CLAUSE_KIND | Clause kind | Product Maintenance | Product Owner, Marketing Business System (MBS) | 4 | Configuration screen | Template PM-09 (sheet PM-09 Lists and parameters) | 9-Apr-2027 (T-38 weeks) |  | Not started
CLIENT_CONFIRMATION_CHANNEL | Client confirmation channel | New Business | Product Owner, BDOI (New Business) | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CLIENT_DEACTIVATION_REASON | Client deactivation reason | New Business | Product Owner, BDOI (New Business) | 7 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CLIENT_TAG | Client tag | New Business | Product Owner, BDOI (New Business) | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CLX_BILLING_FREQUENCY | Billing frequency | Collections | VP and Head, BDOI Operations (Collections) | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CLX_EFFORT_CODE | Collection effort code | Collections | VP and Head, BDOI Operations (Collections) | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CLX_ESCALATION_REASON | Escalation reason | Collections | VP and Head, BDOI Operations (Collections) | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CLX_PR_DISPOSITION | PR collector disposition | Collections | VP and Head, BDOI Operations (Collections) | 8 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CLX_UPP_DISPOSITION | Unapplied payment disposition (collector) | Collections | VP and Head, BDOI Operations (Collections) | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CONSTRUCTION_CLASS | Construction class | New Business | Product Owner, BDOI (New Business) | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
COVERAGE_KIND | Coverage kind | Product Maintenance | Product Owner, Marketing Business System (MBS) | 4 | Configuration screen | Template PM-09 (sheet PM-09 Lists and parameters) | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_CHANGE_REASON | Contact change reason | Customer Servicing Facility | Product Owner, Customer Servicing Facility | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_CHANNEL | Contact channel | Customer Servicing Facility | Product Owner, Customer Servicing Facility | 3 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_DOCUMENT_TYPE | Contact centre document type | Customer Servicing Facility | Product Owner, Customer Servicing Facility | 7 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_REFERRAL_FIELD | Change referred to the fulfilment unit | Customer Servicing Facility | Product Owner, Customer Servicing Facility | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_STATUS | Customer service status | Customer Servicing Facility | Product Owner, Customer Servicing Facility | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_STATUS_MAP | Customer service status mapping | Customer Servicing Facility | Product Owner, Customer Servicing Facility | 14 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
CSF_VERIFY_CHECK | Caller verification check | Customer Servicing Facility | Product Owner, Customer Servicing Facility | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
DISBURSEMENT_TYPE | Disbursement type | Accounting, Disbursement and ACSL | Head, Comptrollership | 12 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
DISB_CANCEL_REASON | DV cancellation reason | Accounting, Disbursement and ACSL | Head, Comptrollership | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
DISB_RETURN_REASON | DV return / rejection reason | Accounting, Disbursement and ACSL | Head, Comptrollership | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
DISPOSITION_TYPE | Unapplied payment disposition | Operations | Head, Operations Services | 7 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
DOCUMENT_TYPE | Document type | Product Maintenance | Product Owner, Marketing Business System (MBS) | 61 | Configuration screen | Template PM-09 (sheet PM-09 Lists and parameters) | 9-Apr-2027 (T-38 weeks) |  | Not started
DP_FEEDBACK_REASON | Direct payment feedback reason | Collections | VP and Head, BDOI Operations (Collections) | 1 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_BENEFIT_LINE | EB benefit line | Employee Benefits | Product Owner, Employee Benefits | 3 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_CAPABILITY_FACTOR | EB capability factor | Employee Benefits | Product Owner, Employee Benefits | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_FRANCHISE_REJECT_REASON | EB franchise rejection reason | Employee Benefits | Product Owner, Employee Benefits | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_LOST_REASON | EB lost / not renewed reason | Employee Benefits | Product Owner, Employee Benefits | 7 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_MEMBER_CHANGE_TYPE | EB member change type | Employee Benefits | Product Owner, Employee Benefits | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_PROCESS_TYPE | EB process type | Employee Benefits | Product Owner, Employee Benefits | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_SOA_REJECT_REASON | EB SOA rejection reason | Employee Benefits | Product Owner, Employee Benefits | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_TEAM | EB team | Employee Benefits | Product Owner, Employee Benefits | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
EB_TRACKED_ITEM_TYPE | EB tracked item type | Employee Benefits | Product Owner, Employee Benefits | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
ENDORSEMENT_DOC_TYPE | Endorsement document type | Operations | Head, Operations Services | 1 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
ENDORSEMENT_REQUEST_TYPE | Endorsement request type | Operations | Head, Operations Services | 12 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
ENDORSEMENT_TYPE | Endorsement type | Operations | Head, Operations Services | 14 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
EPOLICY_REJECT_REASON | E-policy rejection reason | New Business | Product Owner, BDOI (New Business) | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
FFY_CANCEL_REASON | FFY cancellation reason | New Business | Product Owner, BDOI (New Business) | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
HOLD_REASON | Remittance hold reason | Operations | Head, Operations Services | 1 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
ID_TYPE | Identification document | New Business | Product Owner, BDOI (New Business) | 10 | Migration Console | Template R01 (legacy values mapped by code map LOV:ID_TYPE); new values on Lists of Values | 18-Jun-2027 (T-28 weeks) |  | Not started
INCENTIVE_EXCLUSION_RULE | Incentive exclusion rule | New Business | Product Owner, BDOI (New Business) | 2 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
INCENTIVE_TYPE | Incentive type | Product Maintenance | Product Owner, Marketing Business System (MBS) | 2 | Configuration screen | Template PM-09 (sheet PM-09 Lists and parameters) | 9-Apr-2027 (T-38 weeks) |  | Not started
INSTRUCTION_TYPE | Special instruction type | New Business | Product Owner, BDOI (New Business) | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
KYC_DOCS_CORPORATE | KYC checklist - corporate | New Business | Product Owner, BDOI (New Business) | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
KYC_DOCS_INDIVIDUAL | KYC checklist - individual | New Business | Product Owner, BDOI (New Business) | 2 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
KYC_RISK_RATING | KYC risk rating | New Business | Product Owner, BDOI (New Business) | 3 | Migration Console | Template R01 (legacy values mapped by code map LOV:KYC_RISK_RATING); new values on Lists of Values | 18-Jun-2027 (T-28 weeks) |  | Not started
LEGACY_RECORD_STATUS | Legacy record status | Data Migration | Program Manager, Business Project Services (Data Migration) | 18 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
LEGACY_RECORD_TYPE | Legacy record type | Data Migration | Program Manager, Business Project Services (Data Migration) | 11 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
MARKET_SEGMENT | Market segment | Product Maintenance | Product Owner, Marketing Business System (MBS) | 5 | Migration Console | Template R01 (legacy values mapped by code map LOV:MARKET_SEGMENT); new values on Lists of Values | 18-Jun-2027 (T-28 weeks) |  | Not started
MIG_ACCESS_REASON | Legacy access reason | Data Migration | Program Manager, Business Project Services (Data Migration) | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
MIG_BREAK_REASON | Reconciliation break reason | Data Migration | Program Manager, Business Project Services (Data Migration) | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
MIG_OBJECT_CATEGORY | Migration object category | Data Migration | Program Manager, Business Project Services (Data Migration) | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
MIG_SOURCE_SYSTEM | Legacy source system | Data Migration | Program Manager, Business Project Services (Data Migration) | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
MIG_TRUST_LEVEL | Data trust level | Data Migration | Program Manager, Business Project Services (Data Migration) | 3 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
MIG_WAIVER_REASON | Row waiver reason | Data Migration | Program Manager, Business Project Services (Data Migration) | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
MORTGAGEE_BANK | Mortgagee bank | New Business | Product Owner, BDOI (New Business) | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
NATIONALITY | Nationality | New Business | Product Owner, BDOI (New Business) | 6 | Migration Console | Template R01 (legacy values mapped by code map LOV:NATIONALITY); new values on Lists of Values | 18-Jun-2027 (T-28 weeks) |  | Not started
OCCUPANCY | Occupancy | New Business | Product Owner, BDOI (New Business) | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
OPS_EXTERNAL_LINK | Operations external link | Operations | Head, Operations Services | 0 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
OR_TYPE | Official receipt type | Operations | Head, Operations Services | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
PAYEE_CLASS | Payee class | Accounting, Disbursement and ACSL | Head, Comptrollership | 6 | Migration Console | Template R01 (legacy values mapped by code map LOV:PAYEE_CLASS); new values on Lists of Values | 18-Jun-2027 (T-28 weeks) |  | Not started
PKG_ADVISORY_GROUP | Advisory recipient group | Product Maintenance | Product Owner, Marketing Business System (MBS) | 5 | Configuration screen | Template PM-09 (sheet PM-09 Lists and parameters) | 9-Apr-2027 (T-38 weeks) |  | Not started
PKG_NOT_PROCEEDED_REASON | Package not proceeded reason | Product Maintenance | Product Owner, Marketing Business System (MBS) | 5 | Configuration screen | Template PM-09 (sheet PM-09 Lists and parameters) | 9-Apr-2027 (T-38 weeks) |  | Not started
PKG_REQUEST_REASON | Package request reason | Product Maintenance | Product Owner, Marketing Business System (MBS) | 8 | Configuration screen | Template PM-09 (sheet PM-09 Lists and parameters) | 9-Apr-2027 (T-38 weeks) |  | Not started
PKG_REQUEST_TYPE | Package request type | Product Maintenance | Product Owner, Marketing Business System (MBS) | 6 | Configuration screen | Template PM-09 (sheet PM-09 Lists and parameters) | 9-Apr-2027 (T-38 weeks) |  | Not started
PKG_RESPONSE_OUTCOME | Insurer response outcome | Product Maintenance | Product Owner, Marketing Business System (MBS) | 6 | Configuration screen | Template PM-09 (sheet PM-09 Lists and parameters) | 9-Apr-2027 (T-38 weeks) |  | Not started
PRQ_PAYMENT_MODE | Request payment mode | Accounting, Disbursement and ACSL | Head, Comptrollership | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
PRQ_RFP_TYPE | Request for payment type | Accounting, Disbursement and ACSL | Head, Comptrollership | 3 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RECEIPT_CANCEL_REASON | Receipt cancellation reason | Operations | Head, Operations Services | 17 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RECON_COMPANY_CONCERNED | Company concerned | Operations | Head, Operations Services | 0 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RECON_DISPOSITION | Reconciliation disposition | Operations | Head, Operations Services | 0 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
REFUND_REASON | Refund reason | Accounting, Disbursement and ACSL | Head, Comptrollership | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
REINSTATEMENT_REASON | Reinstatement reason | Operations | Head, Operations Services | 9 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
REMITTANCE_TYPE | Remittance type | Operations | Head, Operations Services | 3 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
REMIT_DEDUCTION_SOURCE | Remittance deduction source | Operations | Head, Operations Services | 3 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
REMIT_EXCLUSION_REASON | Remittance exclusion reason | Operations | Head, Operations Services | 7 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
REMIT_RETURN_REASON | Remittance return reason | Operations | Head, Operations Services | 1 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RETURN_REASON | Return reason | New Business | Product Owner, BDOI (New Business) | 7 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_DISPOSITION | Renewal disposition | Renewal | Product Owner, Renewal | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_FOLLOWUP_CHANNEL | Renewal follow-up channel | Renewal | Product Owner, Renewal | 3 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_FOLLOWUP_OUTCOME | Renewal follow-up outcome | Renewal | Product Owner, Renewal | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_INSURER_RESPONSE | Insurer renewal response | Renewal | Product Owner, Renewal | 3 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_LAMD_STATUS | LAMD loan status | Renewal | Product Owner, Renewal | 2 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_NONRENEWAL_REASON | Reason for Not for Renewal | Renewal | Product Owner, Renewal | 11 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_OVERRIDE_REASON | Renewal override reason | Renewal | Product Owner, Renewal | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_RETURN_REASON | Renewal return reason | Renewal | Product Owner, Renewal | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RNW_TRANSFER_REASON | Renewal transfer reason | Renewal | Product Owner, Renewal | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RRF_CATEGORY_A | Refund category A | Accounting, Disbursement and ACSL | Head, Comptrollership | 1 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
RRF_CATEGORY_B | Refund category B | Accounting, Disbursement and ACSL | Head, Comptrollership | 1 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_BUCKET | Submitted policy bucket | Submitted Policies | Product Owner, Submitted Policies | 12 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_CONVERSION_STATUS | Conversion status | Submitted Policies | Product Owner, Submitted Policies | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_DECLINE_REASON | Insurer re-assignment reason | Submitted Policies | Product Owner, Submitted Policies | 5 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_IAAF_FINDING | Policy review finding | Submitted Policies | Product Owner, Submitted Policies | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_LETTER_TYPE | Submitted policy letter type | Submitted Policies | Product Owner, Submitted Policies | 3 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_LOAN_STATUS | Loan status | Submitted Policies | Product Owner, Submitted Policies | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_NON_RENEWAL_REASON | Non-renewal reason (submitted policy) | Submitted Policies | Product Owner, Submitted Policies | 16 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_REASON | Submitted policy reason | Submitted Policies | Product Owner, Submitted Policies | 15 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_RETURN_REASON | IAAF or TOR return reason | Submitted Policies | Product Owner, Submitted Policies | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SBM_SEGMENT | Submitted policy segment | Submitted Policies | Product Owner, Submitted Policies | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_CASE_TYPE | Screening case type | Sanction Screening | Compliance | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_DISPOSITION | Screening disposition | Sanction Screening | Compliance | 13 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_DOCUMENT_TYPE | Screening document type | Sanction Screening | Compliance | 6 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_FORM_TYPE | Screening form type | Sanction Screening | Compliance | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_LIST_TYPE | Watchlist type | Sanction Screening | Compliance | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_REASSIGN_REASON | Case re-assignment reason | Sanction Screening | Compliance | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SCR_STR_REASON | STR reason | Sanction Screening | Compliance | 0 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SERVICE_FEE_SEGMENT | Service fee segment | Accounting, Disbursement and ACSL | Head, Comptrollership | 3 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
SOURCE_CHANNEL | Source channel | New Business | Product Owner, BDOI (New Business) | 5 | Migration Console | Template R01 (legacy values mapped by code map MIS:BUSINESS_ORIGIN); new values on Lists of Values | 18-Jun-2027 (T-28 weeks) |  | Not started
SOURCE_OF_FUNDS | Source of funds | New Business | Product Owner, BDOI (New Business) | 6 | Migration Console | Template R01 (legacy values mapped by code map LOV:SOURCE_OF_FUNDS); new values on Lists of Values | 18-Jun-2027 (T-28 weeks) |  | Not started
SPECIAL_REMIT_CONDITION | Special remittance condition | Operations | Head, Operations Services | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
UAM_BUSINESS_UNIT | Business unit group | User Access Maintenance | Business Administration (User Access) | 0 | Configuration screen | Template UA-06 (sheet UA-06 Lists of values) | 9-Apr-2027 (T-38 weeks) |  | Not started
UAM_DEACTIVATION_REASON | User deactivation reason | User Access Maintenance | Business Administration (User Access) | 6 | Configuration screen | Template UA-06 (sheet UA-06 Lists of values) | 9-Apr-2027 (T-38 weeks) |  | Not started
UAM_USER_LEVEL | User level | User Access Maintenance | Business Administration (User Access) | 0 | Configuration screen | Template UA-06 (sheet UA-06 Lists of values) | 9-Apr-2027 (T-38 weeks) |  | Not started
VEHICLE_BODY_TYPE | Vehicle body type | New Business | Product Owner, BDOI (New Business) | 7 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
VOID_REASON | Void reason | Operations | Head, Operations Services | 4 | Configuration screen | This sheet | 9-Apr-2027 (T-38 weeks) |  | Not started
Note on A4: List: Code of the list on Lists of Values
Note on B4: Name: Name of the list
Note on C4: Module: Module that uses the list
Note on D4: Owner (BDOI unit): Unit that owns the values
Note on E4: Values proposed: Number of values proposed with the platform
Note on F4: Route: Migration Console or Configuration screen
Note on G4: Given in: Template where the values are given
Note on H4: Due: Due date
Note on I4: Values to keep, add or retire: The owner's decision on the values
Note on J4: Status: Status of the row
Note on K4: BDOI comments: Decision, value or comment of the owner

## System parameters
Review list: system parameters
← Back to Start here | Every system parameter of BIBS (other than the SLA and turnaround parameters and the numbering prefixes) with the value proposed and the value BDOI wants
Parameter | Group | Module | Owner (BDOI unit) | What it controls | Type | Value proposed | Allowed range | Given in | Due | Value wanted | Reason | Approved by | Status | BDOI comments
BROKING_CLOSE_TIME | Accounting | Accounting, Disbursement and ACSL | Head, Comptrollership | Time (PHT, HH:MM) at which the broking books are closed on the last day of the month | string | 23:00 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BROKING_SOURCE_MODULES | Accounting | Accounting, Disbursement and ACSL | Head, Comptrollership | Source modules of the broking books: their postings are refused once the BROKING books of the period are closed | code list | BOOKING,OPSLEDGER,CASHIERING,REMITTANCE,ADJUSTMENT,COMMISSION,PRODRECON,DISBURSEMENT |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLOSE_ONLY_PREVIOUS_MONTH | Accounting | Accounting, Disbursement and ACSL | Head, Comptrollership | Month-end close only for the previous month and year | boolean | true |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EWT_RATE_TOLERANCE | Accounting | Accounting, Disbursement and ACSL | Head, Comptrollership | Largest difference in percentage points between the withholding rate of a document and the rate of the ATC before the EWT worksheet flags it | decimal | 0.05 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
OPS_BOOK_RATE_SOURCE | Accounting | Accounting, Disbursement and ACSL | Head, Comptrollership | Source of the Operations BOOK rate: CLOSING_PREV_MONTH copies the revaluation rate of the previous month end, MANUAL keeps it by hand | string | CLOSING_PREV_MONTH |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
YEAR_END_CLOSE_DEADLINE | Accounting | Accounting, Disbursement and ACSL | Head, Comptrollership | Month and day (MM-DD) by which the previous year must be closed; YEAR_END_CLOSE_DUE is raised before | string | 04-15 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
ACSL_SOA_MAX_ROWS | Acsl | Accounting, Disbursement and ACSL | Head, Comptrollership | Largest number of rows of one insurer statement of account upload | integer | 20000 | 1 to 200000 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BOOKING_BILLING_NO_LINES | Booking | New Business | Product Owner, BDOI (New Business) | Product lines whose bookings need the insurer billing number, unique per insurer | code list | HMO,GLI,GPA |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BOOKING_CWT2_SEGMENTS | Booking | New Business | Product Owner, BDOI (New Business) | Market segments whose corporate clients withhold 2% creditable tax on premium | code list | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BOOKING_WTAX_RATE | Booking | New Business | Product Owner, BDOI (New Business) | Withholding tax rate (percent) the insurer withholds on the broker commission, printed on the booked invoice and service invoice | decimal | 10 | 0 to 100 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
OPS_COMMISSION_REALIZATION | Booking | New Business | Product Owner, BDOI (New Business) | When broker commission is realized: ON_COLLECTION (unrealized at booking, realized when premium is applied) or ON_BOOKING (commission income and output VAT at booking) | string | ON_COLLECTION |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SERVICE_INVOICE_CREDIT_DAYS | Booking | New Business | Product Owner, BDOI (New Business) | Credit days printed on a service invoice (payment terms merged into its template) | integer | 30 | 0 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLIENT_CREDIT_DAYS | Broking | New Business | Product Owner, BDOI (New Business) | Credit days of the accounting party created for a client | integer | 30 | 0 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BULK_MAX_ROWS | Bulk | Platform set-up | BDOI IT | Maximum number of data rows in one bulk upload file | integer | 5000 | 10 to 50000 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_AUTH_DP_POLICY | Claims Handling | Claims | Product Owner, Claims | Claims authorization code on a direct-payment cover: ALLOW, CONFIRM (insurer payment evidence attached) or BLOCK | string | CONFIRM |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_DEFAULT_CURRENCY | Claims Handling | Claims | Product Owner, Claims | Currency of a claim whose cover has none | string | PHP |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_PRONE_MIN_CLAIMS | Claims Handling | Claims | Product Owner, Claims | Claims at one location that make it claims-prone | integer | 3 | 1 to 100 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_PRONE_YEARS | Claims Handling | Claims | Product Owner, Claims | Look-back years of the claims-prone location analysis | integer | 3 | 1 to 20 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_EDIT_LOCK_MINUTES | Collections | Collections | VP and Head, BDOI Operations (Collections) | Minutes after which the "<user> is editing" lock of a collection account expires | integer | 15 | 1 to 240 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_EXPORT_MAX_ROWS | Collections | Collections | VP and Head, BDOI Operations (Collections) | Maximum rows of an asynchronous Collections export | integer | 50000 | 100 to 1000000 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_INVOICE_NO_PATTERN | Collections | Collections | VP and Head, BDOI Operations (Collections) | Regular expression of the invoice number of "For application to invoice": EBIX I######## or BI-... of this system | string | ^(I\d{8}¦BI-.+)$ |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_MIN_BALANCE_THRESHOLD | Collections | Collections | VP and Head, BDOI Operations (Collections) | Net outstanding PR above which an invoice enters the collection worklist | decimal | 10.00 | 0 to 100000 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SUSPENSE_ACCOUNT_CODES | Controls | Accounting, Disbursement and ACSL | Head, Comptrollership | GL account codes monitored by the SUSPENSE_BALANCE exception (blank = accounts named Suspense) | code list | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLIENT_MIN_AGE | Crm | New Business | Product Owner, BDOI (New Business) | Minimum age in years of an individual policyholder | integer | 18 | 0 to 100 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLIENT_MIN_FIELDS_CORPORATE | Crm | New Business | Product Owner, BDOI (New Business) | Fields a corporate client needs to be complete. Codes: TIN, ID, CONTACT, ADDRESS, MARKET_SEGMENT, SOURCE_OF_FUNDS | code list | TIN,CONTACT,ADDRESS,MARKET_SEGMENT |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLIENT_MIN_FIELDS_INDIVIDUAL | Crm | New Business | Product Owner, BDOI (New Business) | Fields an individual client needs to be complete. Codes: BIRTH_DATE, TIN, ID, CONTACT, ADDRESS, MARKET_SEGMENT, NATIONALITY, SOURCE_OF_FUNDS, OCCUPATION | code list | BIRTH_DATE,TIN,ID,CONTACT,ADDRESS,MARKET_SEGMENT |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
KYC_DUE_WINDOW_DAYS | Crm | New Business | Product Owner, BDOI (New Business) | Days ahead in which a KYC review is listed as coming due | integer | 30 | 0 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
KYC_REVIEW_MONTHS | Crm | New Business | Product Owner, BDOI (New Business) | Months between periodic KYC reviews of standard and low risk clients | integer | 36 | 1 to 120 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
KYC_REVIEW_MONTHS_HIGH_RISK | Crm | New Business | Product Owner, BDOI (New Business) | Months between periodic KYC reviews of high risk clients | integer | 12 | 1 to 120 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_LEGACY_SYNC_ENABLED | Customer Service | Customer Servicing Facility | Product Owner, Customer Servicing Facility | Send contact changes to the legacy policy systems while they are still in use | boolean | false |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_PAYMENT_HISTORY_MONTHS | Customer Service | Customer Servicing Facility | Product Owner, Customer Servicing Facility | Months of payment history the contact centre sees before Show Older | integer | 12 | 1 to 120 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_SEARCH_MAX_RESULTS | Customer Service | Customer Servicing Facility | Product Owner, Customer Servicing Facility | Maximum clients a customer search returns before the contact centre officer must refine it | integer | 50 | 5 to 500 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_SEARCH_MIN_CHARS | Customer Service | Customer Servicing Facility | Product Owner, Customer Servicing Facility | Minimum characters of a client name search | integer | 3 | 1 to 20 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_VERIFICATION_VALID_MINUTES | Customer Service | Customer Servicing Facility | Product Owner, Customer Servicing Facility | Minutes a passed verification of a caller stays valid for a change | integer | 30 | 1 to 480 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_VERIFY_MAX_FAILS | Customer Service | Customer Servicing Facility | Product Owner, Customer Servicing Facility | Failed verifications of one client in a day that raise an alert to the supervisors | integer | 3 | 1 to 20 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CSF_VERIFY_MIN_MATCHES | Customer Service | Customer Servicing Facility | Product Owner, Customer Servicing Facility | Verification checks that must match before the contact details of a client can be changed | integer | 2 | 1 to 10 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
INSURER_DEFAULT_CREDIT_DAYS | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Credit days of an insurer loaded by data migration without credit days | integer | 30 | 0 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_ACCESS_EXPORT_ALERT_ROWS | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Archive records exported by one user in a day above which the unusual-access alert is raised | integer | 5000 | 1 to 1000000 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_AMOUNT_TOLERANCE | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Largest amount difference accepted by the amount reconciliation | decimal | 0.00 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_ARCHIVE_EXPORT_MAX_ROWS | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Largest number of archive records exported to Excel at a time | integer | 1000 | 1 to 100000 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_CHUNK_SIZE | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Rows loaded per transaction | integer | 500 | 10 to 5000 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_CLIENT_MATCH_AUTO | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Client match score from which two legacy clients are merged automatically | integer | 90 | 60 to 100 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_CLIENT_MATCH_REVIEW | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Client match score from which a pair goes to the Data Steward review queue | integer | 60 | 1 to 100 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_CUTOVER_DATE | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Go-live date (yyyy-MM-dd); the first business day on BIBS | string | 2028-01-03 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_ENVIRONMENT_CLASS | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | PRODUCTION or NON_PRODUCTION; outside production personal data of the extracts is masked before staging | string | NON_PRODUCTION |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_FREEZE_AT | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Start of the legacy business freeze (yyyy-MM-dd HH:mm, Philippine time) | string | 2027-12-31 22:00 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_GOLIVE_RENEWAL_TO | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Last expiry date of the migrated policies taken over by Renewal at go-live (yyyy-MM-dd) | string | 2028-05-31 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_LAST_LEGACY_BUSINESS_DAY | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Last business day processed in the legacy systems (yyyy-MM-dd) | string | 2027-12-29 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_LEGACY_ACCESS_REASON_REQUIRED | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | A reason is required before the legacy archive is searched | boolean | true |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_LEGACY_INVOICE_NO_PATTERN | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Patterns of legacy invoice numbers recognised by the payment matcher (comma separated regular expressions) | string | ^I\d{8}$ |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_LEGACY_LINK_EBIX | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Address of the read-only EBIX application for users who still need it | string | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_LEGACY_LINK_QPS | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Address of the read-only QPS application for users who still need it | string | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_MAX_ERROR_RATE_FINANCIAL | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Largest percentage of failing or waived rows with which open items, unapplied payments and the trial balance may be loaded | decimal | 0 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_MAX_ERROR_RATE_MASTER | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Largest percentage of failing or waived rows with which master data may be loaded | decimal | 0.5 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_OPENING_VALUE_DATE | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Value date of the opening entries and of the opening-balance adjustments (yyyy-MM-dd) | string | 2028-01-01 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_PARTITIONS | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Partitions loaded in parallel | integer | 4 | 1 to 16 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_RA_MAX_LEAD_DAYS | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | An advice already sent more than this number of days before expiry is loaded with a warning | integer | 140 | 1 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_RENEWAL_URGENT_TO | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Migrated policies expiring up to this date are flagged urgent in the go-live renewal queue (yyyy-MM-dd) | string | 2028-01-31 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_RESUBMIT_DEADLINE | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Last time a corrected resubmission of the advices already sent may be approved (yyyy-MM-dd HH:mm, Philippine time) | string | 2028-01-02 12:00 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_STAGING_RETENTION_DAYS | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Days staging data and extract files are kept after the batch is signed off or rolled back | integer | 5 | 1 to 5 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_UPP_ISSUE_AR | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Issue a BIBS acknowledgement receipt for each migrated unapplied payment (no cash posting) | boolean | false |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIG_YEAR_END_OPTION | Data Migration | Data Migration | Program Manager, Business Project Services (Data Migration) | Year-end cut-over option: A = provisional opening trial balance at the year-end boundary with controlled true-ups | string | A |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DISB_AUTO_APPROVER_ROUTING | Disbursement | Accounting, Disbursement and ACSL | Head, Comptrollership | Request types whose disbursement voucher is prepared automatically and routed straight to the approver | code list | REFUND,REMITTANCE |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DISB_CHECK_CLEARING | Disbursement | Accounting, Disbursement and ACSL | Head, Comptrollership | ON: issued checks are credited to checks outstanding until negotiated; OFF: to the bank at approval | string | ON |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DISB_CHECK_CLEARING_ACCOUNT | Disbursement | Accounting, Disbursement and ACSL | Head, Comptrollership | Checks outstanding clearing account credited for issued checks while DISB_CHECK_CLEARING = ON | string | 2241 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DISB_CHECK_SERIES_WARNING | Disbursement | Accounting, Disbursement and ACSL | Head, Comptrollership | Remaining check leaves of a paying account at which CHECK_SERIES_LOW is raised | integer | 20 | 1 to 1000 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DISB_NO_PAYEE_ACTION | Disbursement | Accounting, Disbursement and ACSL | Head, Comptrollership | Gateway request whose payee is not maintained: HOLD keeps it as NO_PAYEE, raises DISB_PAYEE_NO_MATCH and a payee request and resumes it once the payee is authorised; RETURN returns it at once to its source | string | HOLD |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DISB_STALE_DAYS | Disbursement | Accounting, Disbursement and ACSL | Head, Comptrollership | Days after the print date at which a printed or released check becomes stale | integer | 180 | 30 to 720 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EARLY_INCENTIVE_WTAX_RATE | Disbursement | Accounting, Disbursement and ACSL | Head, Comptrollership | Withholding tax rate (percent) of the early-incentive service invoice | decimal | 2 | 0 to 100 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_ADJ_BOOKING_REQUIRES_PAYMENT | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | Raise the endorsement request of a member change only after its billing is paid | boolean | false |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_FOLLOWUP_MAX | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | Follow-ups sent before a tracked item is escalated | integer | 3 | 1 to 20 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EPOLICY_PASSWORD_HINT | Issuance | New Business | Product Owner, BDOI (New Business) | Text telling the client how the password of the e-policy is formed | string | The password follows the BDOI standard; it is sent to you in a separate e-mail. |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
IA_TRIGGER | Issuance | New Business | Product Owner, BDOI (New Business) | When the Insurance Advice of a mortgaged account is generated automatically: ON_POLICY_ISSUE, ON_PLACEMENT or MANUAL | string | ON_POLICY_ISSUE |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MAIL_FROM_ADDRESS | Messaging | Platform set-up | BDOI IT | From address of e-mails sent by this system (quotations, slips, e-policies, invoices) | string | no-reply@bdoi.example.ph |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MAIL_MAX_ATTEMPTS | Messaging | Platform set-up | BDOI IT | Delivery attempts before an e-mail is marked failed | integer | 3 | 1 to 10 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
ADJ_BASELINE_PERCENT | Operations | Operations | Head, Operations Services | Over-adjustment baseline: cumulative adjustments of an invoice above this percent of its original premium need an override reason and raise ADJ_OVER_BASELINE | decimal | 100 | 1 to 1000 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_BANK_ACCOUNT | Operations | Operations | Head, Operations Services | GL account debited for payments received by check, bank or electronic channels | string | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CASH_ON_HAND_ACCOUNT | Operations | Operations | Head, Operations Services | GL account debited for payments received in cash over the counter | string | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CMR_DP_COLLECTION_BANK | Operations | Operations | Head, Operations Services | GL bank account proposed for direct payment commission collections (role BANK of OPS_DP_COMMISSION_COLLECT) | string | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CWT_APPLICATION_PERCENT | Operations | Operations | Head, Operations Services | Share of the premium applied for accounts of clients withholding 2% creditable tax | decimal | 98 | 50 to 100 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DP_PREMIUM_TOLERANCE | Operations | Operations | Head, Operations Services | Largest difference between the premium of a direct payment list and the booked gross premium that still passes the check | decimal | 1.00 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
DP_PR_REVERSAL_POSTING | Operations | Operations | Head, Operations Services | Post the GL entry of the direct payment PR reversal and reinstatement (OPS_DP_PR_REVERSAL / OPS_DP_REINSTATE). Off while booking posts no premium receivable for direct payment invoices; the ledger reversal is always recorded | boolean | false |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
JOB_HISTORY_DAYS | Operations | Operations | Head, Operations Services | Days of scheduled job history shown in the job monitor | integer | 90 | 1 to 3650 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIN_BALANCE_AUTO_MAX | Operations | Operations | Head, Operations Services | Minimal balances up to this amount are reversed automatically | decimal | 10.00 | 0 to 1000 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MIN_BALANCE_FILE_RANGE | Operations | Operations | Head, Operations Services | Balance range of the minimal balance write-off file | string | 10.00-100.00 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
OPS_BOOK_RATE_TYPE | Operations | Operations | Head, Operations Services | Exchange rate type of Operations postings: the Comptrollership BOOK rate, 2 decimals | string | BOOK |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PRODRECON_FILE_PATTERN | Operations | Operations | Head, Operations Services | File naming convention of the production register sent to insurers | string | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RECON_MATCH_KEYS | Operations | Operations | Head, Operations Services | Keys pairing an insurer production line with a booked invoice, tried in order: INVOICE_NO, POLICY_NO, PN_NO | code list | INVOICE_NO,POLICY_NO |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RECON_TOLERANCE | Operations | Operations | Head, Operations Services | Production reconciliation tolerance: differences up to this amount are matched | decimal | 1.00 | 0 to 1000 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
REMIT_CHECK_HOLD_DAYS | Operations | Operations | Head, Operations Services | Banking days a check must be held (and cleared) before its payment is remitted | integer | 3 | 0 to 30 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
REMIT_FILE_PATTERN | Operations | Operations | Head, Operations Services | File naming convention of the remittance extracts | string | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
REMIT_PAIDAR_OVER_DTIP_MODE | Operations | Operations | Head, Operations Services | Paid AR greater than DTIP: EXCLUDE the invoice from extraction or CAP the remittance at the DTIP | string | EXCLUDE |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
HOLD_COVER_DAYS | Placement | New Business | Product Owner, BDOI (New Business) | Days of hold cover requested from the insurer while the placement completes | integer | 30 | 1 to 90 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PACKAGE_RENEWAL_AUTODRAFT | Product Maintenance | Product Maintenance | Product Owner, Marketing Business System (MBS) | The expiry monitor drafts a RENEW package request for packages reaching the notice period | boolean | false |  | Template PM-09 (sheet PM-09 Lists and parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_ADVISORY_GROUPS | Product Maintenance | Product Maintenance | Product Owner, Marketing Business System (MBS) | Recipient groups (list PKG_ADVISORY_GROUP) proposed on a new package advisory | code list | MARKETING,TSU,MBS,OPERATIONS |  | Template PM-09 (sheet PM-09 Lists and parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_AUTO_PLACEMENT | Renewal | Renewal | Product Owner, Renewal | Generate and send the placement slip automatically once an accepted renewal is ready for placement | boolean | true |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_BULK_INITIATION_SEGMENTS | Renewal | Renewal | Product Owner, Renewal | Market segments whose renewals may be initiated in bulk; the others one at a time | code list | CLG |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CBG_SEGMENTS | Renewal | Renewal | Product Owner, Renewal | Market segments on the loan-driven straight-through path (no assignment to an AO) | code list | CBG |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_CBG_STP_LINES | Renewal | Renewal | Product Owner, Renewal | Product lines of the straight-through path of those segments | code list | MOTOR,PROPERTY |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_EXCLUDED_LINES | Renewal | Renewal | Product Owner, Renewal | Product lines never extracted for renewal (renewed as Employee Benefits programmes) | code list | HMO,GLI,GPA |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_FIN_IMPACT_TOLERANCE | Renewal | Renewal | Product Owner, Renewal | Difference in premium, sum insured or rate above which a renewal has a financial impact | decimal | 0.00 | 0 to - | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_INVOICE_NO_REASONS | Renewal | Renewal | Product Owner, Renewal | Reasons for Not for Renewal that need the number of the new invoice | code list | BOOKED_TO_NEW_INVOICE |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_KYC_SEGMENTS | Renewal | Renewal | Product Owner, Renewal | Market segments where the KYC due flag applies; empty = all | code list | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_NAL_REASONS | Renewal | Renewal | Product Owner, Renewal | Reasons for Not for Renewal answered with a No Advice Letter instead of a Not for Renewal Letter | code list | DIRECT_TO_INSURER,WITH_SUBMITTED_POLICY,BOOKED_TO_NEW_INVOICE,UNIT_SOLD,CANCELED_POLICY |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_NON_ACCEPTANCE_DAYS | Renewal | Renewal | Product Owner, Renewal | Days after expiry of the non-acceptance letter and the closure of unrenewed accounts | integer | 0 | 0 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_OUTSTANDING_THRESHOLD | Renewal | Renewal | Product Owner, Renewal | Open premium of the expiring invoice family above which the renewal is flagged Outstanding | decimal | 0.00 | 0 to - | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_PN_REQUIRED_LINES | Renewal | Renewal | Product Owner, Renewal | Product lines whose mortgaged or straight-through renewals need the PN number | code list | MOTOR,PROPERTY |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_REOPEN_DAYS | Renewal | Renewal | Product Owner, Renewal | Days after expiry during which a Not for Renewal account can be re-opened | integer | 30 | 0 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_RMU_UNIT | Renewal | Renewal | Product Owner, Renewal | Sales unit that receives RMU accounts; empty = tag them Not for Renewal | string | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_STP_SKIP_TL_REVIEW | Renewal | Renewal | Product Owner, Renewal | Automatic dispositions of the decision matrix skip the Team Leader review | boolean | true |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
REPORT_FOOTER_TEXT | Reporting | Accounting, Disbursement and ACSL | Head, Comptrollership | Footer text printed on exported reports | string | Confidential - for internal use only. |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SCR_BLOCK_ON_OPEN_MATCH | Screening | Sanction Screening | Compliance | When true, account submission and placement are refused while the client has an open true or potential match | boolean | false |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SCR_COMMITTEE_RULE | Screening | Sanction Screening | Compliance | How the AML Committee decides: ANY, MAJORITY or ALL of SCR_COMMITTEE_SIZE members | string | MAJORITY |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SCR_COMMITTEE_SIZE | Screening | Sanction Screening | Compliance | Members of the AML Committee counted by the MAJORITY / ALL rule | integer | 5 | 1 to 20 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SCR_FULL_RESCREEN_DAY | Screening | Sanction Screening | Compliance | Day of the month of the full rescreen of the in-scope clients; other days screen the list changes only | integer | 1 | 1 to 28 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SCR_INGEST_ALERT_RECIPIENTS | Screening | Sanction Screening | Compliance | Comma separated e-mail addresses that receive the digest of failed watchlist records | string | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SCR_SCREENING_SCOPE | Screening | Sanction Screening | Compliance | Client statuses screened by the periodic run | code list | PROSPECT,CONFIRMED |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
ACCESS_TOKEN_MINUTES | Security | Security settings | BDOI Information Security | Minutes an access token is valid; the web client renews it while the session is in use | integer | 15 | 5 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
AUTH_MODE | Security | Security settings | BDOI Information Security | Sign-in mode: LOCAL (BIBS passwords) or DIRECTORY (BDO directory sign-in by Windows ID, when the EIAM sign-in is specified) | string | LOCAL |  | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
FILE_LINK_TTL_SECONDS | Security | Security settings | BDOI Information Security | Seconds a presigned file download or upload link stays valid | integer | 300 | 30 to 3600 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
JOB_FAILURE_RECIPIENTS | Security | Security settings | BDOI Information Security | Comma separated e-mail addresses told of every failed batch job | string | (blank) |  | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
LOGIN_MAX_FAILED_ATTEMPTS | Security | Security settings | BDOI Information Security | Consecutive failed logins that lock a user account; applies to all users | integer | 3 | 1 to 10 | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MFA_ISSUER_NAME | Security | Security settings | BDOI Information Security | Name of the system shown next to the account in the authenticator app (blank = the system name of the deployment) | string | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MFA_POLICY | Security | Security settings | BDOI Information Security | Who must confirm a sign-in with an authenticator app code: ALL users, PRIVILEGED users (a role of privilege level HIGH or ADMIN) or OFF (only users who enrolled themselves) | string | PRIVILEGED |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
MFA_REMEMBER_DEVICE_DAYS | Security | Security settings | BDOI Information Security | Days a device may be remembered after a code is confirmed, so the code is not asked again on it; 0 = never remembered | integer | 0 | 0 to 30 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PASSWORD_EXPIRY_NOTICE_DAYS | Security | Security settings | BDOI Information Security | Days before a password expires from which the user is told to change it (LOCAL mode) | integer | 7 | 1 to 90 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PASSWORD_HISTORY_COUNT | Security | Security settings | BDOI Information Security | Previous passwords a user may not reuse, LOCAL mode | integer | 8 | 0 to 24 | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PASSWORD_MAX_AGE_DAYS | Security | Security settings | BDOI Information Security | Days after which a password must be changed, LOCAL mode; 0 = never | integer | 90 | 0 to 365 | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PASSWORD_MIN_AGE_DAYS | Security | Security settings | BDOI Information Security | Days before a changed password may be changed again, LOCAL mode | integer | 1 | 0 to 30 | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SESSION_EXPIRY_WARNING_MINUTES | Security | Security settings | BDOI Information Security | Minutes before the system-triggered (absolute) sign-out at which the web client warns the user | integer | 30 | 1 to 240 | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SESSION_IDLE_WARNING_MINUTES | Security | Security settings | BDOI Information Security | Minutes of inactivity after which the web client warns that the session will sign out | integer | 15 | 1 to 480 | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SESSION_TIMEOUT_MINUTES | Security | Security settings | BDOI Information Security | Minutes of inactivity after which the web session signs out automatically | integer | 30 | 5 to 480 | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_ANY_APPROVER | Security | Security settings | BDOI Information Security | When true, any holder of ACCESS_APPROVE may decide a request, not only the approver chosen by the requester | boolean | false |  | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_DIRECT_ROLE_EDIT | Security | Security settings | BDOI Information Security | Emergency path: when true, the System Administrator may create and edit roles directly on the Roles screen (audited, alert UAM_DIRECT_ROLE_EDIT); when false, a role changes only by implementing an approved group-profile request | boolean | false |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_DORMANT_DAYS | Security | Security settings | BDOI Information Security | Days without a sign-in after which a user is deactivated by the daily dormant-user job; 0 = never | integer | 90 | 0 to 730 | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_DORMANT_NOTICE_DAYS | Security | Security settings | BDOI Information Security | Days before the dormant-user deactivation on which the user is told to sign in; 0 = no notice | integer | 7 | 0 to 60 | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_EXTERNAL_USERS | Security | Security settings | BDOI Information Security | When true, access requests may be raised for external (portal) users; stays false while no portal is installed | boolean | false |  | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_ROLE_APPLY_ON_APPROVAL | Security | Security settings | BDOI Information Security | When true, an approved group-profile or role-permission request applies at its last approval; when false it waits for the System Administrator to implement it | boolean | false |  | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
UAM_WORKING_HOURS | Security | Security settings | BDOI Information Security | Working hours; an access request submitted outside them needs a second approval | string | 08:00-18:00,MON-FRI |  | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
USER_ID_FORMAT_TEXT | Security | Security settings | BDOI Information Security | The user ID format in words, shown to the requester with the format check of USER_ID_PATTERN | string | a letter followed by nine digits, for example a013000196 |  | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
USER_ID_PATTERN | Security | Security settings | BDOI Information Security | Regular expression of a new user ID on enrolment requests | string | ^[a-zA-Z][0-9]{9}$ |  | Template UA-05 (sheet UA-05 Parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_INSURER_ACCEPT_DAYS | Submitted | Submitted Policies | Product Owner, Submitted Policies | Days the assigned insurer has to accept the hold cover of a submitted policy renewal before the handler is alerted | integer | 5 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_MANUAL_RENEWAL_SEGMENTS | Submitted | Submitted Policies | Product Owner, Submitted Policies | Segments whose renewal the Account Officer starts by hand with Renew with BDOI; the expiry scan leaves them out | code list | NONCBG_RETAIL |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_MASTERLIST_DAYS_FROM_EXTRACTION | Submitted | Submitted Policies | Product Owner, Submitted Policies | Target days from the extraction of a CBG Motor policy to its masterlist record | integer | 30 | 1 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_OWN_RECORDS_ROLES | Submitted | Submitted Policies | Product Owner, Submitted Policies | Roles whose users see only the submitted policies they handle or whose renewal they own, unless a user scope says otherwise | code list | MKT_AO |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
TAX_FBT_GROSSUP_RATE | Tax | Accounting, Disbursement and ACSL | Head, Comptrollership | Gross-up of the monetary value of fringe benefits in percent (100 / 65) used by the 1603 worksheet | decimal | 153.8462 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
TAX_FBT_RATE | Tax | Accounting, Disbursement and ACSL | Head, Comptrollership | Fringe benefit tax rate in percent used by the 1603 worksheet | decimal | 35 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
TAX_RCIT_RATE | Tax | Accounting, Disbursement and ACSL | Head, Comptrollership | Regular corporate income tax rate in percent used by the 1702-Q / 1702 worksheets | decimal | 25 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
TAX_RDO_CODE | Tax | Accounting, Disbursement and ACSL | Head, Comptrollership | BIR Revenue District Office code of the withholding agent, printed on the SLS/SLP/QAP exports | string | 050 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
Note on A4: Parameter: Parameter on System Parameters
Note on B4: Group: Group of the parameter
Note on C4: Module: Module
Note on D4: Owner (BDOI unit): Unit that decides the value
Note on E4: What it controls: Meaning of the parameter
Note on F4: Type: Kind of value
Note on G4: Value proposed: Value proposed with the platform
Note on H4: Allowed range: Minimum and maximum
Note on I4: Given in: Where the value wanted is given
Note on J4: Due: Due date
Note on K4: Value wanted: Value BDOI wants
Note on L4: Reason: Policy reference or reason of a change
Note on M4: Approved by: BDOI approver of the value
Note on N4: Status: Status of the row
Note on O4: BDOI comments: Decision, value or comment of the owner

## SLA and turnaround
Review list: sla and turnaround
← Back to Start here | The SLA, turnaround, reminder, escalation and ageing parameters: days and hours of the work queues, insurer replies, reminders and alerts
Parameter | Group | Module | Owner (BDOI unit) | What it controls | Type | Value proposed | Allowed range | Given in | Due | Value wanted | Reason | Approved by | Status | BDOI comments
QUOTATION_EXPIRING_DAYS | Broking | New Business | Product Owner, BDOI (New Business) | Quotations whose validity ends within this many days are listed as expiring | integer | 7 | 1 to 90 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
QUOTATION_SLIP_REPLY_DAYS | Broking | New Business | Product Owner, BDOI (New Business) | Days given to insurers to reply to a quotation slip | integer | 5 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
QUOTATION_VALIDITY_DAYS | Broking | New Business | Product Owner, BDOI (New Business) | Default validity of a quotation in days from its creation | integer | 30 | 1 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RATE_EXCEPTION_VALIDITY_DAYS | Broking | New Business | Product Owner, BDOI (New Business) | Days a rate-scheme exception stays valid when the request gives no end date | integer | 30 | 1 to 3650 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_AGEING_BUCKETS | Claims Handling | Claims | Product Owner, Claims | Upper bounds in days of the claims ageing buckets: 0-30, 31-60, 61-90, 91-180, 181+ | integer list | 30,60,90,180 | 1 to 3650 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_FOLLOW_UP_DAYS | Claims Handling | Claims | Product Owner, Claims | Days from a status change to the next follow-up date when the status has no follow up days attribute | integer | 7 | 1 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
BCL_PAST_DUE_DAYS | Claims Handling | Claims | Product Owner, Claims | Age in days above which an outstanding claim is past due: report and alert BCL_CLAIM_PAST_DUE | integer | 90 | 1 to 3650 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_AGING_BASIS | Collections | Collections | VP and Head, BDOI Operations (Collections) | Date the aging of a collection item counts from: BOOKING or INCEPTION | string | BOOKING |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_AGING_BRACKETS | Collections | Collections | VP and Head, BDOI Operations (Collections) | Aging brackets of the worklist, the home chart and the reports, in days | code list | 0-30,31-45,46-60,61-90,91-120,121+ |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CLX_PROMISE_GRACE_DAYS | Collections | Collections | VP and Head, BDOI Operations (Collections) | Days after the promised date before an unpaid promise to pay is broken | integer | 0 | 0 to 30 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_COMPARATIVE_DAYS | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | Working days from the last proposal to the comparative sent to the client | integer | 3 | 1 to 30 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_FOLLOWUP_DAYS | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | Working days between follow-ups of a pending tracked item | integer | 5 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_FRANCHISE_ADVICE_DAYS | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | Working days to advise the client of the franchise outcome | integer | 2 | 1 to 30 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_FRANCHISE_GRACE_DAYS | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | Working days after the franchise decision date before an undecided franchise request expires | integer | 2 | 0 to 30 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_FRANCHISE_TAT_DAYS | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | Working days for the insurer franchise decision | integer | 5 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_PROPOSAL_REPLY_DAYS | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | Working days an insurer has to answer a request for proposal | integer | 5 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_RA_LEAD_DAYS | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | Days before expiry the renewal advice is sent and the renewal cycle opened | integer | 135 | 1 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_RA_REMINDER_DAYS | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | Days before expiry of the RA reminders while no feedback is recorded | integer list | 90,105,120 | 1 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_BOOKING | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days to book once billing is validated | integer | 3 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_CARDS | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days to submit, validate and release member cards | integer | 10 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_COC | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days for the insurer certificate of cover | integer | 1 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_COLLECTION | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days to collect the premium upon SOA / billing receipt | integer | 2 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_CONFIRMATION | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days to send the client confirmation to the insurer | integer | 2 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_FRANCHISE_SUBMIT | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days to submit a franchise request upon complete documents | integer | 3 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_MEMBER_CHANGE | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days per step of an inclusion / deletion | integer | 3 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_OR | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days for the insurer to submit the official receipt | integer | 5 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_PLACEMENT_REQUEST | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days to request placement and booking upon client confirmation | integer | 5 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_PLACEMENT_SLIP | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: days for Processing to submit the placement slip | integer | 3 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_POLICY_CHECK | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days to check the policy / contract against the proposal | integer | 3 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_POLICY_SOA | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days for the insurer policy / contract and billing / SOA | integer | 10 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_RELEASE | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days to release the SOA to Collection and the policy to the client | integer | 3 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_RFQ_SUBMIT | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days to send the request for quotation upon franchise approval | integer | 3 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
EB_TAT_SOA_VALIDATION | Employee Benefits | Employee Benefits | Product Owner, Employee Benefits | TAT: working days for Processing to validate the final SOA | integer | 3 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
NB_STALLED_DAYS | Nb Reports | New Business | Product Owner, BDOI (New Business) | An open New Business account with no stage movement for this many days is reported as stalled | integer | 5 | 1 to 90 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
CMR_FEEDBACK_WORKING_DAYS | Operations | Operations | Head, Operations Services | Working days an insurer has to answer a direct payment commission billing | integer | 10 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
HOLD_COVER_ALERT_DAYS | Placement | New Business | Product Owner, BDOI (New Business) | Days before a hold cover expires when Processing is alerted | integer | 5 | 0 to 30 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PACKAGE_EXPIRY_NOTICE_DAYS | Product Maintenance | Product Maintenance | Product Owner, Marketing Business System (MBS) | Days before the package end date at which PACKAGE_EXPIRING is first raised; again at 30 and 7 days | integer | 60 | 1 to 365 | Template PM-09 (sheet PM-09 Lists and parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PACKAGE_EXPIRY_REMINDER_DAYS | Product Maintenance | Product Maintenance | Product Owner, Marketing Business System (MBS) | Days before the package end date at which PACKAGE_EXPIRING is raised again after the first notice | integer list | 30,7 |  | Template PM-09 (sheet PM-09 Lists and parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_QS_REPLY_DAYS | Product Maintenance | Product Maintenance | Product Owner, Marketing Business System (MBS) | Days insurers have to reply to a package quotation slip | integer | 5 | 1 to 60 | Template PM-09 (sheet PM-09 Lists and parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_SLA_MANCOM | Product Maintenance | Product Maintenance | Product Owner, Marketing Business System (MBS) | SLA hours of the ManCom sign-off | integer | 72 | 1 to 720 | Template PM-09 (sheet PM-09 Lists and parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_SLA_MBS_SETUP | Product Maintenance | Product Maintenance | Product Owner, Marketing Business System (MBS) | SLA hours of the MBS package set-up | integer | 48 | 1 to 720 | Template PM-09 (sheet PM-09 Lists and parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_SLA_MKT_APPROVAL | Product Maintenance | Product Maintenance | Product Owner, Marketing Business System (MBS) | SLA hours of the Marketing approval of a package request | integer | 24 | 1 to 720 | Template PM-09 (sheet PM-09 Lists and parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_SLA_NEGOTIATION | Product Maintenance | Product Maintenance | Product Owner, Marketing Business System (MBS) | SLA hours of the insurer negotiation stage | integer | 120 | 1 to 2160 | Template PM-09 (sheet PM-09 Lists and parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_SLA_TSU_APPROVAL | Product Maintenance | Product Maintenance | Product Owner, Marketing Business System (MBS) | SLA hours of the TSU Team Head approval | integer | 24 | 1 to 720 | Template PM-09 (sheet PM-09 Lists and parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
PKG_SLA_TSU_REVIEW | Product Maintenance | Product Maintenance | Product Owner, Marketing Business System (MBS) | SLA hours of the TSU Team Lead review and recommendation | integer | 24 | 1 to 720 | Template PM-09 (sheet PM-09 Lists and parameters) | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_ESCALATION_DAYS | Renewal | Renewal | Product Owner, Renewal | Days to expiry at which an account not disposed or not accepted is at risk, per segment (* = others) | string | IBG=60,LEASING=60,*=30 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_EXCEPTION_AGEING_DAYS | Renewal | Renewal | Product Owner, Renewal | Days a renewal may stay in the Exception bucket before it is escalated | integer | 7 | 1 to 90 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_EXTRACTION_LEAD_DAYS | Renewal | Renewal | Product Owner, Renewal | Days before expiry at which the daily extraction takes a policy | integer | 140 | 1 to 400 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_EXTRACTION_LEAD_DAYS_BY_SEGMENT | Renewal | Renewal | Product Owner, Renewal | Lead days per market segment, e.g. CBG=150,IBG=120; empty = the general lead days | string | (blank) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_INSURER_REPLY_DAYS | Renewal | Renewal | Product Owner, Renewal | Days the insurer has to answer a renewal batch | integer | 10 | 1 to 90 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_NRNS_REMINDER_DAYS | Renewal | Renewal | Product Owner, Renewal | Days before expiry of the reminder to renewals not yet submitted (NRNS) | integer | 90 | 0 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_RA_MIN_NOTICE_DAYS | Renewal | Renewal | Product Owner, Renewal | A Renewal Advice generated fewer days than this before expiry needs a confirmation | integer | 30 | 0 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
RNW_RA_SECOND_NOTICE_DAYS | Renewal | Renewal | Product Owner, Renewal | Days after the first notice without acceptance before a second notice is offered | integer | 15 | 1 to 365 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
AGEING_BUCKETS | Reporting | Accounting, Disbursement and ACSL | Head, Comptrollership | Default ageing slots in days (up to 5 ascending limits) of the debtors and creditors ageing reports; users may override them per run | integer list | 30,60,90,120 | 1 to 3650 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_HOLD_COVER_UNBOOKED_ALERT_DAYS | Submitted | Submitted Policies | Product Owner, Submitted Policies | Days before a confirmed hold cover ends at which a renewal account not yet booked is alerted | integer | 5 | 0 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_RENEWAL_LEAD_DAYS | Submitted | Submitted Policies | Product Owner, Submitted Policies | Days before expiry at which a submitted policy for renewal is handed to Renewal, per segment (* = other segments) | string | CBG_FIRE=150,CBG_MOTOR=120,*=90 |  | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
SBM_REVIEW_SLA_DAYS | Submitted | Submitted Policies | Product Owner, Submitted Policies | Days an IAAF or TOR approval level may wait before it is alerted | integer | 5 | 1 to 60 | This sheet | 16-Jul-2027 (T-24 weeks) |  |  |  | Not started
Note on A4: Parameter: Parameter on System Parameters
Note on B4: Group: Group of the parameter
Note on C4: Module: Module
Note on D4: Owner (BDOI unit): Unit that decides the value
Note on E4: What it controls: Meaning of the parameter
Note on F4: Type: Kind of value
Note on G4: Value proposed: Value proposed with the platform
Note on H4: Allowed range: Minimum and maximum
Note on I4: Given in: Where the value wanted is given
Note on J4: Due: Due date
Note on K4: Value wanted: Value BDOI wants
Note on L4: Reason: Policy reference or reason of a change
Note on M4: Approved by: BDOI approver of the value
Note on N4: Status: Status of the row
Note on O4: BDOI comments: Decision, value or comment of the owner

## Numbering prefixes
Review list: numbering prefixes
← Back to Start here | Prefixes of the numbered documents; receipt series come from R11, check numbers from D0-12
Parameter | Module | Numbered document | Prefix proposed | Owner (BDOI unit) | Prefix wanted | Status | BDOI comments
PROPOSAL_NUMBER_PREFIX | New Business | Prefix of the PRF marketing reference (<prefix>-<yyyy>-nnnnnn) | PRF | Product Owner, BDOI (New Business) |  | Not started
PROPOSAL_SLIP_PREFIX | New Business | Prefix of proposal slip numbers (<prefix>-<yyyy>-nnnnnn) | PS | Product Owner, BDOI (New Business) |  | Not started
QUOTATION_NUMBER_PREFIX | New Business | Prefix of package quotation numbers (<prefix>-<yyyy>-nnnnnn), shown as Proposal No. | QT | Product Owner, BDOI (New Business) |  | Not started
QUOTATION_REQUEST_PREFIX | New Business | Prefix of quotation request numbers (<prefix>-<yyyy>-nnnnnn) | REQ | Product Owner, BDOI (New Business) |  | Not started
QUOTATION_SLIP_PREFIX | New Business | Prefix of quotation slip numbers (<prefix>-<yyyy>-nnnnnn) | QS | Product Owner, BDOI (New Business) |  | Not started
MIG_INVOICE_NO_COLLISION_PREFIX | Data Migration | Prefix the source system to a legacy invoice number found in two source systems | true | Program Manager, Business Project Services (Data Migration) |  | Not started
PKG_QS_PREFIX | Product Maintenance | Prefix of package quotation slip numbers; the year is appended | PQS- | Product Owner, Marketing Business System (MBS) |  | Not started
PKG_REQUEST_PREFIX | Product Maintenance | Prefix of package request numbers; the year is appended | PKR- | Product Owner, Marketing Business System (MBS) |  | Not started
RNW_REFERENCE_PREFIX | Renewal | Prefix of the renewal reference (prefix-yyyy-nnnnnn) | RNW | Product Owner, Renewal |  | Not started
SCR_CASE_SEQUENCE_PREFIX | Sanction Screening | Prefix of the screening case number <prefix>-yyyy-nnnnnn | SCR | Compliance |  | Not started
SBM_NUMBER_PREFIX | Submitted Policies | Prefix of the masterlist number (prefix-yyyy-nnnnnn) | SBM | Product Owner, Submitted Policies |  | Not started
Note on A4: Parameter: Prefix parameter
Note on B4: Module: Module of the document
Note on C4: Numbered document: Document numbered with the prefix
Note on D4: Prefix proposed: Prefix proposed with the platform
Note on E4: Owner (BDOI unit): Unit that decides the prefix
Note on F4: Prefix wanted: Prefix BDOI wants; the year and a running number follow it
Note on G4: Status: Status of the row
Note on H4: BDOI comments: Decision, value or comment of the owner

## Notification events
Review list: notification events
← Back to Start here | Every notification event with its default channels and the unit mailbox that also receives it; users choose their own channels in Notification Settings
Event | Name | Module | Owner (BDOI unit) | Who is told and when | In-app proposed | E-mail proposed | In-app wanted | E-mail wanted | Unit mailbox (recipient) | Status | BDOI comments
ACSL_CASE_STATUS | ACSL case or correction status | Accounting, Disbursement and ACSL | Head, Comptrollership | An ACSL case you requested has a result, or a correction entry you prepared was returned, approved or posted | Y | N |  |  |  | Not started
ACSL_GLSL_DIFFERENCE | GL-SL difference found | Accounting, Disbursement and ACSL | Head, Comptrollership | The GL-SL reconciliation found a control account whose sub-ledger differs from the general ledger | Y | Y |  |  |  | Not started
ADJ_REQUEST_STATUS | Endorsement request status | Operations | Head, Operations Services | An endorsement request you raised was returned, approved or posted | Y | N |  |  |  | Not started
BOOKING_BILLING_BOOKED | Booked with billing number | New Business | Product Owner, BDOI (New Business) | An account was booked with its insurer billing number | Y | N |  |  |  | Not started
BOOKING_BILLING_DUPLICATE | Duplicate billing number | New Business | Product Owner, BDOI (New Business) | A booking was refused because the insurer billing number is already on an invoice | Y | Y |  |  |  | Not started
CASH_APPROVAL_REQUEST | Cashiering approval request | Operations | Head, Operations Services | A receipt cancellation, reinstatement or disposition waits for approval | Y | N |  |  |  | Not started
BCL_FOLLOW_UP_DUE | Claim follow-up due | Claims | Product Owner, Claims | A claim of yours has its next follow-up or a diary entry due today | Y | N |  |  |  | Not started
BCL_CLAIM_ASSIGNED | Claim assigned | Claims | Product Owner, Claims | A claim was assigned or re-assigned to you | Y | Y |  |  |  | Not started
BCL_STATUS_CHANGED | Claim status changed | Claims | Product Owner, Claims | The status of a claim of one of your accounts changed | Y | N |  |  |  | Not started
BCL_PREMIUM_REMITTED | Claim premium remitted | Claims | Product Owner, Claims | The premium of a claim awaiting premium remittance was fully remitted to the insurer | Y | N |  |  |  | Not started
BCL_NEWER_COVER_VERSION | Newer cover version | Claims | Product Owner, Claims | An endorsement was booked on the cover of an open claim of yours | Y | N |  |  |  | Not started
CLX_ESCALATED | Account escalated | Collections | VP and Head, BDOI Operations (Collections) | A collection account was escalated to you or by your team | Y | Y |  |  |  | Not started
CLX_REASSIGNED | Account reassigned | Collections | VP and Head, BDOI Operations (Collections) | Collection accounts were assigned to you or taken from you | Y | N |  |  |  | Not started
CLX_PROMISE_BROKEN | Promise to pay broken | Collections | VP and Head, BDOI Operations (Collections) | A promise to pay of one of your accounts was not kept | Y | N |  |  |  | Not started
CLX_DP_RETURNED | Direct payment returned by insurer | Collections | VP and Head, BDOI Operations (Collections) | An insurer returned a direct payment account; it is back in your worklist | Y | N |  |  |  | Not started
CLX_FILE_READY | Collections file ready | Collections | VP and Head, BDOI Operations (Collections) | A scheduled Collections file is available for download | Y | N |  |  |  | Not started
DP_FEEDBACK_OVERDUE | Direct payment feedback overdue | Collections | VP and Head, BDOI Operations (Collections) | An insurer has not answered a direct payment billing in time | Y | Y |  |  |  | Not started
EB_FEEDBACK_RECEIVED | EB client feedback received | Employee Benefits | Product Owner, Employee Benefits | A client gave feedback on the renewal advice of your programme | Y | N |  |  |  | Not started
EB_BOR_DECIDED | EB Broker on Record decided | Employee Benefits | Product Owner, Employee Benefits | A Broker on Record you uploaded was validated or rejected | Y | N |  |  |  | Not started
EB_FRANCHISE_DECIDED | EB franchise decided | Employee Benefits | Product Owner, Employee Benefits | An insurer approved or rejected a franchise request of yours | Y | Y |  |  |  | Not started
EB_PROPOSAL_RECEIVED | EB proposal received | Employee Benefits | Product Owner, Employee Benefits | An insurer submitted a proposal to validate | Y | N |  |  |  | Not started
EB_COMPARATIVE_SIGNOFF | EB comparative to sign off | Employee Benefits | Product Owner, Employee Benefits | A comparative waits for your sign-off | Y | Y |  |  |  | Not started
EB_COMPARATIVE_DECIDED | EB comparative decided | Employee Benefits | Product Owner, Employee Benefits | A comparative of your programme was signed off, approved above the threshold or returned | Y | N |  |  |  | Not started
EB_THRESHOLD_APPROVAL | EB threshold approval | Employee Benefits | Product Owner, Employee Benefits | A comparative above the value threshold waits for your approval | Y | Y |  |  |  | Not started
EB_CLIENT_CONFIRMED | EB client confirmation | Employee Benefits | Product Owner, Employee Benefits | A client confirmed the chosen proposals of your programme | Y | N |  |  |  | Not started
EB_PLACEMENT_TRIGGERED | EB placement triggered | Employee Benefits | Product Owner, Employee Benefits | The accounts of an EB cycle were created for placement | Y | N |  |  |  | Not started
EB_ROSTER_STAGED | EB master list staged | Employee Benefits | Product Owner, Employee Benefits | A master list of your programme was loaded and waits for your review | Y | N |  |  |  | Not started
EB_MEMBER_CHANGE_BILLED | EB member change billed | Employee Benefits | Product Owner, Employee Benefits | An insurer billed a member change to validate | Y | N |  |  |  | Not started
EB_SUBMISSION_SENT | EB documents submitted | Employee Benefits | Product Owner, Employee Benefits | Documents of an Employee Benefits programme were submitted to an insurer | Y | N |  |  |  | Not started
EB_SOA_RELEASED | EB SOA released | Employee Benefits | Product Owner, Employee Benefits | An insurer SOA was validated and released to Collection and the client | Y | N |  |  |  | Not started
EB_INVOICE_PAID | EB invoice paid | Employee Benefits | Product Owner, Employee Benefits | An invoice of an EB programme became paid | Y | N |  |  |  | Not started
EB_ITEM_ESCALATED | EB pending item escalated | Employee Benefits | Product Owner, Employee Benefits | A tracked item passed its follow-ups without being received | Y | Y |  |  |  | Not started
OPS_INVOICE_LOCKED | Invoice locked or released | Operations | Head, Operations Services | An invoice you work on was locked by another team or released | Y | N |  |  |  | Not started
OPS_FLOW_IN_FAILED | Interface run failed | Operations | Head, Operations Services | A flow-in or flow-out run failed or had failed records | Y | Y |  |  |  | Not started
OPS_DISBURSEMENT_STATUS | Disbursement status | Operations | Head, Operations Services | A payment request was acknowledged, received its DV number, was paid or returned | Y | N |  |  |  | Not started
PRQ_REQUEST_STATUS | Refund / cash advance request status | Accounting, Disbursement and ACSL | Head, Comptrollership | A refund, cash-advance or check-cancellation request was validated, returned, approved or disbursed | Y | N |  |  |  | Not started
RECON_FEEDBACK_UPLOADED | Insurer reconciliation feedback | Operations | Head, Operations Services | An insurer production feedback was uploaded and matched | Y | N |  |  |  | Not started
REMIT_EXTRACTION_DONE | Remittance extraction completed | Operations | Head, Operations Services | A scheduled or manual remittance extraction finished | Y | Y |  |  |  | Not started
REMIT_BATCH_FOR_APPROVAL | Remittance batch for approval | Operations | Head, Operations Services | A remittance batch was submitted for approval | Y | Y |  |  |  | Not started
REMIT_BATCH_DECIDED | Remittance batch approved or returned | Operations | Head, Operations Services | A remittance batch you prepared was approved or returned | Y | N |  |  |  | Not started
REMIT_NEG_ADJ_PENDING | Negative adjustment on a remittance invoice | Operations | Head, Operations Services | A negative adjustment was requested on an invoice in remittance | Y | Y |  |  |  | Not started
HOLD_EXPIRING | Remittance hold expiring | Operations | Head, Operations Services | A remittance hold reaches its hold date | Y | N |  |  |  | Not started
RNW_ASSIGNED | Renewal assigned | Renewal | Product Owner, Renewal | Expiring accounts were assigned to you for disposition or processing | Y | N |  |  |  | Not started
RNW_TRANSFER_REQUESTED | Renewal transfer requested | Renewal | Product Owner, Renewal | Another Marketing unit transferred an expiring account to your unit | Y | Y |  |  |  | Not started
RNW_TRANSFER_DECIDED | Renewal transfer decided | Renewal | Product Owner, Renewal | The receiving unit accepted or declined your transfer of an expiring account | Y | N |  |  |  | Not started
RNW_RETURNED | Renewal returned | Renewal | Product Owner, Renewal | An expiring account was returned to you with remarks | Y | Y |  |  |  | Not started
RNW_POSTED | Renewal posted | Renewal | Product Owner, Renewal | Dispositioned accounts were posted by the Team Leader | Y | N |  |  |  | Not started
RNW_INSURER_RESPONDED | Insurer renewal response | Renewal | Product Owner, Renewal | An insurer answered the renewal of an account you process | Y | N |  |  |  | Not started
RNW_ACCEPTED | Renewal accepted | Renewal | Product Owner, Renewal | A client accepted the Renewal Advice of an account of yours | Y | N |  |  |  | Not started
RNW_RENEWED | Renewal booked | Renewal | Product Owner, Renewal | The renewal of an account of yours was booked | Y | N |  |  |  | Not started
RNW_GOLIVE_COMPLETED | Go-live renewal extraction completed | Renewal | Product Owner, Renewal | The expiring migrated policies of the go-live window were taken over as renewals | Y | Y |  |  |  | Not started
RNW_PACKAGE_DECIDED | Renewal package choice decided | Renewal | Product Owner, Renewal | Your choice of the package version of a migrated policy was approved or rejected | Y | N |  |  |  | Not started
SCR_CASE_ASSIGNED | Screening case assigned | Sanction Screening | Compliance | A screening case was assigned or re-assigned to you | Y | Y |  |  |  | Not started
SCR_CASE_FOR_APPROVAL | Screening case for approval | Sanction Screening | Compliance | A screening case waits for your approval | Y | Y |  |  |  | Not started
SCR_CASE_RETURNED | Screening case returned | Sanction Screening | Compliance | A screening case was returned to you with a rationale | Y | Y |  |  |  | Not started
SCR_COMMITTEE_REVIEW | AML Committee review | Sanction Screening | Compliance | A screening case waits for the vote of the AML Committee | Y | Y |  |  |  | Not started
SCR_SLA_REMINDER | Screening SLA reminder | Sanction Screening | Compliance | A screening case of yours is about to pass its SLA | Y | Y |  |  |  | Not started
SCR_SLA_ESCALATION | Screening SLA escalation | Sanction Screening | Compliance | A screening case passed its SLA and is escalated to you | Y | Y |  |  |  | Not started
SCR_DOCUMENT_REMINDER | Screening document reminder | Sanction Screening | Compliance | Documents of a screening case are still missing | Y | N |  |  |  | Not started
SCR_NO_POLICY_HIT | Screening hit without active policy | Sanction Screening | Compliance | A high-risk or PEP client without an active policy was found | Y | N |  |  |  | Not started
SCR_CONFIG_TO_APPROVE | Screening configuration to approve | Sanction Screening | Compliance | A screening configuration version waits for your approval | Y | N |  |  |  | Not started
SCR_LIST_CHANGE_TO_APPROVE | Watchlist change to approve | Sanction Screening | Compliance | A watchlist change waits for your approval | Y | N |  |  |  | Not started
FILE_QUARANTINED | File quarantined | Platform set-up | BDOI IT | A file you uploaded, or one you review as security officer, was quarantined by the malware scan | Y | Y |  |  |  | Not started
SBM_NEW_SUBMISSION | New submitted policies | Submitted Policies | Product Owner, Submitted Policies | Submitted policies were loaded from a source file | Y | N |  |  |  | Not started
SBM_MANUAL_VALIDATION | Policy document to confirm | Submitted Policies | Product Owner, Submitted Policies | A submitted policy document waits for the confirmation of its details | Y | N |  |  |  | Not started
SBM_IAAF_PENDING | IAAF to approve | Submitted Policies | Product Owner, Submitted Policies | An IAAF waits for your approval | Y | Y |  |  |  | Not started
SBM_TOR_PENDING | TOR to approve | Submitted Policies | Product Owner, Submitted Policies | A Terms of Reference waits for your approval | Y | Y |  |  |  | Not started
SBM_TOR_RELEASED | TOR approved | Submitted Policies | Product Owner, Submitted Policies | The Terms of Reference of your account was approved; open or download it | Y | Y |  |  |  | Not started
SBM_BUCKET_CHANGED | Submitted policy bucket changed | Submitted Policies | Product Owner, Submitted Policies | Submitted policies moved to the renewal, manual disposition or non-renewal buckets | Y | N |  |  |  | Not started
SBM_FALLOUT | Submitted policies fallout | Submitted Policies | Product Owner, Submitted Policies | A processing run ended with fallout to resolve | Y | N |  |  |  | Not started
SBM_EXPIRY_NEAR | Submitted policy nearing expiry | Submitted Policies | Product Owner, Submitted Policies | A submitted policy for renewal is within the renewal lead days | Y | N |  |  |  | Not started
SBM_RENEWAL_STARTED | Renewal of a submitted policy started | Submitted Policies | Product Owner, Submitted Policies | A submitted policy was handed to Renewal | Y | N |  |  |  | Not started
SBM_PLACEMENT_READY | Submitted policy renewal ready for placement | Submitted Policies | Product Owner, Submitted Policies | The renewal account of a submitted policy is ready for placement | Y | N |  |  |  | Not started
SBM_PLACEMENT_SENT | Submitted policy renewal placed | Submitted Policies | Product Owner, Submitted Policies | The placement slip of a submitted policy renewal was sent to the insurer | Y | N |  |  |  | Not started
SBM_HOLD_COVER_UNBOOKED | Hold cover of an unbooked renewal | Submitted Policies | Product Owner, Submitted Policies | A hold cover ends soon and the renewal account is not booked | Y | Y |  |  |  | Not started
SBM_HANDLER_ASSIGNED | Submitted policy assigned | Submitted Policies | Product Owner, Submitted Policies | Submitted policies were assigned to you | Y | N |  |  |  | Not started
UAM_REQUEST_TO_APPROVE | Access request to approve | User Access Maintenance | Business Administration (User Access) | An access request waits for your approval | Y | Y |  |  |  | Not started
UAM_REQUEST_RETURNED | Access request returned | User Access Maintenance | Business Administration (User Access) | Your access request was returned with remarks | Y | Y |  |  |  | Not started
UAM_REQUEST_CANCELLED | Access request cancelled | User Access Maintenance | Business Administration (User Access) | An access request assigned to you was cancelled | Y | N |  |  |  | Not started
UAM_REQUEST_DECIDED | Access request decided | User Access Maintenance | Business Administration (User Access) | Your access request was approved or rejected | Y | Y |  |  |  | Not started
UAM_ACCESS_CHANGED | Your access changed | User Access Maintenance | Business Administration (User Access) | Your user data or group profiles were changed | Y | Y |  |  |  | Not started
UAM_SECOND_APPROVAL | Access request for second approval | User Access Maintenance | Business Administration (User Access) | A privileged or out-of-hours access request waits for your second approval | Y | Y |  |  |  | Not started
UAM_FOR_IMPLEMENTATION | Group profile request to implement | User Access Maintenance | Business Administration (User Access) | An approved group-profile request waits for the System Administrator | Y | Y |  |  |  | Not started
PASSWORD_EXPIRY_NOTICE | Password expires soon | User Access Maintenance | Business Administration (User Access) | Your password expires within 7 days; change it on My Profile | Y | Y |  |  |  | Not started
UAM_DORMANT_WARNING | Account deactivation soon | User Access Maintenance | Business Administration (User Access) | You have not signed in for a long time; sign in before the date given or your account is deactivated | Y | Y |  |  |  | Not started
UAM_DORMANT_DEACTIVATED | Dormant users deactivated | User Access Maintenance | Business Administration (User Access) | Users who had not signed in for the dormancy period were deactivated | Y | N |  |  |  | Not started
UAM_PARAMETER_TO_APPROVE | Security setting to approve | User Access Maintenance | Business Administration (User Access) | A change of a sign-in, password, session or access setting waits for your approval | Y | Y |  |  |  | Not started
UAM_SOD_TO_AUTHORIZE | Separation-of-duties rule to authorise | User Access Maintenance | Business Administration (User Access) | A new or deactivated separation-of-duties rule waits for your authorisation | Y | N |  |  |  | Not started
MFA_RESET_TO_APPROVE | Second factor reset to approve | User Access Maintenance | Business Administration (User Access) | A reset of a user's authenticator app waits for your approval | Y | Y |  |  |  | Not started
MFA_RESET_DONE | Second factor reset | User Access Maintenance | Business Administration (User Access) | Your authenticator app was reset by the administrators; enrol it again at your next sign-in | Y | Y |  |  |  | Not started
Note on A4: Event: Notification event
Note on B4: Name: Name shown in Notification Settings
Note on C4: Module: Module
Note on D4: Owner (BDOI unit): Unit that confirms the event
Note on E4: Who is told and when: What the event tells the user
Note on F4: In-app proposed: Y or N
Note on G4: E-mail proposed: Y or N
Note on H4: In-app wanted: Y or N
Note on I4: E-mail wanted: Y or N
Note on J4: Unit mailbox (recipient): Mailbox that also receives the e-mail (optional)
Note on K4: Status: Status of the row
Note on L4: BDOI comments: Decision, value or comment of the owner

## Document templates
Review list: document templates
← Back to Start here | Every generated document and letter with the unit that gives its BDOI wording and layout; the layout is uploaded as a Word file on Document Templates
Template | Title | Module | Owner (BDOI unit) | Merge fields available | Given in | Due | BDOI layout attached | Status | BDOI comments
BCL_LOSS_ADVICE | Loss advice {{claimNo}} - {{assuredName}} | Claims | Product Owner, Claims | adjusterName, arn, assuredName, claimNo, currency, handlerName, initialReserve, insurerClaimNos, insurerName, lossDate, lossDescription, lossNature, lossPlace, policyNo, policyYear | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
CLX_SOA | Statement of account | Collections | VP and Head, BDOI Operations (Collections) | arn, balance, currency, cycleFrom, cycleTo, dueDate, frequency | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_ATD | Authority to debit | Accounting, Disbursement and ACSL | Head, Comptrollership | bankAccountNo, bankName, currency, dvNo, netAmount, payeeAccountNo, payeeName, valueDate | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_ATD_EMAIL | Authority to debit {{dvNo}} | Accounting, Disbursement and ACSL | Head, Comptrollership | currency, dvNo, instrumentNo, netAmount, payeeName | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_CHECK | Check | Accounting, Disbursement and ACSL | Head, Comptrollership | bankAccountNo, bankName, currency, dvNo, instrumentNo, netAmount, payeeName, printDate | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_CREDIT_TICKET | Credit ticket | Accounting, Disbursement and ACSL | Head, Comptrollership | bankAccountNo, bankName, currency, dvNo, netAmount, payeeAccountNo, payeeName | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_MC_DD | Manager's check / demand draft request | Accounting, Disbursement and ACSL | Head, Comptrollership | bankAccountNo, bankName, currency, dvNo, netAmount, payeeName | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_PAYMENT_ADVICE | Payment advice {{dvNo}} | Accounting, Disbursement and ACSL | Head, Comptrollership | currency, dvNo, instrumentText, mode, netAmount, payeeName, valueDate | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_TT | Telegraphic transfer | Accounting, Disbursement and ACSL | Head, Comptrollership | bankAccountNo, bankName, currency, dvNo, netAmount, payeeAccountNo, payeeBank, payeeName | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
DSB_VOUCHER | Disbursement voucher | Accounting, Disbursement and ACSL | Head, Comptrollership | currency, dvNo, mode, netAmount, payeeName, purpose, requestNo | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_COMPARATIVE | Comparative analysis - {{programmeName}} ({{policyYear}}) | Employee Benefits | Product Owner, Employee Benefits | aoName, comparativeNo, contactName, programmeName | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_FRANCHISE_ADVICE | Franchise outcome - {{programmeName}} | Employee Benefits | Product Owner, Employee Benefits | aoName, contactName, insurerName, outcome, programmeName, reasonText | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_FRANCHISE_REQUEST | Franchise request {{franchiseNo}} - {{clientName}} | Employee Benefits | Product Owner, Employee Benefits | aoName, clientName, dueDate, insurerName, lines | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_INDICATIVE_PROPOSAL | Indicative renewal terms - {{programmeName}} | Employee Benefits | Product Owner, Employee Benefits | aoName, contactName, incumbentName, policyYear, programmeName | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_ITEM_FOLLOWUP | Follow-up: {{itemType}} for {{programmeName}} | Employee Benefits | Product Owner, Employee Benefits | aoName, dueDate, followUpNo, itemType, programmeName, recipientName, subject | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_MEMBER_CHANGE_RELAY | Member change {{changeNo}} - {{clientName}} | Employee Benefits | Product Owner, Employee Benefits | aoName, clientName, insurerName, memberLines, policyNo, programmeName | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_RA_REMINDER | Reminder: renewal of {{programmeName}} | Employee Benefits | Product Owner, Employee Benefits | aoName, contactName, expiryDate, programmeName | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_RENEWAL_ADVICE | Renewal advice - {{programmeName}} ({{policyYear}}) | Employee Benefits | Product Owner, Employee Benefits | aoName, contactName, expiryDate, insurers, lines, programmeName, programmeNo | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_REVISION_RELAY | Revision request - {{clientName}} | Employee Benefits | Product Owner, Employee Benefits | aoName, dueDate, insurerName, proposalNo, revisionItems | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_RFP_COVER | Request for proposal {{requestNo}} - {{clientName}} | Employee Benefits | Product Owner, Employee Benefits | aoName, clientName, dueDate, insurerName, lines | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_SOA_RELEASE | Statement of account {{soaNo}} - {{programmeName}} | Employee Benefits | Product Owner, Employee Benefits | amount, aoName, contactName, insurerName, period, programmeName, soaNo | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_SUBMISSION_COVER | {{process}} documents - {{clientName}} | Employee Benefits | Product Owner, Employee Benefits | aoName, clientName, documents, insurerName, process, programmeName, remarks | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EB_TOR | Terms of Reference - {{programmeName}} ({{policyYear}}) | Employee Benefits | Product Owner, Employee Benefits | clientName, inceptionDate, lines, programmeNo, torItems, torVersion | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
ENDORSEMENT_SLIP | Endorsement slip | Operations | Head, Operations Services | arn, assured, effectiveDate, invoiceNo, policyNo, requestNo | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
EPOLICY_EMAIL | Your e-policy | New Business | Product Owner, BDOI (New Business) | clientName, insurerName, policyNo, reference | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
HOLD_COVER_REQUEST | Request for hold cover | New Business | Product Owner, BDOI (New Business) | reference, startDate | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
INSURANCE_ADVICE | Insurance advice | New Business | Product Owner, BDOI (New Business) | insurerName, mortgagee, periodFrom, periodTo, policyNo | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
PKG_ADVISORY | Package advisory | Product Maintenance | Product Owner, Marketing Business System (MBS) | effectiveFrom, productCode, productName, reference, versionNo | Template PM-08 (sheet PM-08 Document templates) | 16-Jul-2027 (T-24 weeks) |  | Not started
PKG_COMPARATIVE | Package comparative table | Product Maintenance | Product Owner, Marketing Business System (MBS) | reference, roundNo, variant | Template PM-08 (sheet PM-08 Document templates) | 16-Jul-2027 (T-24 weeks) |  | Not started
PKG_QUOTATION_SLIP | Package quotation slip | Product Maintenance | Product Owner, Marketing Business System (MBS) | reference, replyBy, roundNo | Template PM-08 (sheet PM-08 Document templates) | 16-Jul-2027 (T-24 weeks) |  | Not started
PKG_RENEWAL_ADVISORY | Package renewal advisory | Product Maintenance | Product Owner, Marketing Business System (MBS) | effectiveFrom, productCode, productName, reference, versionNo | Template PM-08 (sheet PM-08 Document templates) | 16-Jul-2027 (T-24 weeks) |  | Not started
PKG_REQUEST_FORM | Package request form | Product Maintenance | Product Owner, Marketing Business System (MBS) | reference, requestType, title | Template PM-08 (sheet PM-08 Document templates) | 16-Jul-2027 (T-24 weeks) |  | Not started
PKG_SLIP | Package slip | Product Maintenance | Product Owner, Marketing Business System (MBS) | reference, title | Template PM-08 (sheet PM-08 Document templates) | 16-Jul-2027 (T-24 weeks) |  | Not started
PLACEMENT_SLIP | Placement slip | New Business | Product Owner, BDOI (New Business) | reference | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
PRODRECON_COVER_LETTER | Production register for reconciliation | Operations | Head, Operations Services | bookingFrom, bookingTo, extractNo, insurerName, productionMonth, rowCount | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
PROPOSAL_SLIP | Proposal slip | New Business | Product Owner, BDOI (New Business) | clientName, reference | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
PRQ_LIQUIDATION | Cash Advance Liquidation Form | Accounting, Disbursement and ACSL | Head, Comptrollership | cashAdvanced, currency, liquidationNo, overShort, payeeName, requestNo, totalExpenses | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
PRQ_RFP | Request for Payment | Accounting, Disbursement and ACSL | Head, Comptrollership | amount, currency, mode, payeeName, purpose, requestDate, requestNo, rfpType | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
PRQ_RRF | Refund Request Form | Accounting, Disbursement and ACSL | Head, Comptrollership | amount, currency, mode, payeeName, reference, requestDate, requestNo, segment | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
QUOTATION_LETTER | Insurance quotation | New Business | Product Owner, BDOI (New Business) | clientName, productName, reference, validUntil | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
QUOTATION_SLIP | Quotation slip | New Business | Product Owner, BDOI (New Business) | reference, replyBy | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
QUOTATION_TERMS | Terms and conditions | New Business | Product Owner, BDOI (New Business) |  | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
REMITTANCE_PAYMENT_REQUEST | Payment request | Operations | Head, Operations Services | amount, approvedBy, currency, insurerName, reference | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
REMITTANCE_SCHEDULE | Remittance schedule | Operations | Head, Operations Services | incentiveNote, insurerName, reference, remittanceType | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_ACCOUNT_DETAILS | Renewal account details - {{renewalRef}} | Renewal | Product Owner, Renewal | asOf, clientName, expiringArn | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_INSURER_COVER | Renewals for your decision - batch {{batchNo}} | Renewal | Product Owner, Renewal | count, expiryFrom, expiryTo, insurerName, replyDue | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_NAL | Notice on your policy {{policyNo}} | Renewal | Product Owner, Renewal | aoName, clientName, expiryDate, insurerName, policyNo, renewalRef | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_NFR | Your policy {{policyNo}} will not be renewed | Renewal | Product Owner, Renewal | aoName, clientName, expiryDate, insurerName, policyNo, reason, renewalRef | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_NON_ACCEPTANCE | Your policy {{policyNo}} has expired | Renewal | Product Owner, Renewal | aoName, clientName, expiryDate, insurerName, policyNo, renewalRef | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_NRNS_REMINDER | Reminder: renewal of your policy {{policyNo}} | Renewal | Product Owner, Renewal | aoName, clientName, expiryDate, insurerName, policyNo, renewalRef | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_RA_FFY | Renewal Advice (first year free) - {{assuredName}} - policy {{policyNo}} | Renewal | Product Owner, Renewal | aoName, clientName, currency, expiryDate, grossPremium, insurerName, policyNo, renewalFrom, renewalRef, renewalTo, sumInsured | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_RA_FIRST | Renewal Advice - {{assuredName}} - policy {{policyNo}} | Renewal | Product Owner, Renewal | aoName, clientName, currency, expiryDate, grossPremium, insurerName, policyNo, productName, renewalFrom, renewalRef, renewalTo, sumInsured | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_RA_SECOND | Second notice: Renewal Advice - {{assuredName}} - policy {{policyNo}} | Renewal | Product Owner, Renewal | aoName, clientName, currency, expiryDate, grossPremium, insurerName, policyNo, renewalRef, sumInsured | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
RNW_SFU | Follow-up on the renewal of your mortgaged property - policy {{policyNo}} | Renewal | Product Owner, Renewal | aoName, clientName, expiryDate, policyNo, renewalRef | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
SBM_IAAF | Insurance Adequacy Assessment Form {{iaafNo}} | Submitted Policies | Product Owner, Submitted Policies | adequacy, assuredName, borrowerName, currency, expiryDate, iaafNo, inceptionDate, insurerName, links, policyNo, reviewCount, reviews, sbmNo, sumInsured | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
SBM_NO_TOUCH_BILLING | No Touch billing statement - {{insurerName}} - {{period}} | Submitted Policies | Product Owner, Submitted Policies | count, currency, grossFee, insurerName, netDue, period, vat, wtax | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
SBM_REMINDER | Reminder on your policy {{policyNo}} | Submitted Policies | Product Owner, Submitted Policies | assuredName, bankCounterpart, expiryDate, findings, insurerName, policyNo, sbmNo | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
SBM_RENEWAL_NOTICE | Renewal notice - policy {{policyNo}} | Submitted Policies | Product Owner, Submitted Policies | assuredName, expiryDate, insurerName, policyNo, riskDescription, sbmNo | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
SBM_RENEWAL_PROPOSAL | Renewal proposal - policy {{policyNo}} | Submitted Policies | Product Owner, Submitted Policies | assuredName, currency, expiryDate, policyNo, proposedInsurer, sbmNo, sumInsured | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
SBM_TOR | Terms of Reference {{torNo}} | Submitted Policies | Product Owner, Submitted Policies | accountRef, aoName, assuredName, breaches, currency, insurerName, proposedTerms, sumInsured, torNo | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
SERVICE_INVOICE_NOTE | Service invoice | New Business | Product Owner, BDOI (New Business) | creditDays, reference | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
VALIDATION_SLIP | Validation slip | New Business | Product Owner, BDOI (New Business) | invoiceNo, requestNo, status, validatedOn | This sheet | 16-Jul-2027 (T-24 weeks) |  | Not started
Note on A4: Template: Template code on Document Templates
Note on B4: Title: Title of the template
Note on C4: Module: Module that generates the document
Note on D4: Owner (BDOI unit): Unit that gives the wording and layout
Note on E4: Merge fields available: Fields BIBS fills in
Note on F4: Given in: Where the text is given
Note on G4: Due: Due date
Note on H4: BDOI layout attached: Y when the layout is sent
Note on I4: Status: Status of the row
Note on J4: BDOI comments: Decision, value or comment of the owner

## Accounting events
Review list: accounting events
← Back to Start here | The accounting events that need a rule of template D0-08 (accounting rules mapping); owner Head, Comptrollership
Event type | Name | Category | Journal type | Amount components | Given in | Status | BDOI comments
COMMISSION_ACCRUAL | Commission accrued | Commission | Commission | COMMISSION, WITHHOLDING_TAX, NET_COMMISSION | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_ADJ_COMMISSION | Commission adjustment without premium change | Commission | Commission | COMMISSION_RECEIVABLE, UNREALIZED_COMMISSION, DEFERRED_OUTPUT_VAT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_INCENTIVE_ACCRUE | Incentive earned from insurer | Commission | Commission | INCENTIVE | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_INCENTIVE_PASS_ON | Incentive pass-on to branches | Commission | Commission | PASS_ON | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_REMIT_CPC2 | CPC2 incentive per remittance batch | Commission | Commission | GROSS, CPC2_INCOME, OUTPUT_VAT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_REMIT_INCENTIVE | Early remittance incentive | Commission | Commission | DUE_FOR_DISBURSEMENT, INCENTIVE_INCOME, OUTPUT_VAT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
ASSET_ACQUISITION | Fixed asset capitalized | Payment | Payment | COST | Template D0-08 (sheet D0-08 Accounting rules) | Not started
COMMISSION_PAYMENT | Commission payment | Payment | Payment | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
DISB_CHECK_NEGOTIATED | Check negotiated | Payment | Payment | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
DISB_CHECK_STALE | Check staled | Payment | Payment | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
DISB_VOUCHER | Disbursement voucher approved | Payment | Payment | REMITTANCE, REFUND, REFUND_FROM_INSURER, SUPPLIER, GOVERNMENT, OTHER_BANK_UNIT, EMPLOYEE, CASH_ADVANCE, SERVICE_FEE, PASS_ON, STALE_REISSUE, OTHER, PAID, EWT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
FRBS_SERVICE_FEE_ACCRUE | Service fee accrual | Payment | Payment | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
MISC_PAYMENT | Miscellaneous payment | Payment | Payment | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_REMITTANCE | Remittance to insurer | Payment | Payment | DTIP, CWT, COMMISSION_RECEIVABLE, DUE_FOR_DISBURSEMENT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_REMIT_DEDUCTION | Remittance deduction on insurer confirmation | Payment | Payment | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
PDC_ISSUED_PRESENTED | Issued PDC presented | Payment | Payment | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
PETTY_CASH_EXPENSE | Petty cash disbursement | Payment | Payment | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
PETTY_CASH_REPLENISHMENT | Petty cash reimbursement | Payment | Payment | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
PREMIUM_REFUND_PAYMENT | Premium refund payment | Payment | Payment | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
PRQ_CA_LIQUIDATION | Cash advance liquidation | Payment | Payment | PER_DIEM, REPRESENTATION, TRANSPORT, LODGING, OTHER, CASH_RETURNED, SHORTAGE, ADVANCE | Template D0-08 (sheet D0-08 Accounting rules) | Not started
SUPPLIER_INVOICE | Supplier invoice | Payment | Payment | NET_AMOUNT, INPUT_VAT, WITHHOLDING_TAX, PAYABLE | Template D0-08 (sheet D0-08 Accounting rules) | Not started
SUPPLIER_PAYMENT | Supplier payment | Payment | Payment | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
TAX_REMITTANCE | Tax remittance | Payment | Payment | TAX_PAYABLE, TAX_CREDIT, AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
BROKER_BOOKING | Broker booking | Premium | Premium | PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER, DTIP, COMMISSION_RECEIVABLE, UNREALIZED_COMMISSION, DEFERRED_OUTPUT_VAT, COMMISSION_INCOME, OUTPUT_VAT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
MIG_LEGACY_INVOICE_OPENING | Legacy invoice opening | Premium | Opening | LG_PR_BASIC, LG_PR_DST, LG_PR_PTX_VAT, LG_PR_LGT, LG_PR_FST, LG_PR_OTHER, LG_PR2307, LG_DTIP, LG_COMMISSION, LG_COMMISSION_VAT, LG_UNREALIZED, LG_DEFERRED_VAT, CLEARING | Template D0-08 (sheet D0-08 Accounting rules) | Not started
MIG_LEGACY_POSITION_TRUEUP | Legacy open-item adjustment | Premium | Opening | LG_PR_BASIC, LG_PR_DST, LG_PR_PTX_VAT, LG_PR_LGT, LG_PR_FST, LG_PR_OTHER, LG_PR2307, LG_DTIP, LG_COMMISSION, LG_COMMISSION_VAT, LG_UNREALIZED, LG_DEFERRED_VAT, LG_AMOUNT, CLEARING | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_AR_INSURER_SETUP | AR Insurer set-up after a remitted decrease | Premium | Premium | AR_INSURER | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_WRITE_OFF | Minimal balance write-off / credit | Premium | Premium | WRITE_OFF, PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER, CREDIT_BALANCE | Template D0-08 (sheet D0-08 Accounting rules) | Not started
ASSET_DEPRECIATION | Monthly depreciation | Provision | Provision | DEPRECIATION | Template D0-08 (sheet D0-08 Accounting rules) | Not started
ASSET_TAKE_ON | Fixed asset opening balance | Provision | Opening | COST, ACCUMULATED_DEPRECIATION, NET_BOOK_VALUE | Template D0-08 (sheet D0-08 Accounting rules) | Not started
ASSET_TRANSFER | Inter-branch asset transfer | Provision | Provision | COST, ACCUMULATED_DEPRECIATION, NET_BOOK_VALUE | Template D0-08 (sheet D0-08 Accounting rules) | Not started
ASSET_DISPOSAL | Fixed asset disposal | Receipt | Receipt | COST, ACCUMULATED_DEPRECIATION, PROCEEDS, GAIN, LOSS | Template D0-08 (sheet D0-08 Accounting rules) | Not started
MIG_UPP_OPENING | Legacy unapplied payment opening | Receipt | Opening | LG_AMOUNT, CLEARING | Template D0-08 (sheet D0-08 Accounting rules) | Not started
MISC_RECEIPT | Miscellaneous receipt | Receipt | Receipt | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_AR_INSURANCE_RECEIPT | Insurer non-premium receipt | Receipt | Receipt | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_AR_RECEIPT | Acknowledgement receipt (premium) | Receipt | Receipt | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_CWT_DTIP_OFFSET | 2307 certificate offset against DTIP | Receipt | Receipt | DTIP, PR2307 | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_CWT_RECLASS | PR reclassified to the client 2307 | Receipt | Receipt | PR2307, PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_DP_COMMISSION_COLLECT | Direct payment commission collected | Receipt | Receipt | CASH, CWT, COMMISSION_RECEIVABLE, REALIZED_COMMISSION, REALIZED_VAT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_DP_PR_REVERSAL | Direct payment PR reversal | Receipt | Receipt | DTIP, PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_DP_REINSTATE | Direct payment reinstatement | Receipt | Receipt | DTIP, PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_EXCESS_TO_OVERAGES | Minimal excess to AP overages | Receipt | Receipt | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_MINIMAL_BALANCE_REVERSAL | Premium minimal balance reversal | Receipt | Receipt | TOTAL, PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_OR_ISSUE | Official receipt issued | Receipt | Receipt | CASH, CWT, SERVICE_FEE_INCOME, PROFIT_SHARE_INCOME, INCENTIVE_INCOME, OTHER_INCOME, OUTPUT_VAT, COMMISSION_COLLECTED, VAT_DUE | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_PAYMENT_APPLY | Payment applied to a booked invoice | Receipt | Receipt | APPLIED, PR_BASIC, PR_DST, PR_PTX_VAT, PR_LGT, PR_FST, PR_OTHER, REALIZED_COMMISSION, REALIZED_VAT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_RECEIPT_REINSTATE | Receipt reinstated | Receipt | Receipt | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_UNAPPLIED_RECLASS | Unapplied payment reclassified | Receipt | Receipt | RELEASED, ASSIGNED | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_UNAPPLIED_REFUND | Unapplied payment refunded | Receipt | Receipt | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
OPS_UNAPPLIED_TO_INCOME | Unapplied payment reclassified to other income | Receipt | Receipt | AMOUNT, LG_AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
PREMIUM_DEPOSIT | Unapplied collection | Receipt | Receipt | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
PREMIUM_RECEIPT | Premium collection | Receipt | Receipt | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
SBM_HANDLING_FEE | Handling fee recognised | Receipt | Receipt | AMOUNT, INCOME, OUTPUT_VAT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
SBM_NO_TOUCH_FEE | No Touch service fee billed | Receipt | Receipt | RECEIVABLE, INCOME, OUTPUT_VAT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
TAX_CWT_CERT_RECEIVED | Insurer 2307 certificate received | Receipt | Receipt | COMMISSION_CWT, INCENTIVE_CWT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
UNAPPLIED_APPLICATION | Application of unapplied collection | Receipt | Receipt | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
BANK_TRANSFER | Bank transfer | Treasury | Payment | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
DISB_FUND_TRANSFER | Account funding transfer | Treasury | Payment | AMOUNT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
INVESTMENT_AMORTIZATION | Premium / discount amortization | Treasury | Investment | AMORTIZATION | Template D0-08 (sheet D0-08 Accounting rules) | Not started
INVESTMENT_FAIR_VALUE | Investment fair value change | Treasury | Revaluation | FAIR_VALUE_CHANGE | Template D0-08 (sheet D0-08 Accounting rules) | Not started
INVESTMENT_INTEREST_ACCRUAL | Investment interest accrual | Treasury | Investment | INTEREST | Template D0-08 (sheet D0-08 Accounting rules) | Not started
INVESTMENT_INTEREST_RECEIPT | Coupon / interest received | Treasury | Investment | CASH, FINAL_TAX, ACCRUED_INTEREST, INCOME_ADJUSTMENT | Template D0-08 (sheet D0-08 Accounting rules) | Not started
INVESTMENT_MATURITY | Investment maturity | Treasury | Investment | PROCEEDS, FINAL_TAX, FV_RESERVE, CARRYING_AMOUNT, ACCRUED_INTEREST, REALIZED_GAIN | Template D0-08 (sheet D0-08 Accounting rules) | Not started
INVESTMENT_PURCHASE | Investment purchase | Treasury | Investment | COST, PURCHASED_INTEREST, TOTAL | Template D0-08 (sheet D0-08 Accounting rules) | Not started
INVESTMENT_SALE | Investment sale | Treasury | Investment | PROCEEDS, FINAL_TAX, FV_RESERVE, CARRYING_AMOUNT, ACCRUED_INTEREST, REALIZED_GAIN | Template D0-08 (sheet D0-08 Accounting rules) | Not started
INVESTMENT_TAKE_ON | Investment opening balance | Treasury | Opening | CARRYING_AMOUNT, ACCRUED_INTEREST, TOTAL | Template D0-08 (sheet D0-08 Accounting rules) | Not started
Note on A4: Event type: Accounting event of the platform
Note on B4: Name: Name of the event
Note on C4: Category: Category
Note on D4: Journal type: Journal type of the entries
Note on E4: Amount components: Amounts the rule lines can post
Note on F4: Given in: Template of the rules
Note on G4: Status: Status of the row
Note on H4: BDOI comments: Decision, value or comment of the owner

## Configured on screens
Datasets configured on screens
← Back to Start here | Set-up that BDOI decides and the BIBS configuration team enters on the named screen in a working session; there is no template to fill in, the decisions go into BDOI comments
ID | Dataset | What BDOI decides or provides | BRD | Owner (BDOI unit) | Configured on | Due | Status | BDOI comments
CFG-006 | Cost-centre rules | Which cost centre an automatic posting takes by module, event, branch, party or account | BRD-05 | Head, Comptrollership | Setup & Administration › Setup › Cost-Centre Rules | 16-Jul-2027 – Values for UAT | Not started
CFG-008 | Production targets | The 2028 production targets per sales unit and officer for the New Business reports | BRD-01 | Product Owner, BDOI (New Business) | Reports › New Business Reports › Production Targets | 16-Jul-2027 – Values for UAT | Not started
CFG-009 | Financial year and periods | Financial year 2028 and its periods, opened by Comptrollership; FY2027 stays in legacy (year-end option A) | BRD-05 | Head, Comptrollership | Finance › General Ledger › Financial Periods | 1-Nov-2027 – Production values before the dress rehearsal | Not started
CFG-026 | Financial statement formats and account schedules | The lines of the financial statements and MIS formats and the accounts in each, as Comptrollership reports them | BRD-05 | Head, Comptrollership | Finance › Accounting Reports › Account Schedules | 16-Jul-2027 – Values for UAT | Not started
CFG-027 | Recurring journals | The monthly accruals and allocations Comptrollership posts as recurring journals from January 2028 | BRD-05 | Head, Comptrollership | Finance › General Ledger › Recurring Journals | 1-Nov-2027 – Production values before the dress rehearsal | Not started
CFG-028 | Asset categories | Fixed-asset categories with their useful life, method and accounts | BRD-05 | Head, Comptrollership | Finance › Assets & Investments › Asset Categories | 16-Jul-2027 – Values for UAT | Not started
CFG-029 | Investment portfolios | The investment portfolios and their accounts, when BDOI keeps investments in BIBS | BRD-05 | Head, Comptrollership | Finance › Assets & Investments › Investment Portfolios | 16-Jul-2027 – Values for UAT | Not started
CFG-030 | GL-SL reconciliation controls (ACSL) | The control accounts reconciled against their sub-ledgers and the tolerance of each | BRD-05 | Head, Comptrollership | Finance › ACSL › GL-SL Reconciliation | 16-Jul-2027 – Values for UAT | Not started
CFG-031 | Service fee rates | The service fee rates per segment and their recipients | BRD-05 | Head, Comptrollership | Finance › Accounting Reports › Service Fee Rates | 16-Jul-2027 – Values for UAT | Not started
CFG-044 | Payment file layouts of the collection channels | Confirmation of the payment files received from Bills Payment, Trade, Direct Credit, CLPC and PMS and their field names | BRD-02 | Head, Operations Services | Finance › Cashiering › Cashiering Setup | 16-Jul-2027 – Values for UAT | Not started
CFG-072 | Exception codes and alert thresholds | Which exceptions raise an alert, with their severity and the amount or day threshold of each | BRD-00 | BDOI IT | Setup & Administration › Administration › Exception Codes | 16-Jul-2027 – Values for UAT | Not started
CFG-073 | Scheduled job times | The run time of each daily and monthly job in Philippine time, and the blackout windows | BRD-00 | BDOI IT | Setup & Administration › Administration › Scheduled Jobs | 16-Jul-2027 – Values for UAT | Not started
CFG-074 | Data retention rules | Years online and in the archive per record type, and the action at the end, as Compliance sets them | BRD-10 | Compliance | Setup & Administration › Broking Setup › Data Retention | 16-Jul-2027 – Values for UAT | Not started
CFG-075 | Directory sign-in and provisioning (EIAM, UIDM-ISC) | The sign-in mode, the EIAM tenant and claims, and the UIDM-ISC option (clarifications CLR-UA-01 and CLR-UA-03) | BRD-00 | BDOI IT | Setup & Administration › Administration › System Parameters | 1-Dec-2026 – Drafts with the Drop 0 sign-off | Not started
CFG-083 | Screening forms and STR layout | The screening forms and the STR report layout Compliance submits | BRD-10 | Compliance | Setup & Administration › Compliance Setup › Templates | 16-Jul-2027 – Values for UAT | Not started
CFG-102 | Business partners other than insurers (suppliers, service providers) | Suppliers and other partners paid through Payables, with TIN, address and bank details | BRD-05 | Head, Comptrollership | Setup & Administration › Setup › Business Partners | 16-Jul-2027 – Values for UAT | Not started
CFG-104 | Insurer location references (claims) | The claim location references of each insurer, entered or uploaded on Insurer Location References | BRD-07 | Product Owner, Claims | Claims & Insurance › Claims Handling › Insurer Location References | 16-Jul-2027 – Values for UAT | Not started
CFG-115 | User scope of Submitted Policies | The segments and units each Submitted Policies user may see | BRD-12 | Product Owner, Submitted Policies | Client & Policy › Submitted Policies › Submitted Policies Setup | 16-Jul-2027 – Values for UAT | Not started
CFG-120 | Booking rules and incentive rules | The automatic booking rules and the booking incentive rules | BRD-01 | Product Owner, BDOI (New Business) | Client & Policy › Booking › Booking Setup | 16-Jul-2027 – Values for UAT | Not started
CFG-121 | Remittance incentive rules | The incentive deductions applied at remittance | BRD-02 | Head, Operations Services | Finance › Remittance › Incentive Rules | 16-Jul-2027 – Values for UAT | Not started
CFG-122 | Commission incentive schemes | The commission incentive schemes and their rates | BRD-04 | VP and Head, BDOI Operations (Collections) | Finance › Commission Receivables › Incentive Schemes | 16-Jul-2027 – Values for UAT | Not started
CFG-123 | Collections assignment and escalation rules | How accounts are assigned to collectors and when they escalate to the team lead and the unit head | BRD-04 | VP and Head, BDOI Operations (Collections) | Finance › Collections › Collections Setup | 16-Jul-2027 – Values for UAT | Not started
CFG-124 | Renewal buckets and decision matrix | The renewal bucket rules, the decision matrix and the non-renewable risk codes | BRD-06 | Product Owner, Renewal | Client & Policy › Renewal › Renewal Setup | 16-Jul-2027 – Values for UAT | Not started
CFG-125 | Submitted Policies rules, limits and letters | The processing rules, insurer rules and limits, and the letter rules of Submitted Policies | BRD-12 | Product Owner, Submitted Policies | Client & Policy › Submitted Policies › Submitted Policies Setup | 16-Jul-2027 – Values for UAT | Not started
CFG-126 | Screening configuration | Match rules, risk categories and rules, assignment, service levels and validation rules of Sanction Screening | BRD-10 | Compliance | Setup & Administration › Compliance Setup › Configuration Versions | 16-Jul-2027 – Values for UAT | Not started
CFG-127 | Watchlist sources and entries | The sanctions and PEP list sources, their load schedule and the first load | BRD-10 | Compliance | Setup & Administration › Compliance Setup › List Sources and Runs | 16-Jul-2027 – Values for UAT | Not started
CFG-128 | Employee Benefits set-up | The required documents per process and the other Employee Benefits settings | BRD-08 | Product Owner, Employee Benefits | Client & Policy › Employee Benefits › EB Setup | 16-Jul-2027 – Values for UAT | Not started
CFG-129 | Claims handlers and set-up | The claims handlers per unit and the Claims settings | BRD-07 | Product Owner, Claims | Claims & Insurance › Claims Handling › Claims Setup | 16-Jul-2027 – Values for UAT | Not started
CFG-130 | Production reconciliation extract schedules | The insurers and the schedule of the production extracts sent for reconciliation | BRD-02 | Head, Operations Services | Client & Policy › Production Reconciliation › Extract Schedules | 16-Jul-2027 – Values for UAT | Not started
CFG-131 | New Business report variants | The report variants the units use | BRD-01 | Product Owner, BDOI (New Business) | Reports › New Business Reports › New Business Reports | 16-Jul-2027 – Values for UAT | Not started
Note on A4: ID: Configuration item of the Drop 0 register
Note on B4: Dataset: What is configured
Note on C4: What BDOI decides or provides: Content of the set-up
Note on D4: BRD: BRD
Note on E4: Owner (BDOI unit): Unit that decides
Note on F4: Configured on: Screen of BIBS
Note on G4: Due: Due date
Note on H4: Status: Status of the item
Note on I4: BDOI comments: Decisions and values of the owner

## Gaps
Gaps
← Back to Start here | Datasets whose template rows the platform cannot take by file (keyed on the screen from the filled-in template), and data BDOI may need that BIBS does not hold (asked as a question in the BDOI Requirements and Inputs workbook)
Kind of gap | Template or question | Dataset | BRD | Provided by | Keyed on | Columns | Mandatory | Due | How the rows get into BIBS, or what is asked
No upload route: keyed on the screen from the template | D0-02 | Branches | BRD-05 | Head, Comptrollership | Setup & Administration › Setup › Branches | 12 | 5 | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | D0-04 | Cost centres and business lines | BRD-05 | Head, Comptrollership | Setup & Administration › Setup › Dimensions | 4 | 4 | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | D0-07 | Account categories and numbering | BRD-05 | Head, Comptrollership | Finance › General Ledger › Chart of Accounts | 8 | 1 | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | MD-02 | Currencies | BRD-05 | Head, Comptrollership (Treasury) | Setup & Administration › Setup › Currencies & Rates | 5 | 4 | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | PM-09 | Lists of values and parameters | BRD-03 | Product Owner, MBS; System Administrator (entry) | Setup & Administration › Broking Setup › Lists of Values | 5 | 2 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | UA-02 | Role-to-permission matrix | BRD-11 | Business Administration with the unit heads; reviewed and signed by BDOI Information Security | Setup & Administration › User Access › Group Profile Requests | 8 | 6 | 9-Apr-2027 – Reference data for Trial migration 1 (M4) | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | UA-06 | Lists of values | BRD-11 | Business Administration | Lists of Values (New Business set) under maker-checker | 5 | 4 | 1-Nov-2027 – before the templates that use its codes | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | D0-05 | Employees | BRD-05 | Human Resources; Head, Comptrollership | Setup & Administration › Setup › Employees | 7 | 4 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | MD-01 | Business partners (reinsurers, intermediaries, suppliers) | BRD-05 | Head, Comptrollership; Head, Operations for the reinsurers and intermediaries | Setup & Administration › Setup › Business Partners | 14 | 4 | 9-Apr-2027 – Reference data for Trial migration 1 (M4) | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | D0-03 | Holiday calendar | BRD-05 | Head, Comptrollership; Human Resources | Setup & Administration › Setup › Holiday Calendar | 3 | 2 | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | MD-03 | Exchange rates and their source | BRD-05 | Head, Comptrollership (Treasury) | Setup & Administration › Setup › Currencies & Rates | 4 | 4 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | UA-04 | Separation-of-duties rules | BRD-11 | BDOI Information Security | Setup & Administration › User Access › Separation of Duties | 7 | 4 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | D0-10 | Tax codes | BRD-05 | Head, Comptrollership (Tax) | Finance › Tax & Statutory › Tax Codes & Forms | 10 | 6 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | D0-11 | Company bank accounts | BRD-05 | Head, Comptrollership; Treasury | Finance › Disbursement › Bank Accounts and Checks | 9 | 7 | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | D0-01 | Company | BRD-05 | Head, Comptrollership | Setup & Administration › Setup › Companies | 9 | 9 | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | D0-08 | Accounting rules | BRD-05 | Head, Comptrollership | Finance › Accounting Engine › Accounting Rules | 10 | 7 | 4-Jan-2027 – Platform set-up for Drop 1 SIT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | D0-09 | Legacy control accounts | BRD-05 | Head, Comptrollership | Finance › General Ledger › Chart of Accounts | 5 | 2 | 1-Dec-2026 – Drafts with the Drop 0 sign-off | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | D0-15 | Approval limits and matrices | BRD-00 | Owners of the modules; Head, Comptrollership for the amounts | Submitted Policies Setup, EB Setup, Compliance Setup (Configuration Versions) and Disbursement approver routing | 9 | 4 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | TX-02 | Tax forms and filing calendar | BRD-05 | Head, Comptrollership (Tax) | Finance › Tax & Statutory › Tax Codes & Forms | 10 | 8 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | UA-03 | Approvers, approval rules and limits | BRD-11 | Business Administration; BDOI Information Security for the second approval; Comptrollership for the authorisation limits | Setup & Administration › User Access › New Request | 6 | 3 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | PM-02 | Coverages, perils and field rules | BRD-03 | MBS | Client & Policy › Product Maintenance › Coverages & Clauses | 9 | 6 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | PM-03 | Clause library | BRD-03 | TSU (wordings); MBS (maintenance) | Client & Policy › Product Maintenance › Coverages & Clauses | 6 | 5 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | D0-12 | Check books | BRD-05 | Treasury; Product Owner, Comptrollership - Disbursement | Finance › Disbursement › Bank Accounts and Checks | 5 | 5 | 1-Nov-2027 – Production values before the dress rehearsal | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | D0-13 | Petty cash funds | BRD-05 | Head, Comptrollership | Finance › Payables & Cash › Petty Cash | 8 | 8 | 1-Nov-2027 – Production values before the dress rehearsal | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | D0-14 | Bank statement layouts | BRD-05 | Head, Comptrollership; Treasury | Setup & Administration › Setup › Bank Statement Layouts | 10 | 5 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | PM-04 | Rate tables | BRD-03 | Product Owner, MBS; Comptrollership (taxes) | Client & Policy › Product Maintenance › Rates & Taxes | 7 | 2 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | PM-10 | Incentive criteria | BRD-03 | Incentive Maintenance user (MBS); Comptrollership (CPC2 definition, PQ04) | Client & Policy › Product Maintenance › Incentive Criteria | 6 | 5 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | TX-01 | Party tax profiles (clients, insurers, payees) | BRD-05 | Head, Comptrollership (Tax) | Finance › Tax & Statutory › Party Tax Profiles | 12 | 4 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | PM-06 | Packages in force at go-live | BRD-03 | TSU (prepares); Product Owner, MBS (approves) | Client & Policy › Product Maintenance › New Package Request | 9 | 9 | 1-Nov-2027 – Production values before the dress rehearsal | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | PM-08 | Document templates | BRD-03 | TSU and MBS (texts); Business Administrator (maintenance) | Setup & Administration › Broking Setup › Document Templates | 5 | 4 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
No upload route: keyed on the screen from the template | UA-05 | Password, session and sign-in parameters | BRD-11 | BDOI Information Security; BDOI IT for the sign-in mode | Setup & Administration › Administration › System Parameters | 5 | 4 | 16-Jul-2027 – Values for UAT | Configuration screen – upload on the screen (being added; until then BDOI fills this template and it is loaded on the screen with maker-checker)
Not held by BIBS: question to BDOI | TX-Q04 | CTPL COCAF / LTO authentication fee | BRD-03 | Accounting Head / Controller | - |  |  | 30-Nov-2026 | No field: BIBS has no charge other than the taxes above. Question TX-Q04 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | TX-Q04 | Notarial fee | BRD-03 | Accounting Head / Controller | - |  |  | 30-Nov-2026 | No field. Question TX-Q04 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | TX-Q04 | Policy or documentation fee | BRD-03 | Accounting Head / Controller | - |  |  | 30-Nov-2026 | No field. Question TX-Q04 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | TX-Q04 | Any other charge BDOI bills | BRD-03 | Accounting Head / Controller | - |  |  | 30-Nov-2026 | No field. Question TX-Q04 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | TX-Q06 | Government payors (final VAT and EWT withheld) | BRD-05 | Accounting Head / Controller | - |  |  | 30-Nov-2026 | BIBS has no final VAT or final withholding tax type and no government-payor flag on the client. Question TX-Q06 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | TX-Q09 | Top withholding agent clients | BRD-01 | Accounting Head / Controller | - |  |  | 30-Nov-2026 | Withholding by a client is recorded as a 2307 received; BIBS has no top withholding agent flag on the client. Question TX-Q09 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | TX-Q06 | Final tax on bank interest | BRD-05 | Accounting Head / Controller | - |  |  | 30-Nov-2026 | BIBS has no final withholding tax type; bank interest is posted by journal. Question TX-Q06 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | TX-Q06 | Percentage tax on BDOI's own receipts | BRD-05 | Accounting Head / Controller | - |  |  | 30-Nov-2026 | The premium tax type is a charge on premiums; BIBS has no percentage tax on BDOI's own receipts. Question TX-Q06 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | TX-Q09 | Tax exemption certificates of clients | BRD-01 | Accounting Head / Controller | - |  |  | 30-Nov-2026 | BIBS keeps no exemption certificate number or validity. Question TX-Q09 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | TX-Q08 | Company tax registration | BRD-05 | Accounting Head / Controller | - |  |  | 30-Nov-2026 | BIBS keeps the TIN with its branch code (D0-01) only; no RDO, VAT registration, CAS or e-invoicing permit. Question TX-Q08 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | MD-Q02 | Geographic master (province, city / municipality, barangay, ZIP) and the LGU of the LGT | BRD-01 | Product Owner, New Business | - |  |  | 30-Nov-2026 | Addresses are free text (address, city, province, postal code); LGT follows the insurer branch rate (R04B), not the LGU Question MD-Q02 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | MD-Q03 | Motor vehicle master (make, model, body type, FMV / depreciation schedule) | BRD-01 | Product Owner, New Business | - |  |  | 30-Nov-2026 | Make and model are free text; motor rating uses the sum insured, the own damage factor and the rate, with no FMV or depreciation schedule Question MD-Q03 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | MD-Q04 | Industry codes (PSIC) | BRD-10 | Compliance Officer | - |  |  | 30-Nov-2026 | No industry field on the client Question MD-Q04 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | MD-Q04 | Countries and nationalities for KYC / AML | BRD-10 | Compliance Officer | - |  |  | 30-Nov-2026 | Nationality is a list; there is no country list for addresses or residence Question MD-Q04 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | MD-Q05 | Authorised signatories for letters, checks and BIR forms | BRD-00 | Accounting Head / Controller | - |  |  | 16-Jul-2027 | Documents print signature lines; there is no signatory master for checks, letters and BIR forms Question MD-Q05 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | MD-Q06 | Report recipients and schedules | BRD-00 | BIBS Product Owner | - |  |  | 30-Nov-2026 | No report subscription: reports are run on demand except the production reconciliation extracts Question MD-Q06 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | MD-Q07 | E-mail and SMS sender settings | BRD-00 | BDOI IT | - |  |  | 31-Jan-2027 | E-mail sender and fixed recipients are parameters; BIBS sends no SMS Question MD-Q07 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | MD-Q08 | Insurer contacts | BRD-03 | Operations Head | - |  |  | 30-Nov-2026 | No contact persons per insurer Question MD-Q08 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | TX-Q04 | Premium charges (DST, premium tax, VAT, FST, LGT, VAT on commission) and other charges | BRD-03 | Accounting Head / Controller | - |  |  | 30-Nov-2026 | Other charges (COCAF / LTO authentication, notarial, documentation fees) have no field Question TX-Q04 of the BDOI Requirements and Inputs workbook.
Not held by BIBS: question to BDOI | TX-Q06 | BDOI's own taxes, tax profiles and tax forms | BRD-05 | Accounting Head / Controller | - |  |  | 30-Nov-2026 | No final tax type, no government / top withholding agent flags, no exemption certificates Question TX-Q06 of the BDOI Requirements and Inputs workbook.
Note on A4: Kind of gap: No upload route, or not held by BIBS
Note on B4: Template or question: Template of this workbook, or Ref of the question
Note on C4: Dataset: Dataset
Note on D4: BRD: BRD
Note on E4: Provided by: Who fills in the template
Note on F4: Keyed on: Screen where the rows are entered
Note on G4: Columns: Columns of the template
Note on H4: Mandatory: Mandatory columns
Note on I4: Due: Due date of the template
Note on J4: How the rows get into BIBS, or what is asked: Handling of the dataset

## Coverage check
Coverage check
← Back to Start here | The datasets the product owner asked about and where each is in this workbook, or why BIBS does not hold it
Dataset | Where it is in this workbook | Held by BIBS | Note | Question
Currencies and exchange-rate source | MD-02 Currencies; MD-03 Exchange rates | Yes | Four rate types (spot, closing, average, budget); the source and owner of the daily rate is a question | MD-Q01
Geographic master (province, city / municipality, barangay, ZIP) and the LGU of the LGT | Not held | No | Addresses are free text (address, city, province, postal code); LGT follows the insurer branch rate (R04B), not the LGU | MD-Q02
Motor vehicle master (make, model, body type, FMV / depreciation schedule) | Lists of values: VEHICLE_BODY_TYPE | Partly | Make and model are free text; motor rating uses the sum insured, the own damage factor and the rate, with no FMV or depreciation schedule | MD-Q03
Fire occupancy and construction class codes | Lists of values: OCCUPANCY, CONSTRUCTION_CLASS | Yes | Values given on the sheet Lists of values | -
Industry codes (PSIC) | Not held | No | No industry field on the client | MD-Q04
Countries and nationalities for KYC / AML | Lists of values: NATIONALITY | Partly | Nationality is a list; there is no country list for addresses or residence | MD-Q04
AML risk rating matrix | Lists of values: KYC_RISK_RATING; Configured on screens: CFG-126 Screening configuration | Yes | Risk categories and rules are set on Compliance Setup › Configuration Versions | -
KYC document checklist by client type | Lists of values: KYC_DOCS_INDIVIDUAL, KYC_DOCS_CORPORATE, ID_TYPE | Yes | - | -
Authorised signatories for letters, checks and BIR forms | D0-15 (signatory title of the approval matrices) | Partly | Documents print signature lines; there is no signatory master for checks, letters and BIR forms | MD-Q05
Report recipients and schedules | Configured on screens: CFG-130; System parameters (job failure recipients) | Partly | No report subscription: reports are run on demand except the production reconciliation extracts | MD-Q06
E-mail and SMS sender settings | System parameters (Messaging: sender address, fixed recipients) | Partly | E-mail sender and fixed recipients are parameters; BIBS sends no SMS | MD-Q07
Data retention schedule | Configured on screens: CFG-074 Data retention rules | Yes | - | -
Adjusters and surveyors | Lists of values: BCL_ADJUSTER; MD-01 (type Surveyor or adjuster) | Yes | - | -
Insurer contacts | R04 placement e-mail; R04B branch e-mail | Partly | No contact persons per insurer | MD-Q08
Premium charges (DST, premium tax, VAT, FST, LGT, VAT on commission) and other charges | PM-04 with its charges checklist; R04B LGT | Partly | Other charges (COCAF / LTO authentication, notarial, documentation fees) have no field | TX-Q04
BDOI's own taxes, tax profiles and tax forms | D0-10 with its tax checklist; TX-01; TX-02 | Partly | No final tax type, no government / top withholding agent flags, no exemption certificates | TX-Q06
Note on A4: Dataset: Dataset asked about
Note on B4: Where it is in this workbook: Template, list or sheet
Note on C4: Held by BIBS: Yes, Partly or No
Note on D4: Note: What BIBS keeps and what it does not
Note on E4: Question: Ref of the question in the BDOI Requirements and Inputs workbook

## Reference lists
Reference lists
← Back to Start here | Every list of allowed values used by the drop-downs, with its code and label. A drop-down accepts the codes of its list.
List | Used in | Code | Label | Note
Yes or no (YES_NO) | D0-02 Branches: Head office D0-02 Branches: Foreign currency authorised D0-04 Dimensions: Active D0-07 Categories and numbering: Bank category MD-02 Currencies: Active R01 Lists of values and MIS val: active_flag D0-06 Chart of accounts: Control Account D0-06 Chart of accounts: Manual Posting D0-06 Chart of accounts: Cost Centre Required D0-06 Chart of accounts: Revaluation Required R03 Sales organisation (units a: active_flag R05 Product lines, cover types,: packaged_flag R02 Branches and invoicing bran: invoicing_branch_flag R02 Branches and invoicing bran: active_flag UP-01 Clients (upload): Bank Client C01 Client master: bank_client_flag PM-01 Product catalogue: Package PM-01 Product catalogue: Fleet PM-01 Product catalogue: Mortgage related PM-01 Product catalogue: Direct payment allowed PM-01 Product catalogue: Free First Year R08 Chart of accounts mapping: branch_specific_flag UA-03 Approval rules: Any approver may decide PM-02 Coverages and rules: Basic PM-02 Coverages and rules: Mandatory C02 Client addresses and contac: primary_flag C03 Client payout accounts: active_flag Notification events: In-app wanted Notification events: E-mail wanted Document templates: BDOI layout attached | Y | Yes
|  | N | No
Market segment (MARKET_SEGMENT) | PM-01 Product catalogue: Market segments | CBG | Consumer Banking Group (CBG) | The values of the list MARKET_SEGMENT as delivered with BIBS; a new value is added with its template and may then be used here.
|  | COMBANK | Commercial Banking
|  | CORBANK | Corporate Banking
|  | RETAIL | Retail Marketing
|  | INSTITUTIONAL | Institutional Banking / SM / BDO accounts
Placement after (PLACEMENT_GATE) | PM-01 Product catalogue: Placement after | PAID | Premium paid
|  | CLIENT_CONFIRMATION | Client confirmation
TSU review (TSU_REVIEW) | PM-01 Product catalogue: TSU review | BY_RULES | By the review rules
|  | ALWAYS | Always
|  | NEVER | Never
Coverage and rule record (CI02_RECORD) | PM-02 Coverages and rules: Record | COVERAGE | Coverage or peril of a line
|  | FIELD_RULE | Field an account of the product needs
|  | DOCUMENT_RULE | Document an account of the product needs
Document type (DOCUMENT_TYPE) | PM-02 Coverages and rules: Document type | IDF | Insurance Declaration Form (IDF) | The values of the list DOCUMENT_TYPE as delivered with BIBS; a new value is added with its template and may then be used here.
|  | VALID_ID | Valid ID
|  | BIRTH_CERTIFICATE | Birth certificate
|  | ACCOUNT_LIST | List of account details (Excel)
|  | QUOTATION | Quotation / proposal
|  | CLIENT_ACCEPTANCE | Client acceptance e-mail
|  | EPOLICY | E-policy
|  | OFFICIAL_RECEIPT | Official receipt
|  | POLICY_COPY | Issued policy copy
|  | OTHERS | Others
|  | KYC_FORM | Client information sheet / KYC form
|  | PROOF_OF_ADDRESS | Proof of address
|  | SEC_CERTIFICATE | SEC / DTI certificate of registration
|  | GIS | General Information Sheet (GIS)
|  | SECRETARY_CERTIFICATE | Secretary's certificate / board resolution
|  | PKG_REQUEST_FORM | Package request form
|  | PKG_QUOTATION_SLIP | Package quotation slip
|  | PKG_INSURER_RESPONSE | Insurer package terms
|  | PKG_COMPARATIVE | Package comparative table
|  | PKG_SLIP_SIGNED | Package slip (signed)
|  | MANCOM_SIGNOFF | ManCom sign-off
|  | PKG_ADVISORY | Package advisory
|  | REQUEST_EMAIL | Quotation / proposal request e-mail
|  | QUOTATION_SLIP | Quotation slip
|  | INSURER_RESPONSE | Insurer response / terms
|  | COMPARATIVE_TABLE | Comparative table
|  | PROPOSAL_SLIP | Proposal slip
|  | PAYMENT_CONFIRMATION | Payment / client confirmation
|  | HOLD_COVER | Hold cover confirmation
|  | INSURANCE_ADVICE | Insurance Advice
|  | RENEWAL_ADVICE | Renewal advice
|  | RA_ACCEPTANCE | Renewal advice acceptance (e-mail)
|  | SIGNED_RA | Signed renewal advice
|  | LAMD_REPORT | LAMD loan report
|  | INSURER_RENEWAL_FILE | Insurer renewal file
|  | RENEWAL_LETTER | Renewal letter
|  | CLAIM_REPORT | Claims report
|  | EB_CLIENT_FEEDBACK | EB client feedback
|  | EB_BOR | Broker on Record (signed)
|  | EB_TOR | Terms of Reference (TOR)
|  | EB_MASTERLIST | Master list (named)
|  | EB_MASTERLIST_UNNAMED | Unnamed master list (census)
|  | EB_UTILIZATION | Utilization report
|  | EB_INDICATIVE_PROPOSAL | Indicative (incumbent) proposal
|  | EB_PROPOSAL | Insurer proposal
|  | EB_COMPARATIVE | Comparative analysis
|  | EB_FRANCHISE_FORM | Franchise request form
|  | EB_CLIENT_CONFIRMATION | Client confirmation of the chosen proposal
|  | EB_POLICY_FORM | EB policy form / contract
|  | EB_DIRECT_BILLING | Insurer direct billing (EB changes)
|  | EB_SOA | Insurer statement of account (EB)
|  | EB_MEMBER_CHANGE | Member change request
|  | EB_ISACOM_APPROVAL | ISACOM approval (non-accredited provider)
|  | CLIENT_REQUEST | Client request or letter
|  | CLIENT_PHOTO | Photo sent by the client
|  | SUBMITTED_POLICY | Submitted policy document
|  | SBM_IAAF | Insurance Adequacy Assessment Form (IAAF)
|  | SBM_TOR | Terms of Reference (TOR)
|  | SBM_LETTER | Submitted policy letter
|  | LEGACY_DOCUMENT | Legacy document (archive)
|  | MIG_EVIDENCE | Migration sign-off evidence
Clause kind (CLAUSE_KIND) | PM-03 Clause library: Kind | WARRANTY | Warranty | The values of the list CLAUSE_KIND as delivered with BIBS; a new value is added with its template and may then be used here.
|  | CLAUSE | Clause
|  | EXCLUSION | Exclusion
|  | DEDUCTIBLE_WORDING | Deductible wording
Rate table (RATE_TABLE) | PM-04 Rate tables: Table | TAX | Statutory charge or rating factor
|  | SHORT_PERIOD | Short-period table
|  | MOTOR_LIMIT | Motor BI / PD limit premium
Package map action (MAP_ACTION) |  | MAP | Renew with the BIBS package version
|  | REJECT | Send the candidate to the Renewal Exception bucket
Package document template (PKG_DOCUMENT) | PM-08 Document templates: Template | PKG_REQUEST_FORM | Package Request Form
|  | PKG_QUOTATION_SLIP | Package quotation slip
|  | PKG_COMPARATIVE | Package comparative table
|  | PKG_SLIP | Package slip
|  | PKG_ADVISORY | Package advisory
|  | PKG_RENEWAL_ADVISORY | Package renewal advisory
Product Maintenance list or parameter (PM_LIST_OR_PARAMETER) | PM-09 Lists and parameters: List or parameter | PKG_REQUEST_REASON | List: Package request reason
|  | PKG_RESPONSE_OUTCOME | List: Insurer response outcome
|  | PKG_ADVISORY_GROUP | List: Advisory recipient group
|  | PKG_NOT_PROCEEDED_REASON | List: Package not proceeded reason
|  | PKG_REQUEST_TYPE | List: Package request type
|  | INCENTIVE_TYPE | List: Incentive type
|  | COVERAGE_KIND | List: Coverage kind
|  | CLAUSE_KIND | List: Clause kind
|  | DOCUMENT_TYPE | List: Document type
|  | MARKET_SEGMENT | List: Market segment
|  | PKG_REQUEST_PREFIX | Parameter: Prefix of package request numbers; the year is appended
|  | PKG_QS_PREFIX | Parameter: Prefix of package quotation slip numbers; the year is appended
|  | PKG_QS_REPLY_DAYS | Parameter: Days insurers have to reply to a package quotation slip
|  | PACKAGE_EXPIRY_NOTICE_DAYS | Parameter: Days before the package end date at which PACKAGE_EXPIRING is first raised; again at 30 and 7 days
|  | PACKAGE_RENEWAL_AUTODRAFT | Parameter: The expiry monitor drafts a RENEW package request for packages reaching the notice period
|  | PKG_SLA_MKT_APPROVAL | Parameter: SLA hours of the Marketing approval of a package request
|  | PKG_SLA_TSU_REVIEW | Parameter: SLA hours of the TSU Team Lead review and recommendation
|  | PKG_SLA_TSU_APPROVAL | Parameter: SLA hours of the TSU Team Head approval
|  | PKG_SLA_NEGOTIATION | Parameter: SLA hours of the insurer negotiation stage
|  | PKG_SLA_MANCOM | Parameter: SLA hours of the ManCom sign-off
|  | PKG_SLA_MBS_SETUP | Parameter: SLA hours of the MBS package set-up
|  | PACKAGE_EXPIRY_REMINDER_DAYS | Parameter: Days before the package end date at which PACKAGE_EXPIRING is raised again after the first notice
|  | PKG_ADVISORY_GROUPS | Parameter: Recipient groups (list PKG_ADVISORY_GROUP) proposed on a new package advisory
Incentive type (INCENTIVE_TYPE) | PM-10 Incentive criteria: Incentive type | OTHERS | Others (see description) | The values of the list INCENTIVE_TYPE as delivered with BIBS; a new value is added with its template and may then be used here.
|  | MIGRATED | Migrated booking incentive rule
Bulk request action (UA_ACTION) | UA-01 Users and roles: Action | ENROL | Enrol a new user
|  | MODIFY | Modify a user
|  | DEACTIVATE | Deactivate a user
|  | REACTIVATE | Reactivate a user
Privilege level (PRIVILEGE_LEVEL) | UA-02 Role matrix: Privilege level | Low | Low
|  | Standard | Standard
|  | High | High: a second approval when given or raised
|  | Admin | Admin: a second approval when given or raised
Change against the matrix (KEEP_ADD_REMOVE) | UA-02 Role matrix: Keep / Add / Remove | KEEP | Keep the permission
|  | ADD | Add the permission
|  | REMOVE | Remove the permission
Role in user access (UA_ROLE) | UA-03 Approval rules: Role in user access | Requestor | Raises access requests for the unit
|  | Approver | Approves access requests
|  | Second Approver | Second approval of High and Admin privileges
|  | Group-profile requester | Raises group-profile requests
|  | Implementer | System Administrator who implements approved requests
Separation-of-duties rule status (SOD_STATUS) | UA-04 SoD rules: Status | Enforced | A fixed rule of BIBS
|  | To confirm | Proposed; BDOI confirms
|  | New | Added by BDOI
Separation-of-duties control (SOD_CONTROL) | UA-04 SoD rules: Control | Prevent | A rule of Separation of Duties: BIBS refuses the request
|  | Detect by review | Reviewed with the reports
|  | Second approval | A second approver decides
Review frequency (REVIEW_FREQUENCY) | UA-04 SoD rules: Review frequency | Monthly | Monthly
|  | Quarterly | Quarterly
Sign-in (UA_PARAMETER) | UA-05 Parameters: Parameter | LOGIN_MAX_FAILED_ATTEMPTS | Consecutive failed logins that lock a user account; applies to all users
|  | SESSION_IDLE_WARNING_MINUTES | Minutes of inactivity after which the web client warns that the session will sign out
|  | SESSION_TIMEOUT_MINUTES | Minutes of inactivity after which the web session signs out automatically
|  | SESSION_EXPIRY_WARNING_MINUTES | Minutes before the system-triggered (absolute) sign-out at which the web client warns the user
|  | AUTH_MODE | Sign-in mode: LOCAL (BIBS passwords) or DIRECTORY (BDO directory sign-in by Windows ID, when the EIAM sign-in is specified)
|  | USER_ID_PATTERN | Regular expression of a new user ID on enrolment requests
|  | USER_ID_FORMAT_TEXT | The user ID format in words, shown to the requester with the format check of USER_ID_PATTERN
|  | PASSWORD_HISTORY_COUNT | Previous passwords a user may not reuse, LOCAL mode
|  | PASSWORD_MAX_AGE_DAYS | Days after which a password must be changed, LOCAL mode; 0 = never
|  | PASSWORD_MIN_AGE_DAYS | Days before a changed password may be changed again, LOCAL mode
|  | UAM_WORKING_HOURS | Working hours; an access request submitted outside them needs a second approval
|  | UAM_ANY_APPROVER | When true, any holder of ACCESS_APPROVE may decide a request, not only the approver chosen by the requester
|  | UAM_ROLE_APPLY_ON_APPROVAL | When true, an approved group-profile or role-permission request applies at its last approval; when false it waits for the System Administrator to implement it
|  | UAM_EXTERNAL_USERS | When true, access requests may be raised for external (portal) users; stays false while no portal is installed
|  | UAM_DORMANT_DAYS | Days without a sign-in after which a user is deactivated by the daily dormant-user job; 0 = never
|  | UAM_DORMANT_NOTICE_DAYS | Days before the dormant-user deactivation on which the user is told to sign in; 0 = no notice
|  | JOB_FAILURE_RECIPIENTS | Comma separated e-mail addresses told of every failed batch job
User access list (UA_LIST) | UA-06 Lists of values: List | UAM_BUSINESS_UNIT | List: Business unit group
|  | UAM_USER_LEVEL | List: User level
|  | UAM_DEACTIVATION_REASON | List: User deactivation reason
Dimension (DIMENSION) | D0-04 Dimensions: Dimension | COST_CENTER | Cost centre
|  | BUSINESS_LINE | Business line
Account class (ACCOUNT_CLASS) | D0-07 Categories and numbering: Account class | ASSET | Asset
|  | LIABILITY | Liability
|  | EQUITY | Equity
|  | INCOME | Income
|  | EXPENSE | Expense
Account class of the chart (ACCOUNT_CLASS_CHART) | D0-06 Chart of accounts: Class | ASSET | Asset
|  | LIABILITY | Liability
|  | EQUITY | Equity
|  | INCOME | Income
|  | EXPENSE | Expense
|  | MEMORANDUM | Memorandum
Account level (ACCOUNT_LEVEL) | D0-06 Chart of accounts: Level | GROUP | Group
|  | MAIN | Main account
|  | SUB | Sub-account
|  | MICRO | Micro account
Negative balance (NEGATIVE_BALANCE) | D0-06 Chart of accounts: Negative Balance | ALLOW | Allowed
|  | WARN | Allowed with a warning
|  | BLOCK | Refused
Category or numbering row (CATEGORY_ROW) | D0-07 Categories and numbering: Row | CATEGORY | GL category
|  | NUMBERING | Numbering scheme under a parent account
Accounting event (ACCOUNTING_EVENT) | D0-08 Accounting rules: Event type | COMMISSION_ACCRUAL | Commission accrued
|  | OPS_ADJ_COMMISSION | Commission adjustment without premium change
|  | OPS_INCENTIVE_ACCRUE | Incentive earned from insurer
|  | OPS_INCENTIVE_PASS_ON | Incentive pass-on to branches
|  | OPS_REMIT_CPC2 | CPC2 incentive per remittance batch
|  | OPS_REMIT_INCENTIVE | Early remittance incentive
|  | ASSET_ACQUISITION | Fixed asset capitalized
|  | COMMISSION_PAYMENT | Commission payment
|  | DISB_CHECK_NEGOTIATED | Check negotiated
|  | DISB_CHECK_STALE | Check staled
|  | DISB_VOUCHER | Disbursement voucher approved
|  | FRBS_SERVICE_FEE_ACCRUE | Service fee accrual
|  | MISC_PAYMENT | Miscellaneous payment
|  | OPS_REMITTANCE | Remittance to insurer
|  | OPS_REMIT_DEDUCTION | Remittance deduction on insurer confirmation
|  | PDC_ISSUED_PRESENTED | Issued PDC presented
|  | PETTY_CASH_EXPENSE | Petty cash disbursement
|  | PETTY_CASH_REPLENISHMENT | Petty cash reimbursement
|  | PREMIUM_REFUND_PAYMENT | Premium refund payment
|  | PRQ_CA_LIQUIDATION | Cash advance liquidation
|  | SUPPLIER_INVOICE | Supplier invoice
|  | SUPPLIER_PAYMENT | Supplier payment
|  | TAX_REMITTANCE | Tax remittance
|  | BROKER_BOOKING | Broker booking
|  | MIG_LEGACY_INVOICE_OPENING | Legacy invoice opening
|  | MIG_LEGACY_POSITION_TRUEUP | Legacy open-item adjustment
|  | OPS_AR_INSURER_SETUP | AR Insurer set-up after a remitted decrease
|  | OPS_WRITE_OFF | Minimal balance write-off / credit
|  | ASSET_DEPRECIATION | Monthly depreciation
|  | ASSET_TAKE_ON | Fixed asset opening balance
|  | ASSET_TRANSFER | Inter-branch asset transfer
|  | ASSET_DISPOSAL | Fixed asset disposal
|  | MIG_UPP_OPENING | Legacy unapplied payment opening
|  | MISC_RECEIPT | Miscellaneous receipt
|  | OPS_AR_INSURANCE_RECEIPT | Insurer non-premium receipt
|  | OPS_AR_RECEIPT | Acknowledgement receipt (premium)
|  | OPS_CWT_DTIP_OFFSET | 2307 certificate offset against DTIP
|  | OPS_CWT_RECLASS | PR reclassified to the client 2307
|  | OPS_DP_COMMISSION_COLLECT | Direct payment commission collected
|  | OPS_DP_PR_REVERSAL | Direct payment PR reversal
|  | OPS_DP_REINSTATE | Direct payment reinstatement
|  | OPS_EXCESS_TO_OVERAGES | Minimal excess to AP overages
|  | OPS_MINIMAL_BALANCE_REVERSAL | Premium minimal balance reversal
|  | OPS_OR_ISSUE | Official receipt issued
|  | OPS_PAYMENT_APPLY | Payment applied to a booked invoice
|  | OPS_RECEIPT_REINSTATE | Receipt reinstated
|  | OPS_UNAPPLIED_RECLASS | Unapplied payment reclassified
|  | OPS_UNAPPLIED_REFUND | Unapplied payment refunded
|  | OPS_UNAPPLIED_TO_INCOME | Unapplied payment reclassified to other income
|  | PREMIUM_DEPOSIT | Unapplied collection
|  | PREMIUM_RECEIPT | Premium collection
|  | SBM_HANDLING_FEE | Handling fee recognised
|  | SBM_NO_TOUCH_FEE | No Touch service fee billed
|  | TAX_CWT_CERT_RECEIVED | Insurer 2307 certificate received
|  | UNAPPLIED_APPLICATION | Application of unapplied collection
|  | BANK_TRANSFER | Bank transfer
|  | DISB_FUND_TRANSFER | Account funding transfer
|  | INVESTMENT_AMORTIZATION | Premium / discount amortization
|  | INVESTMENT_FAIR_VALUE | Investment fair value change
|  | INVESTMENT_INTEREST_ACCRUAL | Investment interest accrual
|  | INVESTMENT_INTEREST_RECEIPT | Coupon / interest received
|  | INVESTMENT_MATURITY | Investment maturity
|  | INVESTMENT_PURCHASE | Investment purchase
|  | INVESTMENT_SALE | Investment sale
|  | INVESTMENT_TAKE_ON | Investment opening balance
Debit or credit (DEBIT_CREDIT) | D0-08 Accounting rules: Debit or credit | DEBIT | Debit
|  | CREDIT | Credit
Legacy control account (LEGACY_ACCOUNT) | D0-09 Legacy accounts: Legacy account | Premium Receivable - Legacy | Per component
PR 2307 - Legacy
Due to Insurers - Legacy
Commission Receivable - Legacy
Unrealised Commission - Legacy
Deferred Output VAT - Legacy
Unapplied Collections - Legacy
|  | Migration Clearing | Nets to zero after the opening
Tax type (TAX_TYPE) |  | EWT | Expanded withholding tax
|  | FWT | Final withholding tax
|  | VAT | Value-added tax
|  | PT | Percentage tax
Payee class (PAYEE_CLASS) |  | SUPPLIER | Supplier | The values of the list PAYEE_CLASS as delivered with BIBS; a new value is added with its template and may then be used here.
|  | INSURER | Insurer
|  | EMPLOYEE | Employee
|  | CLIENT | Client
|  | GOVERNMENT | Government agency
|  | OTHER | Others
Module of an approval matrix (APPROVAL_MODULE) | D0-15 Approval limits: Module | Submitted Policies
Employee Benefits
Sanction Screening
Disbursement
R03 record_type (R03_RECORD_TYPE) | R03 Sales organisation (units a: record_type | REGION
DEPARTMENT
TEAM
AO
R08 account_type (R08_ACCOUNT_TYPE) | R08 Chart of accounts mapping: account_type | ASSET
LIABILITY
EQUITY
INCOME
EXPENSE
R08 normal_balance (R08_NORMAL_BALANCE) | R08 Chart of accounts mapping: normal_balance | DR
CR
R08 legacy_control_type (R08_LEGACY_CONTROL_TYPE) | R08 Chart of accounts mapping: legacy_control_type | PR
PR2307
DTIP
COMMISSION_REC
UNREALIZED_COMM
DEFERRED_VAT
UPP
NONE
Tax authority (TAX_AUTHORITY) | TX-02 Tax forms: Authority | BIR | Bureau of Internal Revenue
|  | LGU | Local government unit
|  | BFP | Bureau of Fire Protection
Filing frequency (FILING_FREQUENCY) | TX-02 Tax forms: Frequency | MONTHLY | Monthly
|  | QUARTERLY | Quarterly
|  | MONTHLY_EXCEPT_QUARTER_END | Monthly except the quarter-end month
|  | ANNUAL | Annual
Tax worksheet (TAX_WORKSHEET) | TX-02 Tax forms: Worksheet | VAT | VAT worksheet
|  | EWT | Withholding tax worksheet
|  | DST | Documentary stamp tax worksheet
|  | PREMIUM_TAX | Premium tax worksheet
|  | LGT | Local government tax worksheet
|  | FST | Fire service tax worksheet
|  | NONE | Prepared outside BIBS (reminder only)
Payee class (BIR) (TAX_PAYEE_CLASS) | TX-01 Party tax profiles: Payee class | INDIVIDUAL | Individual
|  | CORPORATE | Corporate (juridical person)
VAT treatment (VAT_TREATMENT) | TX-01 Party tax profiles: VAT treatment | REGULAR | Regular: sales with VAT are taxable, without VAT exempt
|  | ZERO_RATED | Zero-rated (for example PEZA or BOI-registered exporters)
|  | EXEMPT | Exempt
Exchange rate type (FX_RATE_TYPE) | MD-03 Exchange rates: Rate type | SPOT | Daily transaction rate
|  | CLOSING | Month-end closing rate
|  | AVERAGE | Period average rate
|  | BUDGET | Planning rate
G01 tb_version (G01_TB_VERSION) | G01 GL opening trial balance: tb_version | PROVISIONAL
TU1
TU2
TU3
FINAL
R11 kind (R11_KIND) | R11 Receipt series in use: kind | AR
OR
R06 qualifier (R06_QUALIFIER) | R06 Package code map (legacy pa: qualifier | RISK_CODE
INSURER
SI_BAND
R06 action (R06_ACTION) | R06 Package code map (legacy pa: action | MAP
REJECT
Business partner type (PARTY_TYPE) | MD-01 Business partners: Party type | AGENT | Agent
|  | BROKER | Broker
|  | REINSURER | Reinsurer
|  | RI_BROKER | Reinsurance broker
|  | COINSURER | Co-insurer
|  | SUPPLIER | Supplier
|  | GARAGE | Garage
|  | SURVEYOR | Surveyor or adjuster
|  | BANK | Bank
|  | EMPLOYEE | Employee
|  | GOVERNMENT | Government agency
|  | OTHER_PAYEE | Other payee
Currency (CURRENCY) | MD-01 Business partners: Default currency | PHP | Philippine peso
|  | USD | US dollar
|  | EUR | Euro
|  | JPY | Japanese yen
|  | GBP | Pound sterling
|  | SGD | Singapore dollar
|  | HKD | Hong Kong dollar
|  | AUD | Australian dollar
|  | CNY | Chinese yuan
Payee class (LOV_PAYEE_CLASS) | UP-02 Payees (upload): Payee class | SUPPLIER | Supplier | The values of the list as delivered with BIBS; a new value is added on Lists of Values first.
|  | INSURER | Insurer
|  | EMPLOYEE | Employee
|  | CLIENT | Client
|  | GOVERNMENT | Government agency
|  | OTHER | Others
Default mode (UP-02) (UP_02_DEFAULT_MODE) | UP-02 Payees (upload): Default mode | CTA | Credit to account
|  | ATD | Authority to debit
|  | MC_DD | Manager's check or demand draft
|  | CREDIT_TICKET | Credit ticket
|  | TT | Telegraphic transfer
|  | ONLINE_BANKING | Business online banking
|  | CHECK | Check
C01 client_type (C01_CLIENT_TYPE) | C01 Client master: client_type | I
C
C02 record_type (C02_RECORD_TYPE) | C02 Client addresses and contac: record_type | ADDRESS
CONTACT
C02 address_type (C02_ADDRESS_TYPE) | C02 Client addresses and contac: address_type | HOME
BUSINESS
MAILING
BILLING
C03 mode (C03_MODE) | C03 Client payout accounts: mode | CTA
CHECK
Client Type (UP-01) (UP_01_CLIENT_TYPE) | UP-01 Clients (upload): Client Type | INDIVIDUAL | Individual
|  | CORPORATE | Corporate
Identification document (LOV_ID_TYPE) | UP-01 Clients (upload): ID Type | PASSPORT | Passport | The values of the list as delivered with BIBS; a new value is added on Lists of Values first.
|  | DRIVERS_LICENSE | Driver's license
|  | UMID | UMID
|  | PHILSYS | PhilSys national ID
|  | SSS | SSS ID
|  | PRC | PRC ID
|  | POSTAL | Postal ID
|  | TIN_ID | TIN ID
|  | SEC_REG | SEC registration (corporate)
|  | DTI_REG | DTI registration (sole proprietor)
Market segment (LOV_MARKET_SEGMENT) | UP-01 Clients (upload): Market Segment | CBG | Consumer Banking Group (CBG) | The values of the list as delivered with BIBS; a new value is added on Lists of Values first.
|  | COMBANK | Commercial Banking
|  | CORBANK | Corporate Banking
|  | RETAIL | Retail Marketing
|  | INSTITUTIONAL | Institutional Banking / SM / BDO accounts
Nationality (LOV_NATIONALITY) | UP-01 Clients (upload): Nationality | FILIPINO | Filipino | The values of the list as delivered with BIBS; a new value is added on Lists of Values first.
|  | AMERICAN | American
|  | CHINESE | Chinese
|  | JAPANESE | Japanese
|  | KOREAN | Korean
|  | OTHERS | Others
Source of funds (LOV_SOURCE_OF_FUNDS) | UP-01 Clients (upload): Source of Funds | SALARY | Salary / employment | The values of the list as delivered with BIBS; a new value is added on Lists of Values first.
|  | BUSINESS | Business income
|  | REMITTANCE | Remittance
|  | INVESTMENT | Investments / savings
|  | PENSION | Pension
|  | OTHERS | Others
KYC risk rating (LOV_KYC_RISK_RATING) | UP-01 Clients (upload): Risk Rating | LOW | Low | The values of the list as delivered with BIBS; a new value is added on Lists of Values first.
|  | STANDARD | Standard
|  | HIGH | High (enhanced due diligence)
Entity Type (UP-03) (UP_03_ENTITY_TYPE) | UP-03 Watchlist entries (upload: Entity Type | INDIVIDUAL | Individual
|  | ENTITY | Entity
List Type (UP-03) (UP_03_LIST_TYPE) | UP-03 Watchlist entries (upload: List Type | SANCTION | Sanctions list
|  | PEP | Politically exposed persons
|  | INTERNAL | Internal list
Tax type (BIBS) (D0_10_TAX_TYPE) | D0-10 Tax codes: Tax type | VAT_OUTPUT | Output VAT (12 %) on BDOI's sales
|  | VAT_INPUT | Input VAT on purchases
|  | VAT_ZERO_RATED | Zero-rated sales and purchases
|  | VAT_EXEMPT | VAT-exempt sales and purchases
|  | EWT | Creditable (expanded) withholding tax per ATC
|  | PREMIUM_TAX | Premium tax (insurer return; only if BDOI confirms)
|  | DST | Documentary stamp tax (insurer return; only if BDOI confirms)
|  | LGT | Local government tax (insurer return; only if BDOI confirms)
|  | FST | Fire service tax (insurer return; only if BDOI confirms)
Payee class (BIR) (D0_10_PAYEE_CLASS) | D0-10 Tax codes: Payee class | INDIVIDUAL | Individual
|  | CORPORATE | Corporate (juridical person)
Premium charge or rating factor (BIBS) (PM_04_RATE) | PM-04 Rate tables: Rate | DST | Documentary stamp tax
|  | PREMIUM_TAX | Premium tax
|  | VAT_PREMIUM | VAT on premium
|  | FIRE_SERVICE_TAX | Fire service tax
|  | VAT_COMMISSION | VAT on BDOI's commission
|  | MOTOR_OD_ANNUAL | Motor own damage / theft coverage, % of TSI, annual
|  | MOTOR_OD_MULTI_YEAR | Motor own damage / theft coverage, % of TSI, multi-year
Route (ROUTE) | Lists of values: Route | Migration Console
Configuration screen
Status (STATUS) | Lists of values: Status System parameters: Status SLA and turnaround: Status Numbering prefixes: Status Notification events: Status Document templates: Status Accounting events: Status Configured on screens: Status PM-04 Charges checklist: Status D0-10 Tax checklist: Status Start here: Status | Not started
In progress
Ready for review
Confirmed
Not applicable
Kind of gap (KIND_OF_GAP) | Gaps: Kind of gap | No upload route: keyed on the screen from the template
Not held by BIBS: question to BDOI
Held by BIBS (HELD_BY_BIBS) | PM-04 Charges checklist: Held by BIBS D0-10 Tax checklist: Held by BIBS | Yes
No
Rule confirmed (RULE_CONFIRMED) | PM-04 Charges checklist: Rule confirmed D0-10 Tax checklist: Rule confirmed | Agree
Change
Held by BIBS (HELD_BY_BIBS_2) | Coverage check: Held by BIBS | Yes
Partly
No
Templates of this workbook (TEMPLATES) | Questions and comments: Template | D0-02 Branches
D0-04 Cost centres and business lines
D0-07 Account categories and numbering
MD-02 Currencies
PM-09 Lists of values and parameters
R01 Lists of values and MIS values
R04 Insurers
UA-02 Role-to-permission matrix
UA-06 Lists of values
D0-05 Employees
D0-06 Chart of accounts
MD-01 Business partners (reinsurers, intermediaries, suppliers)
R03 Sales organisation (units and account officers)
R05 Product lines, cover types, products and risk codes
UA-01 Users and roles load
D0-03 Holiday calendar
MD-03 Exchange rates and their source
R02 Branches and invoicing branches
R04B Insurer branches
R11 Receipt series in use
UA-04 Separation-of-duties rules
UP-01 Clients not held in the legacy systems
C01 Client master
D0-10 Tax codes
D0-11 Company bank accounts
PM-01 Product catalogue
R08 Chart of accounts mapping
UP-02 Payees
D0-01 Company
D0-08 Accounting rules
D0-09 Legacy control accounts
D0-15 Approval limits and matrices
R07 Commission rates by insurer and product
TX-02 Tax forms and filing calendar
UA-03 Approvers, approval rules and limits
PM-02 Coverages, perils and field rules
PM-03 Clause library
C02 Client addresses and contacts
C03 Client payout accounts
D0-12 Check books
D0-13 Petty cash funds
D0-14 Bank statement layouts
G01 GL opening trial balance
PM-04 Rate tables
PM-10 Incentive criteria
TX-01 Party tax profiles (clients, insurers, payees)
PM-06 Packages in force at go-live
R06 Package code map (legacy package to BIBS package version)
PM-08 Document templates
UA-05 Password, session and sign-in parameters
UP-03 Watchlist entries (sanctions, PEP and internal lists)
General
Question status (QUESTION_STATUS) | Questions and comments: Status | Open
Answered
Closed

## Questions and comments
Questions and comments
← Back to Start here | Raise a question or a comment on a template or a column; the iorta TechNXT project team answers here.
No. | Template | Column | Question / comment | Raised by | Date | Answer | Answered by | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100