RUNBOOK

Cutover Runbook

BRD-13 Data Migration - production cutover from T-30 to hypercare exit

BIBS – BDOI Broker System

| Client | BDO Insurance and Reinsurance Brokers, Inc. |
| --- | --- |
| Document | BIBS-DMC-BRD-13 |
| Version | 1.0 |
| Date | 26 September 2026 |
| Status | Issued for BDOI review |
| Classification | Confidential |

Prepared by iorta TechNXT for BDOI

iNXT BrokerVerse. This document is confidential to BDO Insurance and Reinsurance Brokers, Inc. and iorta TechNXT.

Document Control

| Version | Date | Author | Reviewer | Approver | Change |
| --- | --- | --- | --- | --- | --- |
| 1.0 | 26 Sep 2026 | iorta TechNXT Project Manager | iorta TechNXT Solution Architect | BDOI Program Manager (pending) | First issue; dates are relative to T until BDOI confirms the go-live date (DMQ25); re-issued after the dress rehearsal with named people and measured timings |

Distribution List

| Name / Unit | Role | Organisation | Purpose |
| --- | --- | --- | --- |
| Program Manager, Business Project Services | Approver | BDO Unibank ESG | Owner of the cutover; chair of the go / no-go board |
| Go / no-go board members | Approver | BDOI | Checkpoints GNG-1, GNG-2, GNG-3 |
| BDOI IT (legacy EBIX, QPS, ISYS, CMS) | Task owner | BDOI | Freeze, extracts, read-only, rollback |
| Comptrollership; Operations; Marketing; Compliance | Task owner | BDOI | Accounts, reconciliation, verification, communication |
| Project team | Task owner | iorta TechNXT | Loads, reconciliation, environment, hypercare |

Contents

1 Purpose and use	4

2 Cutover organisation	4

2.1 Command centre	4

2.2 Roles	4

3 Timeline	5

3.1 Freeze windows	6

4 Go / no-go checkpoints	7

5 Task list	8

5.1 Phase A - Readiness	8

5.2 Phase B - Pre-load and daily deltas	9

5.3 Phase C - Legacy freeze and final extracts	10

5.4 Phase D - Production load	10

5.5 Phase E - Reconciliation, verification and go / no-go	11

5.6 Phase F - Go-live	12

5.7 Phase G - Hypercare	12

6 Rollback	14

7 Communication plan	14

8 Hypercare	15

8.1 Roster	15

8.2 Exit criteria	15

9 Decommissioning checklists	16

Sign-off	17

# 1 Purpose and use

This runbook is the plan of the production cutover of BIBS: from 30 days before go-live (T) to the end of hypercare. It lists every task with its owner, start, duration, predecessors and the evidence that proves it is done; the go / no-go checkpoints with their criteria; the freeze windows; the rollback procedure; the communication plan; the hypercare roster and exit criteria; and the decommissioning checklists of the legacy systems.

•	T is the go-live date: the first business day (a Monday) of a month, after a legacy month-end close (proposal, DMQ25, register DCR-200). Days are calendar days; times are Philippine time (PHT).

•	The same tasks are in the Cutover Task Plan workbook (BIBS_Migration_BRD-13_Cutover_Task_Plan_v1.0.xlsx), where names, actual times and status are recorded, and in the Migration Console as the plan of kind PRODUCTION (FR-DM-120). The console is the record during the cutover; the workbook is the planning and review copy.

•	The plan was rehearsed in three mocks and a dress rehearsal (Strategy chapter 10). This version gives planned durations; version 1.1, issued after the dress rehearsal, gives the measured durations and the named people.

# 2 Cutover organisation

## 2.1 Command centre

•	Location and channels. A command centre room at BDOI head office, a standing bridge line and a chat channel for the cutover team, open from T-3 17:00 to T+5.

•	Status calls. T-3 to T: every 4 hours and at each checkpoint. T+1 to T+5: 08:00 and 17:00. Afterwards daily at 17:00 until hypercare exit.

•	Decisions. Task owners report completion with the evidence in the console. The Data Migration Lead decides within the plan; anything that changes the plan, the scope or a checkpoint goes to the go / no-go board.

•	Escalation. Task owner to the Data Migration Lead (15 minutes), to the iorta Project Manager and the Program Manager (30 minutes), to the go / no-go board (1 hour, or immediately for a stop condition).

Stop conditions (the board meets at once): a rejected final extract that cannot be re-sent within 2 hours; a load failure that leaves a financial object incomplete; Migration Clearing not 0.00 after the reconciliation window; a legacy posting after the freeze; loss of the production environment or of the snapshot.

## 2.2 Roles

Table 1: Roles used in the task plan

| Code | Role | Organisation |
| --- | --- | --- |
| PM | BDOI Program Manager (ESG - Business Project Services) | BDOI |
| DML | BDOI Data Migration Lead | BDOI |
| OWN | Data owners (department heads of each object) | BDOI |
| STW | Data stewards | BDOI |
| COMP | Comptrollership (reconciliation approver for financial objects) | BDOI |
| OPS | Operations (Financial Transactions, Cashiering, Remittance, Collections) | BDOI |
| MKT | Marketing (Retail and Corporate) and Renewal handlers | BDOI |
| CMP | Compliance and Audit | BDOI |
| BIT | BDOI IT (legacy systems | extracts |
| GNG | Go / no-go board (Program Manager, heads of Operations, Comptrollership, Marketing, Compliance, IT; iorta Project Manager) | BDOI and iorta TechNXT |
| IPM | iorta TechNXT Project Manager | iorta TechNXT |
| IML | iorta TechNXT Migration Lead (loaders | reconciliation |
| IOP | iorta TechNXT Migration Operator (intake | validation |
| IDO | iorta TechNXT DevOps (AWS environment | snapshots |
| IQA | iorta TechNXT QA (smoke tests | defect triage) |

# 3 Timeline

Table 2: Cutover phases

| Phase | Name | When | Tasks | IDs |
| --- | --- | --- | --- | --- |
| A | Readiness | T-30 to T-15 | 13 | CT-001 to CT-013 |
| B | Pre-load and daily deltas | T-14 to T-4 | 17 | CT-014 to CT-030 |
| C | Legacy freeze and final extracts | T-3 (Friday) | 6 | CT-031 to CT-036 |
| D | Production load | T-2 (Saturday) | 13 | CT-037 to CT-049 |
| E | Reconciliation, verification and go / no-go | T-1 (Sunday) | 8 | CT-050 to CT-057 |
| F | Go-live | T (Monday) | 7 | CT-058 to CT-064 |
| G | Hypercare | T+1 to the first month-end close | 11 | CT-065 to CT-075 |

Figure 1: The cutover weekend (T = Monday go-live; times PHT)

## 3.1 Freeze windows

Table 3: Freeze windows

| Freeze | From | Until | Scope | Exception route |
| --- | --- | --- | --- | --- |
| Reference data | T-7 (map freeze) | Go-live | Insurers, products, risk codes, packages, AOs, branches, LOVs in EBIX and QPS | Change request approved by the data owner; new code map version; delta load of R objects |
| Client master | T-3 22:00 (last delta) | Go-live | New and changed clients in QPS / EBIX / CMS | None after the freeze; changes keyed in BIBS after go-live |
| Business transactions | T-3 22:00 (after the last legacy EOD) | Go-live | All postings in EBIX, QPS, CMS - bookings, receipts, UPP, dispositions, remittances, endorsements, GL journals | None; an urgent item is recorded on paper and keyed in BIBS on T |
| BIBS configuration | T-2 00:00 | T+3 | Parameters, accounting rules, code maps, workflows in production | Emergency change approved by the go / no-go board |
| BIBS releases | T-7 | T+14 | Deployments to production | Hotfix of a Critical defect approved by the go / no-go board |

# 4 Go / no-go checkpoints

Each checkpoint is recorded in the Migration Console with the value of every criterion at the time of the decision (FR-DM-121). A criterion that is not met blocks GO unless the board records a waiver with its reason (only for criteria marked as waivable in the console; the financial and clearing criteria of GNG-3 are never waived).

Table 4: GNG-1 at T-15 - Start the production pre-load

| # | Criterion |
| --- | --- |
| 1 | Dress rehearsal completed within the window with at least 20 percent margin, rollback rehearsed |
| 2 | Production environment, roles and PH-only access ready; masking off only in production |
| 3 | Legacy control accounts, Migration Clearing and LG_ rule lines approved in production (DMQ18) |
| 4 | Code map versions for production approved |
| 5 | Transfer path (SFTP or console) tested |
| 6 | No open Critical defect of the migration or of a Day-1 module |

Table 5: GNG-2 at T-4 - Enter the legacy freeze on T-3

| # | Criterion |
| --- | --- |
| 1 | Reference data and clients loaded and accepted (G6) in production; daily deltas running |
| 2 | Client review queue empty |
| 3 | Final extract jobs timed within the window (dry run) |
| 4 | In-flight items and remittance batches closed or listed for carry-forward |
| 5 | RMEL cohorts to carry confirmed |
| 6 | Communications sent; branches and insurers informed |

Table 6: GNG-3 at T-1 18:00 - Go live on T

| # | Criterion |
| --- | --- |
| 1 | Every Day-1 object at G6 (100 percent) |
| 2 | Counts - received = control and loaded + skipped + rejected + excluded = staged, for every object |
| 3 | Financial rejects (F01, F02, G01) - 0, or each excluded item approved by the owner with a manual-entry plan |
| 4 | Amount reconciliation of open items, UPP and trial balance - 0.00 difference per currency |
| 5 | Migration Clearing - 0.00 per branch and currency |
| 6 | Legacy control accounts equal their sub-ledgers (ACSL, context LEGACY) - 0.00 |
| 7 | Client review queue empty; screening run complete |
| 8 | Business smoke test passed |
| 9 | Rollback point (snapshot) taken and verified |
| 10 | Hypercare roster and support channels in place |

Table 7: POINT OF NO RETURN at T 18:00 - Continue in BIBS; fallback to legacy no longer offered (DMQ32)

| # | Criterion |
| --- | --- |
| 1 | No Critical defect that stops receipts, payment application, remittance or booking |
| 2 | Migration Clearing still 0.00; no posting in legacy since the freeze |
| 3 | Every branch has transacted in BIBS |

# 5 Task list

Columns: When is the day relative to T and the planned start time; Owner is the accountable role (codes in section 2.2); Hours is the planned elapsed time; After lists the tasks that must be complete first; Verification is the evidence recorded in the console.

## 5.1 Phase A - Readiness

Table 8: Phase A - Readiness

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-001 | T-30 | Confirm the dress rehearsal met its exit criteria (all objects loaded and reconciled L1-L5, window met with 20 percent margin, rollback rehearsed) | DML | 4 | - | Dress rehearsal report signed by the Data Migration Lead and the iorta Migration Lead |
| CT-002 | T-30 | Confirm the go-live date, the freeze start (last legacy EOD) and the blackout dates (DMQ25); publish the cutover calendar | PM | 2 | CT-001 | Calendar approved by the Program Manager and circulated |
| CT-003 | T-29 | Name the cutover team, the command centre room and bridge line, and the hypercare roster (section Hypercare) | PM | 4 | CT-002 | Roster with names and phone numbers in the runbook annex |
| CT-004 | T-28 | Freeze the production cutover plan in the Migration Console (plan kind PRODUCTION, tasks and owners from this list) | IML | 4 | CT-002 | MIG-CUTOVER-STATUS shows the plan with every task owned |
| CT-005 | T-28 | Production environment ready - BIBS release of the go-live build deployed, MIG_ENVIRONMENT_CLASS = PRODUCTION, MIG_CUTOVER_DATE = T, jobs scheduled | IDO | 8 | - | Deployment record; parameter screen; job list |
| CT-006 | T-27 | Grant the migration roles in production (DATA_MIGRATION_LEAD, DATA_STEWARD, DATA_OWNER, MIGRATION_OPERATOR, MIGRATION_RECON_APPROVER, MIGRATION_GONOGO) through User Access requests; check PH-only network access | IDO | 8 | CT-005 | User Access approvals; access test from an allowed and a blocked location |
| CT-007 | T-26 | Comptrollership sets up in production the legacy control accounts, Migration Clearing and the LG_ accounting rule lines (DMQ18), through maker-checker | COMP | 16 | CT-005 | Chart and accounting rules approved; test posting in the dress rehearsal environment matched |
| CT-008 | T-25 | Approve the final code map versions for production (all sets); record versions in the plan | OWN | 16 | - | MIG-MAP-VERSIONS lists one APPROVED version per set |
| CT-009 | T-24 | Users of every persona created and trained; BIBS menus checked per persona (UAT readiness items 1 and 14) | PM | 40 | CT-006 | User list; training attendance; persona menu check |
| CT-010 | T-21 | Communicate the go-live and freeze to branches, insurers and bank channels (autopay files carry the legacy invoice number after go-live) | PM | 4 | CT-002 | Communications sent (communication plan items 1-4) |
| CT-011 | T-20 | Legacy clean-up drives - UPP with no reference, invoices open more than 5 years, duplicate clients flagged in Mock 3, unmapped codes | STW | 80 | - | Clean-up tracker; counts reduced against Mock 3 profiling |
| CT-012 | T-18 | SFTP drop or console upload path tested end to end from BDOI IT with a masked file; checksum verified | BIT | 4 | CT-005 | Test extract accepted and purged |
| CT-013 | T-15 | Go / no-go checkpoint GNG-1 (readiness to start the pre-load) | GNG | 2 | CT-001, CT-004, CT-006, CT-007, CT-008, CT-012 | Decision recorded in the console with the GNG-1 criteria |

## 5.2 Phase B - Pre-load and daily deltas

Table 9: Phase B - Pre-load and daily deltas

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-014 | T-14 08:00 | Take a production database snapshot before the pre-load | IDO | 1 | CT-013 | Snapshot ID recorded in the plan |
| CT-015 | T-14 09:00 | Extract and send R01-R08 and R11 (current values) with control files | BIT | 6 | CT-014 | Files received; intake checks passed (extract status CHECKED) |
| CT-016 | T-14 15:00 | Validate and load reference data R01-R08; authorise CREATE values in each master | IOP | 8 | CT-015 | Batches LOADED; MIG-UNMAPPED-CODES empty for R objects |
| CT-017 | T-13 | Reconcile and sign off the reference objects (G5, G6) | DML | 6 | CT-016 | MIG-SIGNOFF-STATUS shows G6 for R01-R08 |
| CT-018 | T-13 | Load payees R09 if in scope (DMQ30) | IOP | 4 | CT-017 | Batch SIGNED_OFF |
| CT-019 | T-12 | Extract and send the full client extract C01, C02, C03 (as of the previous EOD) | BIT | 8 | CT-017 | Files CHECKED; counts against the Mock 3 volumes within 5 percent |
| CT-020 | T-12 | Validate clients; run matching; clear the review queue | STW | 24 | CT-019 | Review queue empty; MIG-CLIENT-MATCH reviewed |
| CT-021 | T-10 | Load clients C01-C03; reconcile L1-L4; business sample checks; sign off (G5, G6) | IOP | 16 | CT-020 | MIG-RECON-SUMMARY all MATCHED or EXPLAINED; G6 signed |
| CT-022 | T-10 | Daily client delta (new and changed clients of the day) from T-10 to T-4 - extract 23:00, load 00:30 (job MIG_CLIENT_DELTA) | BIT | 1 | CT-021 | Delta batch SIGNED_OFF each morning by 07:00 |
| CT-023 | T-9 | Complete legacy remittance batches in process, or tag the holds and special remittances that carry forward (DMQ21) | OPS | 40 | - | List of carried items for F04 agreed by Operations - Remittance |
| CT-024 | T-9 | Complete in-flight legacy items where possible - pending endorsements, un-booked accounts, check pick-ups, refunds (DMQ33) | OPS | 40 | - | In-flight list reduced; the rest listed for carry-forward or re-keying |
| CT-025 | T-7 | Code map freeze - no new legacy code without a change request and a map version | OWN | 1 | CT-017 | Freeze notice sent; change log opened |
| CT-026 | T-7 | Legacy reference-data change freeze in EBIX and QPS (insurers, products, AOs, branches) | BIT | 1 | CT-025 | Maintenance screens locked or change log reviewed daily |
| CT-027 | T-7 | Dry run of the final extract jobs on the current day's data (timing and control files) | BIT | 6 | CT-015 | Extract timings within the plan; control files correct |
| CT-028 | T-5 | Confirm the RMEL cohorts to carry (expiry T to T+140) with Marketing; freeze new legacy RMEL extractions | MKT | 4 | - | Cohort list and counts per month agreed |
| CT-029 | T-4 | Go / no-go checkpoint GNG-2 (enter the legacy freeze) | GNG | 2 | CT-021, CT-022, CT-023, CT-024, CT-027, CT-028 | Decision recorded with the GNG-2 criteria |
| CT-030 | T-4 | Announce the freeze and the Monday opening to all users, branches and insurers | PM | 1 | CT-029 | Communication plan item 5 sent |

## 5.3 Phase C - Legacy freeze and final extracts

Table 10: Phase C - Legacy freeze and final extracts

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-031 | T-3 17:00 | Last legacy business transactions; cashiers deposit and close; UPP of the day recorded | OPS | 3 | CT-029 | Branch close checklist from every branch |
| CT-032 | T-3 20:00 | Last legacy EOD and month-end close (EBIX, QPS, ISYS, CMS) | BIT | 2 | CT-031 | EOD logs complete without error |
| CT-033 | T-3 22:00 | Legacy business freeze - EBIX, QPS, CMS set to read-only for business users; batch jobs that post are disabled | BIT | 1 | CT-032 | Test posting refused in each legacy system; job list shows disabled jobs |
| CT-034 | T-3 22:15 | Final client delta (last changes of the day) extracted and loaded | IOP | 2 | CT-033 | Last delta batch SIGNED_OFF |
| CT-035 | T-3 22:30 | Final extracts after the EOD - P01, P01S, P03, F01, F01S, F01C, F02, F03, F04, F06, R11 (final numbers), G01 trial balance | BIT | 5 | CT-033 | Every file and control file in the intake; SHA-256 recorded |
| CT-036 | T-3 23:30 | Comptrollership confirms the legacy trial balance is final and balanced per branch and currency | COMP | 2 | CT-032 | Signed TB total per branch and currency |

## 5.4 Phase D - Production load

Table 11: Phase D - Production load

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-037 | T-2 02:00 | Take the production database snapshot - the rollback point | IDO | 1 | CT-034, CT-035 | Snapshot ID and restore test of the snapshot metadata recorded |
| CT-038 | T-2 03:00 | Intake checks of all final extracts (checksum, layout, row count, control totals, hash totals) | IOP | 1 | CT-037 | Every extract CHECKED; rejected files re-sent within 1 hour |
| CT-039 | T-2 04:00 | Validate P01 and P01S; resolve issues; approve load (G3, G4) | IOP | 2 | CT-038 | Error rate within the master threshold; G4 signed by the Data Migration Lead |
| CT-040 | T-2 06:00 | Load policy headers P01; reconcile L1-L4 | IOP | 3 | CT-039 | MIG-RECON-SUMMARY for P01 MATCHED |
| CT-041 | T-2 06:00 | Validate F01, F01S, F01C; resolve issues; approve load (G3, G4) | IOP | 3 | CT-038 | 0 financial errors or owner-approved exclusions with manual-entry plan |
| CT-042 | T-2 09:00 | Load open legacy invoices F01 with opening entries MIG_LEGACY_INVOICE_OPENING | IOP | 5 | CT-040, CT-041 | Batch LOADED without rejects |
| CT-043 | T-2 09:00 | Validate and load UPP F02 with opening entries MIG_UPP_OPENING | IOP | 3 | CT-038, CT-021 | Batch LOADED without rejects |
| CT-044 | T-2 14:00 | Load collection state F03, remittance items F04, PDCs and pick-ups F06 | IOP | 3 | CT-042 | Batches LOADED |
| CT-045 | T-2 15:00 | Load the GL opening trial balance G01 (OPENING journals per branch and currency) | IOP | 2 | CT-036, CT-042, CT-043 | Journals posted; TB in BIBS equals the legacy TB |
| CT-046 | T-2 16:00 | Load RMEL cohorts P03 and make them available to Renewal | IOP | 2 | CT-040 | Candidates visible in Renewal with source LEGACY |
| CT-047 | T-2 17:00 | Update the receipt series R11 to the final next numbers | IOP | 1 | CT-038 | Next AR / OR numbers = legacy last used + 1 per branch |
| CT-048 | T-2 18:00 | Reconcile L1-L4 of every financial object; run L5 - Migration Clearing per branch and currency, legacy control accounts vs sub-ledgers (ACSL, context LEGACY) | IML | 4 | CT-044, CT-045 | MIG-GL-CLEARING shows 0.00 per branch and currency |
| CT-049 | T-2 22:00 | Explain or fix every break (rerun batches); reconciliation approver signs G5 per object | COMP | 6 | CT-048 | MIG-RECON-SUMMARY all MATCHED or EXPLAINED with approval |

## 5.5 Phase E - Reconciliation, verification and go / no-go

Table 12: Phase E - Reconciliation, verification and go / no-go

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-050 | T-1 06:00 | Start the full sanction screening run of migrated clients (SCR_PERIODIC_SCREENING, full rescreen) | IOP | 6 | CT-021 | Run completed; hits in the screening queue for Compliance |
| CT-051 | T-1 07:00 | Business verification of samples per object on the BIBS screens (Reconciliation Approach, sample plan); data owners sign G6 | OWN | 6 | CT-049 | Sample checklists signed; G6 for every Day-1 object |
| CT-052 | T-1 09:00 | Business smoke test on production with test-marked transactions reversed afterwards - OTC payment preview on a legacy invoice, automatch preview, remittance extraction preview, Invoice 360, client and policy search by legacy reference | IQA | 4 | CT-049 | Smoke test checklist passed; no posting left open |
| CT-053 | T-1 13:00 | Check jobs, alerts and integrations for Monday (PAYMENT_AUTOMATCH hourly, payment file handlers, Renewal extraction, e-mail) | IDO | 2 | CT-052 | Job schedule and alert routing checked |
| CT-054 | T-1 15:00 | Prepare the go / no-go pack - MIG-GONOGO with measured criteria, open defects, sign-off status | IML | 2 | CT-050, CT-051, CT-052, CT-053 | Pack circulated to the board by 17:00 |
| CT-055 | T-1 18:00 | Go / no-go decision GNG-3 (go-live) | GNG | 1 | CT-054 | Decision recorded in the console with every criterion value |
| CT-056 | T-1 19:00 | If NO-GO - execute the rollback procedure (section Rollback) and reopen legacy for Monday | IDO | 6 | CT-055 | Legacy open for business Monday 08:00; BIBS restored to the rollback point |
| CT-057 | T-1 19:00 | If GO - send the go-live notice; open BIBS roles for business users from 06:00 Monday | PM | 1 | CT-055 | Communication plan item 6 sent |

## 5.6 Phase F - Go-live

Table 13: Phase F - Go-live

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-058 | T 06:00 | Enable business logins; confirm legacy stays read-only; legacy links shown in BIBS | IDO | 1 | CT-057 | Log-in test per persona; legacy posting refused |
| CT-059 | T 07:00 | Command centre opens; hypercare roster on duty | IPM | 1 | CT-058 | Attendance on the bridge |
| CT-060 | T 08:00 | BIBS open for business | PM | 0 | CT-059 | First transactions observed in each branch |
| CT-061 | T 09:00 | First payment file uploads and the first automatch run including migrated UPP; review results | OPS | 2 | CT-060 | Run summary; legacy and new postings in the right accounts |
| CT-062 | T 12:00 | Midday check - defects, queues, Migration Clearing still 0.00, no legacy posting | IML | 1 | CT-060 | Midday report to the board |
| CT-063 | T 18:00 | End-of-day review - point of no return (DMQ32); decide continue or fallback | GNG | 1 | CT-062 | Decision recorded |
| CT-064 | T 20:00 | First BIBS EOD jobs; check GL posting, sub-ledgers and the Cash Receipts Book | IDO | 2 | CT-063 | Job run log; CRB lists the day's receipts |

## 5.7 Phase G - Hypercare

Table 14: Phase G - Hypercare

| ID | When | Task | Owner | Hours | After | Verification |
| --- | --- | --- | --- | --- | --- | --- |
| CT-065 | T+1 | Daily hypercare check - Migration Clearing 0.00, legacy control accounts vs sub-ledgers, automatch results, exception queues, failed jobs (daily until exit) | IML | 1 | CT-064 | Daily hypercare report |
| CT-066 | T+1 | Defect triage twice a day (10:00 and 16:00) with Operations, Comptrollership and iorta QA | IQA | 1 | CT-064 | Defect log updated; severity agreed |
| CT-067 | T+2 | First remittance extraction with legacy invoices for the main insurers; compare with the legacy remittance pattern | OPS | 4 | CT-064 | Schedules show legacy invoice numbers; OPS_REMITTANCE posts to DTIP legacy |
| CT-068 | T+3 | First Collections worklist refresh with legacy invoices; collectors confirm carried promises and assignments | OPS | 2 | CT-064 | Worklist counts agree with F03 |
| CT-069 | T+5 | Staging purge - payloads and intake files of the signed-off production batches deleted within 5 days (MIG_STAGING_PURGE) | IDO | 1 | CT-055 | No staging payload older than 5 days after sign-off; purge log |
| CT-070 | T+5 | Check the daily Renewal extraction from the migrated headers (policies expiring at business date + 140 days) - first runs | MKT | 2 | CT-046 | Candidates created with source LEGACY |
| CT-071 | T+7 | Week-1 review with the board - defects, volumes, performance, user feedback | GNG | 2 | CT-065 | Minutes; actions |
| CT-072 | T+10 | First DPPR or PR2307 legacy reversal batch (if any) approved and posted | COMP | 4 | CT-064 | Run report; legacy sub-ledgers reduced by the batch total |
| CT-073 | T+14 | Hypercare mid-point review against the exit criteria | GNG | 2 | CT-071 | Criteria status recorded |
| CT-074 | T+30 | First month-end close with legacy control accounts; ACSL GL-SL reconciliation with context LEGACY | COMP | 16 | CT-073 | ACSL reconciliation without difference; FRBS schedules include legacy balances |
| CT-075 | T+30 | Hypercare exit decision | GNG | 2 | CT-074 | Exit criteria met; hand-over to production support (L1 / L2 / L3) |

# 6 Rollback

The rollback returns BDOI to legacy with no loss of data. It is available until the point of no return, the end-of-day review on T at 18:00 (DMQ32). The rollback point is the production database snapshot taken at T-2 02:00 (task CT-037), before any open item, header or trial balance is loaded; reference data and clients pre-loaded before it stay loaded and are harmless because legacy stays the system of record until go-live.

Table 15: Rollback procedure

| Step | Name | Action | Owner |
| --- | --- | --- | --- |
| RB-1 | Stop | The go / no-go board records NO-GO (or a failure before T 18:00 that the board judges unrecoverable). The Program Manager announces the rollback on the bridge. | GNG |
| RB-2 | Lock BIBS | Disable business logins to BIBS; stop the scheduled jobs (PAYMENT_AUTOMATCH, payment file handlers, Renewal extraction, e-mail dispatch). | IDO |
| RB-3 | Capture | If business transactions were keyed in BIBS after 08:00 on T, export them (receipts, applications, bookings) with MIG-CUTOVER-STATUS and the Operations reports for re-keying in legacy. | IML |
| RB-4 | Restore | Restore the production database to the rollback-point snapshot (CT-037); restore the object store for attachments of the same time; verify the restore (row counts of key tables, application start). | IDO |
| RB-5 | Reopen legacy | Set EBIX, QPS and CMS back to read-write; re-enable the legacy batch jobs; confirm the last legacy EOD is intact. | BIT |
| RB-6 | Re-key | Operations re-keys in legacy the transactions captured in RB-3, with the BIBS AR numbers voided in the receipt register. | OPS |
| RB-7 | Communicate | Send the rollback notice to users, branches, insurers and bank channels (communication plan item 7). | PM |
| RB-8 | Review | Within 2 business days - root cause, new go-live date, which mocks to repeat; purge the production staging of the failed cutover within 5 days. | PM |

After the point of no return, there is no technical rollback. A defect is fixed forward in BIBS through the normal business functions (correction, reversal, adjustment), with the change visible in the Prod Recon legacy change report where it touches a legacy invoice.

# 7 Communication plan

Table 16: Communication plan

| # | Message | Audience | Channel | When | Owner |
| --- | --- | --- | --- | --- | --- |
| 1 | Go-live date, freeze and what changes for each department | All BDOI users, branch heads | E-mail from the Program Manager; team briefings | T-21 | PM |
| 2 | Payments after go-live - legacy invoice numbers stay valid; new invoices are BI- numbers | Insurers, BDO bank channels (bills payment, CLPC, direct credit), corporate clients | Letter / e-mail from Operations | T-21 | OPS |
| 3 | Freeze of reference data and the change request route | Product, Marketing and Operations maintainers | E-mail from the Data Migration Lead | T-8 | DML |
| 4 | Training schedule and log-in instructions | All BIBS users per persona | E-mail; training calendar | T-20 | PM |
| 5 | Legacy freeze at T-3 22:00; BIBS opens T 08:00; what to do with urgent items during the weekend | All users, branches, insurers | E-mail; branch notice | T-4 | PM |
| 6 | Go-live confirmed; support channels and hypercare contacts | All users | E-mail; intranet | T-1 19:00 | PM |
| 7 | Rollback notice (only if NO-GO) - legacy stays in use; next steps | All users, branches, insurers, bank channels | E-mail; phone tree for branch heads | T-1 on NO-GO | PM |
| 8 | Daily hypercare status | Go / no-go board, department heads | Daily report and bridge call 17:00 | T to hypercare exit | IPM |
| 9 | Hypercare exit and hand-over to production support | All users, IT | E-mail | At exit | PM |

# 8 Hypercare

Hypercare runs from go-live to the first month-end close with the legacy control accounts (about T+30). The command centre stays open to T+5, then the daily 17:00 call continues until exit.

Daily checks (task CT-065): Migration Clearing 0.00 per branch and currency; legacy control accounts against their sub-ledgers (ACSL, context LEGACY); automatch runs and the unapplied items they left; payment file results; exception queues (rejected receipts, remittance exclusions, failed postings); failed jobs and alerts; open defects by severity; user tickets by department.

## 8.1 Roster

Table 17: Hypercare roster (names in the task plan, sheet Hypercare Roster)

| Function | Who | Coverage | Escalates to |
| --- | --- | --- | --- |
| Command centre lead | iorta TechNXT Project Manager | 07:00-20:00 T to T+5; 08:00-18:00 after | Program Manager |
| Migration and reconciliation | iorta Migration Lead; Migration Operator | 07:00-22:00 T to T+5; business hours after | iorta Project Manager |
| Application support (L2 / L3) | iorta developers - Operations, Accounting, CRM, Renewal | 07:00-20:00 T to T+5; on call to 22:00 | iorta Project Manager |
| Infrastructure | iorta DevOps | 24 x 7 on call T-3 to T+5; business hours after | iorta Project Manager |
| Business floor support | BDOI super-users per department (Cashiering, Remittance, Collections, Accounting, Marketing) | Branch hours T to T+10 | Data Migration Lead |
| Comptrollership | Reconciliation approver; GL lead | Daily 16:00 check T to first month-end | Head, Comptrollership |
| Legacy systems | BDOI IT legacy administrator | Business hours; on call T-3 to T+1 | BDOI IT head |
| Service desk (L1) | BDOI service desk | Service hours | BDOI IT head |

## 8.2 Exit criteria

Table 18: Hypercare exit criteria

| # | Exit criterion |
| --- | --- |
| 1 | No open Critical or High defect; Medium defects have an agreed fix date |
| 2 | Migration Clearing 0.00 and legacy control accounts equal their sub-ledgers on 10 consecutive business days |
| 3 | First month-end close completed with the ACSL GL-SL reconciliation (context LEGACY) without difference |
| 4 | Payment files, automatch, remittance, DPPR / PR2307 batches and endorsements on legacy invoices each processed at least once in production without incident |
| 5 | Staging and extract files of production purged within 5 days of sign-off (purge log) |
| 6 | Service desk ticket volume back to the level agreed in the support model; production support runbook (deliverable 24) accepted |

# 9 Decommissioning checklists

A legacy system is decommissioned only when every item of its checklist is met and signed (FR-DM-123; DMQ27). The legacy context in BIBS closes separately, when the legacy positions have run off.

Table 19: Decommissioning checklist - EBIX

| # | Criterion |
| --- | --- |
| 1 | Final extracts reconciled and signed off (F01, F02, F03, F04, F06, G01, C01) |
| 2 | Archive objects H01, H02 and G02 of EBIX loaded and reconciled (counts and hash totals per record type against legacy) |
| 3 | Legacy Inquiry verified by Audit / Compliance on samples of each record type |
| 4 | No open legacy invoice or legacy UPP that needs an EBIX document; the legacy context in BIBS may still be open |
| 5 | Claims tail covered - no open claim that needs EBIX (DMQ27, DMQ30) |
| 6 | Read-only access logs exported to the archive |
| 7 | Database backup retained per the retention decision (DMQ27); retention obligations covered (5 years online, 15 years archive, umbrella p.45) |
| 8 | Sign-off by the EBIX system owner, Compliance and Comptrollership |

Table 20: Decommissioning checklist - QPS

| # | Criterion |
| --- | --- |
| 1 | Final extracts reconciled and signed off (C01, P01, P03, R objects) |
| 2 | Last QPS-issued policy expired and its renewal decided (run-off tracker shows no open cohort), or the policy is archived |
| 3 | Archive objects of QPS loaded and reconciled |
| 4 | Legacy Inquiry verified by Audit / Compliance |
| 5 | Read-only access logs exported; database backup retained per DMQ27 |
| 6 | Sign-off by the QPS system owner, Compliance and the Heads of Marketing |

Table 21: Decommissioning checklist - ISYS

| # | Criterion |
| --- | --- |
| 1 | Claims and ACSL reports and the Marketing Diary no longer needed (replaced by BIBS reports) |
| 2 | GL history (G02) and closed claims (H01 CLAIM) archived and reconciled |
| 3 | Sign-off by the ISYS system owner, Claims and Comptrollership |

Table 22: Decommissioning checklist - CMS

| # | Criterion |
| --- | --- |
| 1 | Collection state F03 and UPP F02 reconciled and signed off |
| 2 | Disposition history archived (H01) if required by DMQ34 |
| 3 | Sign-off by the Head of Operations (Collections) and BDOI IT |

Table 23: Decommissioning checklist - Excel masterlists and file shares

| # | Criterion |
| --- | --- |
| 1 | Submitted-policy masterlists migrated (P04) or archived |
| 2 | KYC documents and legacy documents (C04, H02) archived with checksums |
| 3 | Folders set to read-only, then removed per the retention decision |
| 4 | Sign-off by the owning department and Compliance |

Table 24: Decommissioning checklist - Legacy context in BIBS

| # | Criterion |
| --- | --- |
| 1 | No open legacy invoice (paid, reversed, written off or reclassified) |
| 2 | No legacy UPP with a balance |
| 3 | Legacy control accounts and Migration Clearing at 0.00 |
| 4 | Comptrollership decides whether the legacy accounts are closed in the chart |

# Sign-off

By signing, BDOI approves this runbook as the plan of the production cutover. The go-live date, the named people and the measured durations are added in version 1.1 after the dress rehearsal.

| Name | Role | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
|  | Program Manager, Business Project Services (chair, go / no-go board) | BDO Unibank ESG |  |  |
|  | Data Migration Lead | BDOI |  |  |
|  | Head, Operations | BDOI |  |  |
|  | Head, Comptrollership | BDOI |  |  |
|  | Head, BDOI IT | BDOI |  |  |
|  | Project Manager | iorta TechNXT |  |  |