## Cover
CUTOVER RUNBOOK - TASK PLAN
Cutover Task Plan
BRD-13 Data Migration - production cutover from T-30 to hypercare exit
BIBS – BDOI Broker System
Client | BDO Insurance and Reinsurance Brokers, Inc.
BRD | BRD-13
Version | 1.2
Date | 26 September 2026
Classification | Confidential
Prepared by | iorta TechNXT
Sheets
Sheet | Content | Rows
README | What each column of each sheet means, with the allowed values
Tasks | Cutover tasks with owner, duration, predecessors and verification | 95
Roles | Owner roles | 16
Phases | Cutover phases | 8
Calendar | Relative days mapped to the calendar of the recommended go-live (DMQ25, DMQ39) | 26
Checkpoints | Go / no-go checkpoints and their criteria | 35
Freeze Windows | Freeze windows | 6
Rollback | Rollback procedure (only on NO-GO or before the point of no return) | 8
Communication | Communication plan | 12
Hypercare Roster | Hypercare roster | 9
Hypercare Exit | Hypercare exit criteria | 8
Decommissioning | Decommissioning checklist per legacy system (BRID 12.1; DMQ27) | 31
Legend
DONE | Task completed and verified
IN PROGRESS | Task running
BLOCKED | Task cannot start or finish
N/A | Not needed in this cutover
T = go-live: January 2028 (BDOI timeline), recommended Monday 3 January 2028 at the year-end boundary (DMQ25; DMQ39 option A, awaiting Comptrollership confirmation). Days are calendar days; times are Philippine time; the sheet Calendar gives the date of each relative day.
The same plan is loaded in the Migration Console (plan kind PRODUCTION); the console records actual times and evidence (FR-DM-120).
Prepared by iorta TechNXT for BDOI. Confidential – BDOI.

## README
README – columns of each sheet
Cutover Task Plan, version 1.2. Drop-down columns accept only the listed values.
Sheet | Column | Meaning | Allowed values
Tasks | Task | Task ID
Tasks | Phase | Phase of the cutover
Tasks | Day | Day relative to go-live (T)
Tasks | Start (PHT) | Planned start time
Tasks | Task | What is done
Tasks | Owner | Accountable role (sheet Roles)
Tasks | Hours | Planned elapsed hours
Tasks | Predecessors | Tasks that must be complete first
Tasks | Verification / evidence | How completion is proven
Tasks | Checkpoint | Go / no-go checkpoint or milestone
Tasks | Assignee (name) | Named person
Tasks | Actual start | Date and time
Tasks | Actual end | Date and time
Tasks | Status | Task status | NOT STARTED, IN PROGRESS, DONE, BLOCKED, N/A
Roles | Code | Role code used in the Owner column
Roles | Role | Role
Roles | Organisation | Organisation
Roles | Name (to fill) | Named person and phone
Phases | Phase | Phase code
Phases | Name | Phase
Phases | When | Days
Calendar | Day | Day relative to go-live (T)
Calendar | Date (T = 3-Jan-2028) | Calendar date for the recommended go-live
Calendar | Note | Holiday or year-end note
Checkpoints | Checkpoint | Checkpoint
Checkpoints | When | Day and time
Checkpoints | Decision | What is decided
Checkpoints | # | Criterion no.
Checkpoints | Criterion | Criterion that must be met
Checkpoints | Measured value | Value at the decision
Checkpoints | Met | Y / N | Y, N
Freeze Windows | Freeze | What is frozen
Freeze Windows | From | Start
Freeze Windows | Until | End
Freeze Windows | Scope | What may not change
Freeze Windows | Exception route | How an urgent change is handled
Rollback | Step | Step
Rollback | Name | Step name
Rollback | Action | What is done
Rollback | Owner | Role
Rollback | Done at | Date and time
Communication | # | Item
Communication | Message | What is said
Communication | Audience | Who receives it
Communication | Channel | How
Communication | When | Day
Communication | Owner | Role
Communication | Sent on | Date
Hypercare Roster | Function | Support function
Hypercare Roster | Who | Team
Hypercare Roster | Coverage | Hours
Hypercare Roster | Escalates to | Escalation
Hypercare Roster | Names and phone (to fill) | Named people
Hypercare Exit | # | Criterion
Hypercare Exit | Exit criterion | Criterion
Hypercare Exit | Met | Y / N | Y, N
Hypercare Exit | Evidence | Report or sign-off
Decommissioning | Legacy system | System or context
Decommissioning | # | Criterion
Decommissioning | Criterion | Criterion
Decommissioning | Evidence | Report, log or sign-off
Decommissioning | Signed by / date | Signer
Decommissioning | Status | Status | OPEN, DONE, N/A

## Tasks
Tasks
Cutover tasks with owner, duration, predecessors and verification
Task | Phase | Day | Start (PHT) | Task | Owner | Hours | Predecessors | Verification / evidence | Checkpoint | Assignee (name) | Actual start | Actual end | Status
CT-001 | A Readiness | T-30 |  | Confirm the dress rehearsal met its exit criteria (all objects loaded and reconciled L1-L5, window met with 20 percent margin, rollback rehearsed, go-live renewal extraction run) | DML | 4 |  | Dress rehearsal report signed by the Data Migration Lead and the iorta Migration Lead |  |  |  |  | NOT STARTED
CT-002 | A Readiness | T-30 |  | Confirm the go-live date, the freeze start (last legacy EOD) and the blackout dates (DMQ25) with Comptrollership's confirmation of the year-end option A (DMQ39); publish the cutover calendar | PM | 2 | CT-001 | Calendar approved by the Program Manager and circulated; option A confirmed in writing by the Head of Comptrollership |  |  |  |  | NOT STARTED
CT-003 | A Readiness | T-29 |  | Name the cutover team, the command centre room and bridge line, and the hypercare roster (section Hypercare) | PM | 4 | CT-002 | Roster with names and phone numbers in the runbook annex |  |  |  |  | NOT STARTED
CT-004 | A Readiness | T-28 |  | Freeze the production cutover plan in the Migration Console (plan kind PRODUCTION, tasks and owners from this list) | IML | 4 | CT-002 | MIG-CUTOVER-STATUS shows the plan with every task owned |  |  |  |  | NOT STARTED
CT-005 | A Readiness | T-28 |  | Production environment ready - BIBS release of the go-live release deployed, MIG_ENVIRONMENT_CLASS = PRODUCTION, MIG_CUTOVER_DATE = T, MIG_OPENING_VALUE_DATE = 1-Jan-2028, MIG_GOLIVE_RENEWAL_TO = 31-May-2028, MIG_RENEWAL_URGENT_TO = 31-Jan-2028, jobs scheduled | IDO | 8 |  | Deployment record; parameter screen; job list |  |  |  |  | NOT STARTED
CT-006 | A Readiness | T-27 |  | Grant the migration roles in production (DATA_MIGRATION_LEAD, DATA_STEWARD, DATA_OWNER, MIGRATION_OPERATOR, MIGRATION_RECON_APPROVER, MIGRATION_GONOGO), the true-up permissions (MIG_TRUEUP_PREPARE, MIG_TRUEUP_APPROVE) and the P03 permissions of the Renewal processing team (MIG_DQ_RESOLVE, MIG_RESUBMIT_APPROVE) through User Access requests; check PH-only network access | IDO | 8 | CT-005 | User Access approvals; access test from an allowed and a blocked location |  |  |  |  | NOT STARTED
CT-007 | A Readiness | T-25 |  | Comptrollership sets up in production the legacy control accounts, Migration Clearing, the LG_ accounting rule lines (DMQ18) and the retained earnings account of the opening, through maker-checker | COMP | 16 | CT-005 | Chart and accounting rules approved; test posting in the dress rehearsal environment matched |  |  |  |  | NOT STARTED
CT-008 | A Readiness | T-25 |  | Approve the final code map versions for production (all sets, including the PACKAGE map loaded for Renewal); record versions in the plan | OWN | 16 |  | MIG-MAP-VERSIONS lists one APPROVED version per set |  |  |  |  | NOT STARTED
CT-009 | A Readiness | T-24 |  | Users of every persona created and trained; BIBS menus checked per persona (UAT readiness items 1 and 14) | PM | 40 | CT-006 | User list; training attendance; persona menu check |  |  |  |  | NOT STARTED
CT-010 | A Readiness | T-21 |  | Communicate the go-live and freeze to branches, insurers and bank channels (autopay files carry the legacy invoice number after go-live) | PM | 4 | CT-002 | Communications sent (communication plan items 1-6) |  |  |  |  | NOT STARTED
CT-011 | A Readiness | T-21 |  | Legacy December soft close - accruals and cut-offs, bank reconciliations, sub-ledger to GL reconciliations, known year-end adjustments posted - completed by 20 December 2027 (T-14) | COMP | 56 |  | Soft-close checklist signed by the Head of Comptrollership on 20 Dec 2027 |  |  |  |  | NOT STARTED
CT-012 | A Readiness | T-20 |  | Legacy clean-up drives - UPP with no reference, invoices open more than 5 years, duplicate clients flagged in Trial migration 3, unmapped codes | STW | 80 |  | Clean-up tracker; counts reduced against Trial migration 3 profiling |  |  |  |  | NOT STARTED
CT-013 | A Readiness | T-20 |  | Renewal processing team ready for the January expiries - staffing plan for January (handlers, overtime, back-up) signed; BIBS Renewal training completed; day-1 priority queue worked on the Trial migration 4 and dress-rehearsal data; draft RA-sent file from the Excel trackers validated and its rejects reviewed (maker-checker) | RNW | 16 | CT-009 | Staffing plan signed by the Head of the Renewal processing team; draft P03 validated; rejects corrected and approved |  |  |  |  | NOT STARTED
CT-014 | A Readiness | T-18 |  | SFTP drop or console upload path tested end to end from BDOI IT with a masked file; checksum verified | BIT | 4 | CT-005 | Test extract accepted and purged |  |  |  |  | NOT STARTED
CT-015 | A Readiness | T-15 |  | Go / no-go checkpoint GNG-1 (readiness to start the pre-load) | GNG | 2 | CT-001, CT-004, CT-006, CT-007, CT-008, CT-013, CT-014 | Decision recorded in the console with the GNG-1 criteria | GNG-1 |  |  |  | NOT STARTED
CT-016 | B Pre-load and daily deltas | T-14 | 08:00 | Take a production database snapshot before the pre-load | IDO | 1 | CT-015 | Snapshot ID recorded in the plan |  |  |  |  | NOT STARTED
CT-017 | B Pre-load and daily deltas | T-14 | 09:00 | Extract and send R01-R08 and R11 (current values; R06 is the PACKAGE map prepared by TSU) with control files | BIT | 6 | CT-016 | Files received; intake checks passed (extract status CHECKED) |  |  |  |  | NOT STARTED
CT-018 | B Pre-load and daily deltas | T-14 | 15:00 | Validate and load reference data R01-R08 (R06 into the Renewal package map); authorise CREATE values in each master | IOP | 8 | CT-017 | Batches LOADED; MIG-UNMAPPED-CODES empty for R objects |  |  |  |  | NOT STARTED
CT-019 | B Pre-load and daily deltas | T-13 |  | Reconcile and sign off the reference objects (G5, G6) | DML | 6 | CT-018 | MIG-SIGNOFF-STATUS shows G6 for R01-R08 |  |  |  |  | NOT STARTED
CT-020 | B Pre-load and daily deltas | T-13 |  | Load payees R09 if in scope (DMQ30) | IOP | 4 | CT-019 | Batch SIGNED_OFF |  |  |  |  | NOT STARTED
CT-021 | B Pre-load and daily deltas | T-12 |  | Extract and send the full client extract C01, C02, C03 (as of the previous EOD) | BIT | 8 | CT-019 | Files CHECKED; counts against the Trial migration 4 volumes within 5 percent |  |  |  |  | NOT STARTED
CT-022 | B Pre-load and daily deltas | T-12 |  | Validate clients; run matching; clear the review queue | STW | 24 | CT-021 | Review queue empty; MIG-CLIENT-MATCH reviewed |  |  |  |  | NOT STARTED
CT-023 | B Pre-load and daily deltas | T-11 |  | Load clients C01-C03; reconcile L1-L4; business sample checks; sign off (G5, G6) | IOP | 16 | CT-022 | MIG-RECON-SUMMARY all MATCHED or EXPLAINED; G6 signed |  |  |  |  | NOT STARTED
CT-024 | B Pre-load and daily deltas | T-11 |  | Daily client delta (new and changed clients of the day) from T-11 to T-5 - extract 23:00, load 00:30 (job MIG_CLIENT_DELTA) | BIT | 1 | CT-023 | Delta batch SIGNED_OFF each morning by 07:00 |  |  |  |  | NOT STARTED
CT-025 | B Pre-load and daily deltas | T-12 |  | Complete legacy remittance batches in process, or tag the holds and special remittances that carry forward (DMQ21) | OPS | 40 |  | List of carried items for F04 agreed by Operations - Remittance |  |  |  |  | NOT STARTED
CT-026 | B Pre-load and daily deltas | T-12 |  | Complete in-flight legacy items where possible - pending endorsements, un-booked accounts, renewals placed or bound in legacy and not yet booked (booked before the freeze so that the new term migrates as a header), check pick-ups, refunds (DMQ33) | OPS | 40 |  | In-flight list reduced; the rest listed for carry-forward or re-keying |  |  |  |  | NOT STARTED
CT-027 | B Pre-load and daily deltas | T-7 |  | Code map freeze - no new legacy code without a change request and a map version | OWN | 1 | CT-019 | Freeze notice sent; change log opened |  |  |  |  | NOT STARTED
CT-028 | B Pre-load and daily deltas | T-7 |  | Legacy reference-data change freeze in EBIX and QPS (insurers, products, packages, AOs, branches) | BIT | 1 | CT-027 | Maintenance screens locked or change log reviewed daily |  |  |  |  | NOT STARTED
CT-029 | B Pre-load and daily deltas | T-7 |  | Dry run of the final extract jobs on the current day's data (timing and control files; P01 covers every expiry to 31-May-2028 and every booked renewal term starting on or after T) | BIT | 6 | CT-017 | Extract timings within the plan; control files correct; P01 dry run checked against the legacy in-force list |  |  |  |  | NOT STARTED
CT-030 | B Pre-load and daily deltas | T-5 |  | Go / no-go checkpoint GNG-2 (enter the legacy freeze) | GNG | 2 | CT-013, CT-023, CT-024, CT-025, CT-026, CT-029 | Decision recorded with the GNG-2 criteria | GNG-2 |  |  |  | NOT STARTED
CT-031 | B Pre-load and daily deltas | T-5 |  | Announce the freeze and the Monday opening to all users, branches and insurers | PM | 1 | CT-030 | Communication plan item 7 sent |  |  |  |  | NOT STARTED
CT-032 | B Pre-load and daily deltas | T-5 | 17:00 | Last legacy business day - last business transactions; cashiers deposit and close; UPP of the day recorded (30 and 31 December are holidays, DMQ39) | OPS | 3 | CT-030 | Branch close checklist from every branch |  |  |  |  | NOT STARTED
CT-033 | B Pre-load and daily deltas | T-5 | 18:00 | Final RA-sent file (P03) compiled from the Excel trackers with the RAs sent up to the last business day (maker); the checker compares it with the trackers and releases it; trackers closed for new RAs | RNW | 3 | CT-032 | File and control file ready; checker's release recorded |  |  |  |  | NOT STARTED
CT-034 | B Pre-load and daily deltas | T-5 | 18:00 | Name the Comptrollership users who may post FY2027 closing and audit adjustments in the legacy GL after the freeze; open the FY2027 adjustment register | COMP | 2 | CT-030 | Access list signed by the Head of Comptrollership; register opened |  |  |  |  | NOT STARTED
CT-035 | C Legacy freeze and final extracts | T-3 | 20:00 | Last legacy EOD (EBIX, QPS, ISYS, CMS); preliminary December 2027 trial balance run | BIT | 2 | CT-032 | EOD logs complete without error; preliminary TB printed per branch and currency |  |  |  |  | NOT STARTED
CT-036 | C Legacy freeze and final extracts | T-3 | 22:00 | Legacy business freeze - EBIX, QPS, CMS business modules set to read-only; batch jobs that post are disabled; legacy GL restricted to the named Comptrollership users and to FY2027 periods (FY2028 periods are not opened in legacy) | BIT | 1 | CT-035, CT-034 | Test posting refused in each business module and by a GL user not on the list; job list shows disabled jobs | FREEZE |  |  |  | NOT STARTED
CT-037 | C Legacy freeze and final extracts | T-3 | 22:15 | Final client delta (last changes of the day) extracted and loaded | IOP | 2 | CT-036 | Last delta batch SIGNED_OFF |  |  |  |  | NOT STARTED
CT-038 | C Legacy freeze and final extracts | T-3 | 22:30 | Final extracts after the EOD - P01, P01S, P03 (the RA-sent file of the Renewal processing team), F01, F01S, F01C, F02, F03, F04, F06, R11 (final numbers), G01 preliminary December TB (version PROVISIONAL) | BIT | 5 | CT-036, CT-033 | Every file and control file in the intake; SHA-256 recorded |  |  |  |  | NOT STARTED
CT-039 | C Legacy freeze and final extracts | T-3 | 23:30 | Comptrollership signs the preliminary December trial balance as the provisional opening - balanced per branch and currency, with the FY2027 result per branch and currency | COMP | 2 | CT-035 | Signed TB totals and FY2027 result per branch and currency |  |  |  |  | NOT STARTED
CT-040 | D Production load | T-2 | 02:00 | Take the production database snapshot - the rollback point | IDO | 1 | CT-037, CT-038 | Snapshot ID and restore test of the snapshot metadata recorded | ROLLBACK POINT |  |  |  | NOT STARTED
CT-041 | D Production load | T-2 | 03:00 | Intake checks of all final extracts (checksum, layout, row count, control totals, hash totals) | IOP | 1 | CT-040 | Every extract CHECKED; rejected files re-sent within 1 hour |  |  |  |  | NOT STARTED
CT-042 | D Production load | T-2 | 04:00 | Validate P01 and P01S; resolve issues; approve load (G3, G4) | IOP | 2 | CT-041 | Error rate within the master threshold; every expiry to 31-May-2028 present against the legacy in-force list; G4 signed by the Data Migration Lead |  |  |  |  | NOT STARTED
CT-043 | D Production load | T-2 | 06:00 | Load policy headers P01; reconcile L1-L4 | IOP | 3 | CT-042 | MIG-RECON-SUMMARY for P01 MATCHED |  |  |  |  | NOT STARTED
CT-044 | D Production load | T-2 | 06:00 | Validate F01, F01S, F01C; resolve issues; approve load (G3, G4) | IOP | 3 | CT-041 | 0 financial errors or owner-approved exclusions with manual-entry plan |  |  |  |  | NOT STARTED
CT-045 | D Production load | T-2 | 09:00 | Load open legacy invoices F01 with opening entries MIG_LEGACY_INVOICE_OPENING | IOP | 5 | CT-043, CT-044 | Batch LOADED without rejects |  |  |  |  | NOT STARTED
CT-046 | D Production load | T-2 | 09:00 | Validate and load UPP F02 with opening entries MIG_UPP_OPENING | IOP | 3 | CT-041, CT-023 | Batch LOADED without rejects |  |  |  |  | NOT STARTED
CT-047 | D Production load | T-2 | 14:00 | Load collection state F03, remittance items F04, PDCs and pick-ups F06 | IOP | 3 | CT-045 | Batches LOADED |  |  |  |  | NOT STARTED
CT-048 | D Production load | T-2 | 15:00 | Load the provisional GL opening G01 - OPENING journals per branch and currency, value date 1-Jan-2028; balance-sheet lines; FY2027 result to retained earnings; legacy control-account lines to Migration Clearing | IOP | 2 | CT-039, CT-045, CT-046 | Journals posted and flagged PROVISIONAL; balance sheet in BIBS equals the preliminary TB; P&L accounts 0.00 |  |  |  |  | NOT STARTED
CT-049 | D Production load | T-2 | 16:00 | Validate and load the RA-sent file P03; send MIG-REJECTS of P03 to the Renewal processing team (maker and checker) | IOP | 2 | CT-043 | Batch LOADED or LOADED_WITH_REJECTS; rejection report with correction columns sent |  |  |  |  | NOT STARTED
CT-050 | D Production load | T-2 | 17:00 | Update the receipt series R11 to the final next numbers | IOP | 1 | CT-041 | Next AR / OR numbers = legacy last used + 1 per branch |  |  |  |  | NOT STARTED
CT-051 | D Production load | T-2 | 18:00 | Reconcile L1-L4 of every financial object; run L5 - Migration Clearing per branch and currency, legacy control accounts vs sub-ledgers (ACSL, context LEGACY) | IML | 4 | CT-047, CT-048 | MIG-GL-CLEARING shows 0.00 per branch and currency |  |  |  |  | NOT STARTED
CT-052 | D Production load | T-2 | 22:00 | Explain or fix every break (rerun batches); reconciliation approver signs G5 per object | COMP | 6 | CT-051 | MIG-RECON-SUMMARY all MATCHED or EXPLAINED with approval |  |  |  |  | NOT STARTED
CT-053 | E Reconciliation, verification and go / no-go | T-1 | 06:00 | Start the full sanction screening run of migrated clients (SCR_PERIODIC_SCREENING, full rescreen) | IOP | 6 | CT-023 | Run completed; hits in the screening queue for Compliance |  |  |  |  | NOT STARTED
CT-054 | E Reconciliation, verification and go / no-go | T-1 | 07:00 | Business verification of samples per object on the BIBS screens (Reconciliation Approach, sample plan); data owners sign G6 | OWN | 6 | CT-052 | Sample checklists signed; G6 for every Day-1 object |  |  |  |  | NOT STARTED
CT-055 | E Reconciliation, verification and go / no-go | T-1 | 08:00 | P03 rejects - the maker corrects each row and prepares the resubmission; the checker approves it by 12:00 (MIG_RESUBMIT_DEADLINE); the operator loads the rerun batch; rows still rejected are listed for the day-1 queue | RNW | 4 | CT-049 | Resubmission approved by a checker other than the maker; rerun reconciled; list of rows still rejected |  |  |  |  | NOT STARTED
CT-056 | E Reconciliation, verification and go / no-go | T-1 | 09:00 | Business smoke test on production with test-marked transactions reversed afterwards - OTC payment preview on a legacy invoice, automatch preview, remittance extraction preview, Invoice 360, client and policy search by legacy reference | IQA | 4 | CT-052 | Smoke test checklist passed; no posting left open |  |  |  |  | NOT STARTED
CT-057 | E Reconciliation, verification and go / no-go | T-1 | 13:00 | Check jobs, alerts and integrations for Monday (Renewal go-live extraction at T 04:00, PAYMENT_AUTOMATCH hourly, payment file handlers, daily Renewal extraction, e-mail) | IDO | 2 | CT-056 | Job schedule and alert routing checked |  |  |  |  | NOT STARTED
CT-058 | E Reconciliation, verification and go / no-go | T-1 | 15:00 | Prepare the go / no-go pack - MIG-GONOGO with measured criteria, open issues, sign-off status | IML | 2 | CT-053, CT-054, CT-055, CT-056, CT-057 | Pack circulated to the board by 17:00 |  |  |  |  | NOT STARTED
CT-059 | E Reconciliation, verification and go / no-go | T-1 | 18:00 | Go / no-go decision GNG-3 (go-live) | GNG | 1 | CT-058 | Decision recorded in the console with every criterion value | GNG-3 |  |  |  | NOT STARTED
CT-060 | E Reconciliation, verification and go / no-go | T-1 | 19:00 | If NO-GO - execute the rollback procedure (section Rollback) and reopen legacy for Monday | IDO | 6 | CT-059 | Legacy open for business Monday 08:00; BIBS restored to the rollback point |  |  |  |  | NOT STARTED
CT-061 | E Reconciliation, verification and go / no-go | T-1 | 19:00 | If GO - send the go-live notice; open BIBS roles for business users from 06:00 Monday | PM | 1 | CT-059 | Communication plan item 8 sent |  |  |  |  | NOT STARTED
CT-062 | F Go-live | T | 04:00 | Renewal go-live extraction - a candidate for every migrated header expiring 3-Jan to 31-May-2028 that was not renewed in legacy; priority by expiry date, January expiries flagged URGENT; RAs already sent recorded from P03; extraction check MIG-RENEWAL-GOLIVE | IOP | 2 | CT-061 | MIG-RENEWAL-GOLIVE balances for every month January-May 2028; URGENT count = January headers |  |  |  |  | NOT STARTED
CT-063 | F Go-live | T | 06:00 | Enable business logins; confirm legacy business modules stay read-only; legacy links shown in BIBS | IDO | 1 | CT-061 | Log-in test per persona; legacy posting refused |  |  |  |  | NOT STARTED
CT-064 | F Go-live | T | 07:00 | Command centre opens; hypercare roster on duty | IPM | 1 | CT-063 | Attendance on the bridge |  |  |  |  | NOT STARTED
CT-065 | F Go-live | T | 08:00 | BIBS open for business | PM | 0 | CT-064 | First transactions observed in each branch | GO-LIVE |  |  |  | NOT STARTED
CT-066 | F Go-live | T | 08:00 | Renewal processing team works the day-1 priority queue - URGENT January expiries first, earliest expiry first; insurer requests and RAs for the expiries without an RA; the tracker is checked first for rows still rejected in P03 | RNW | 10 | CT-062, CT-065 | End-of-day count of URGENT candidates with an RA sent or an insurer request made |  |  |  |  | NOT STARTED
CT-067 | F Go-live | T | 09:00 | First payment file uploads and the first automatch run including migrated UPP; review results | OPS | 2 | CT-065 | Run summary; legacy and new postings in the right accounts |  |  |  |  | NOT STARTED
CT-068 | F Go-live | T | 12:00 | Midday check - issues, queues, Migration Clearing still 0.00, no legacy business posting | IML | 1 | CT-065 | Midday report to the board |  |  |  |  | NOT STARTED
CT-069 | F Go-live | T | 18:00 | End-of-day review - point of no return (DMQ32); decide continue or fallback | GNG | 1 | CT-068 | Decision recorded | POINT OF NO RETURN |  |  |  | NOT STARTED
CT-070 | F Go-live | T | 20:00 | First BIBS EOD jobs; check GL posting, sub-ledgers and the Cash Receipts Book | IDO | 2 | CT-069 | Job run log; CRB lists the day's receipts |  |  |  |  | NOT STARTED
CT-071 | G Hypercare and true-up 1 | T+1 |  | Daily hypercare check - Migration Clearing 0.00, legacy control accounts vs sub-ledgers, automatch results, exception queues, URGENT January renewals without an RA or insurer request, failed jobs (daily until exit) | IML | 1 | CT-070 | Daily hypercare report |  |  |  |  | NOT STARTED
CT-072 | G Hypercare and true-up 1 | T+1 |  | Issue triage twice a day (10:00 and 16:00) with Operations, Comptrollership, Renewal and iorta QA | IQA | 1 | CT-070 | Issue log updated; severity agreed |  |  |  |  | NOT STARTED
CT-073 | G Hypercare and true-up 1 | T+2 |  | First remittance extraction with legacy invoices for the main insurers; compare with the legacy remittance pattern | OPS | 4 | CT-070 | Schedules show legacy invoice numbers; OPS_REMITTANCE posts to DTIP legacy |  |  |  |  | NOT STARTED
CT-074 | G Hypercare and true-up 1 | T+3 |  | First Collections worklist refresh with legacy invoices; collectors confirm carried promises and assignments | OPS | 2 | CT-070 | Worklist counts agree with F03 |  |  |  |  | NOT STARTED
CT-075 | G Hypercare and true-up 1 | T+5 |  | Staging purge - payloads and intake files of the signed-off production batches deleted within 5 days (MIG_STAGING_PURGE) | IDO | 1 | CT-059 | No staging payload older than 5 days after sign-off; purge log |  |  |  |  | NOT STARTED
CT-076 | G Hypercare and true-up 1 | T+7 |  | Week-1 review with the board - issues, volumes, performance, renewal queue, user feedback | GNG | 2 | CT-071 | Minutes; actions |  |  |  |  | NOT STARTED
CT-077 | G Hypercare and true-up 1 | T+10 |  | First daily Renewal extraction that creates new candidates - expiry 1-Jun-2028 on 13-Jan-2028; headers already extracted at go-live are skipped | RNW | 1 | CT-062 | Candidates of 1-Jun-2028 created; no duplicate of a go-live candidate |  |  |  |  | NOT STARTED
CT-078 | G Hypercare and true-up 1 | T+10 |  | First DPPR or PR2307 legacy reversal batch (if any) approved and posted | COMP | 4 | CT-070 | Run report; legacy sub-ledgers reduced by the batch total |  |  |  |  | NOT STARTED
CT-079 | G Hypercare and true-up 1 | T+14 |  | Hypercare mid-point review against the exit criteria | GNG | 2 | CT-076 | Criteria status recorded | CHECKPOINT |  |  |  | NOT STARTED
CT-080 | G Hypercare and true-up 1 | T+15 |  | Legacy FY2027 year-end close completed by Comptrollership - closing adjustments posted in legacy, each entered in the FY2027 adjustment register | COMP | 8 | CT-036 | Register complete for the close; legacy post-close TB run |  |  |  |  | NOT STARTED
CT-081 | G Hypercare and true-up 1 | T+16 |  | Extract for true-up 1 - legacy TB after the close (G01, version TU1), adjustment journal lines since the freeze (G03), open-item detail of the lines on legacy control accounts (G03D), legacy journal listing since the freeze from the audit trail; control files | BIT | 4 | CT-080 | Every file and control file CHECKED |  |  |  |  | NOT STARTED
CT-082 | G Hypercare and true-up 1 | T+17 |  | Validate true-up 1 (cut-off, FY2027 dates, register, balance, mapping, open-item detail); the Comptrollership GL lead prepares and submits it | COMP | 6 | CT-081 | Validation without error; true-up 1 submitted |  |  |  |  | NOT STARTED
CT-083 | G Hypercare and true-up 1 | T+18 |  | Head of Comptrollership approves true-up 1; BIBS posts the opening-balance adjustment journals MIG-TU-1 (type OPENING, value date 1-Jan-2028) and the open-item adjustments | COMP | 2 | CT-082 | Journals posted; approver is not the preparer |  |  |  |  | NOT STARTED
CT-084 | G Hypercare and true-up 1 | T+18 |  | Reconcile true-up 1 (MIG-TRUEUP-RECON) - cut-off; movement = legacy TB change = register; BIBS opening = legacy post-close TB; Migration Clearing 0.00; legacy control accounts = sub-ledgers; the Head of Comptrollership signs | COMP | 4 | CT-083 | All checks met; true-up 1 signed |  |  |  |  | NOT STARTED
CT-085 | G Hypercare and true-up 1 | T+30 |  | First month-end close with legacy control accounts; ACSL GL-SL reconciliation with context LEGACY | COMP | 16 | CT-079, CT-084 | ACSL reconciliation without difference; FRBS schedules include legacy balances; opening balances include true-up 1 |  |  |  |  | NOT STARTED
CT-086 | G Hypercare and true-up 1 | T+30 |  | Hypercare exit decision | GNG | 2 | CT-085 | Exit criteria met; hand-over to production support (L1 / L2 / L3) | HYPERCARE EXIT |  |  |  | NOT STARTED
CT-087 | H Final true-up and legacy GL close | T+60 |  | Interim true-up 2 when Comptrollership has posted material FY2027 adjustments since true-up 1 - same steps as true-up 1; skipped when there are none | COMP | 16 | CT-084 | True-up 2 signed, or 'none' recorded by the Head of Comptrollership |  |  |  |  | NOT STARTED
CT-088 | H Final true-up and legacy GL close | T+85 |  | Auditor's adjustments agreed and posted in legacy; audited FY2027 financial statements signed (about March-April 2028; the date follows the audit timetable) | COMP | 16 | CT-080 | Audited FS; register complete with the AUDIT adjustments |  |  |  |  | NOT STARTED
CT-089 | H Final true-up and legacy GL close | T+92 |  | Extract for the final true-up - legacy audited TB (G01, version FINAL), adjustment lines since the previous true-up (G03), their open-item detail (G03D), legacy journal listing since the freeze; control files | BIT | 4 | CT-087, CT-088 | Every file and control file CHECKED |  |  |  |  | NOT STARTED
CT-090 | H Final true-up and legacy GL close | T+95 |  | Validate the final true-up; the Comptrollership GL lead prepares and submits it | COMP | 6 | CT-089 | Validation without error; final true-up submitted |  |  |  |  | NOT STARTED
CT-091 | H Final true-up and legacy GL close | T+99 |  | Head of Comptrollership approves the final true-up; January 2028 is reopened for the posting when closed; BIBS posts MIG-TU-F; January is closed again the same day | COMP | 4 | CT-090 | Journals posted; period reopen and close logged with the reason |  |  |  |  | NOT STARTED
CT-092 | H Final true-up and legacy GL close | T+99 |  | FY2027 BIR annual returns and the audited FS filed from legacy data by Comptrollership (not a BIBS task; BIBS is the source from FY2028) | COMP | 8 | CT-088 | Filing evidence recorded |  |  |  |  | NOT STARTED
CT-093 | H Final true-up and legacy GL close | T+100 |  | Reconcile the final true-up to the audited FY2027 TB (MIG-TRUEUP-RECON); re-run the February and March 2028 balance-sheet reports it changed; the Head of Comptrollership signs and shares the reconciliation with the external auditor | COMP | 8 | CT-091 | All checks met; final true-up signed; reports re-filed |  |  |  |  | NOT STARTED
CT-094 | H Final true-up and legacy GL close | T+106 |  | Lock the legacy GL for all users (FY2027 closed in legacy); close the FY2027 adjustment register | BIT | 2 | CT-093 | Test posting refused in the legacy GL; register closed |  |  |  |  | NOT STARTED
CT-095 | H Final true-up and legacy GL close | T+120 |  | Close the true-ups - final opening statement signed by the Head of Comptrollership and the Program Manager; opening journals no longer PROVISIONAL; a later FY2027 finding is a prior-period adjustment in BIBS outside the migration | PM | 2 | CT-094 | Closure recorded in the console | TRUE-UP CLOSED |  |  |  | NOT STARTED

## Roles
Roles
Owner roles
Code | Role | Organisation | Name (to fill)
PM | BDOI Program Manager (ESG - Business Project Services) | BDOI
DML | BDOI Data Migration Lead | BDOI
OWN | Data owners (department heads of each object) | BDOI
STW | Data stewards | BDOI
COMP | Comptrollership (reconciliation approver for financial objects) | BDOI
OPS | Operations (Financial Transactions, Cashiering, Remittance, Collections) | BDOI
MKT | Marketing (Retail and Corporate) | BDOI
RNW | Renewal processing team (makers and checkers; Head of the Renewal processing team) | BDOI
CMP | Compliance and Audit | BDOI
BIT | BDOI IT (legacy systems, extracts, network, SFTP) | BDOI
GNG | Go / no-go board (Program Manager, heads of Operations, Comptrollership, Marketing, Compliance, IT; iorta Project Manager) | BDOI and iorta TechNXT
IPM | iorta TechNXT Project Manager | iorta TechNXT
IML | iorta TechNXT Migration Lead (loaders, reconciliation, console) | iorta TechNXT
IOP | iorta TechNXT Migration Operator (intake, validation, loads) | iorta TechNXT
IDO | iorta TechNXT DevOps (AWS environment, snapshots, access, monitoring) | iorta TechNXT
IQA | iorta TechNXT QA (smoke tests, issue triage) | iorta TechNXT

## Phases
Phases
Cutover phases
Phase | Name | When
A | Readiness | T-30 to T-15 (4 to 19 Dec 2027)
B | Pre-load and daily deltas | T-14 to T-4 (20 to 30 Dec 2027)
C | Legacy freeze and final extracts | T-3 (Friday 31 Dec 2027)
D | Production load | T-2 (Saturday 1 Jan 2028)
E | Reconciliation, verification and go / no-go | T-1 (Sunday 2 Jan 2028)
F | Go-live | T (Monday 3 Jan 2028)
G | Hypercare and true-up 1 | T+1 to T+30 (4 Jan to 2 Feb 2028)
H | Final true-up and legacy GL close | T+31 to T+120 (Feb to 2 May 2028)

## Calendar
Calendar
Relative days mapped to the calendar of the recommended go-live (DMQ25, DMQ39)
Day | Date (T = 3-Jan-2028) | Note
T-30 | Sat 4 Dec 2027 | Dress rehearsal (15-26 Nov 2027) already done; reserve slot 6-10 Dec 2027 if its exit criteria were missed
T-26 | Wed 8 Dec 2027 | Feast of the Immaculate Conception (special non-working day) - the Comptrollership set-up (CT-007) is planned from T-25
T-21 | Mon 13 Dec 2027 | Communications to branches, insurers and bank channels; legacy December soft close under way
T-20 | Tue 14 Dec 2027 | Renewal processing team readiness - January staffing plan, training, day-1 queue rehearsed
T-15 | Sun 19 Dec 2027 | GNG-1 (board meets on Friday 17 December if preferred)
T-14 | Mon 20 Dec 2027 | December soft close complete; production pre-load of reference data starts
T-12 | Wed 22 Dec 2027 | Client extract; completion drives for remittance batches and in-flight items (moved from T-9, Christmas Day)
T-11 | Thu 23 Dec 2027 | Client load and sign-off; daily client deltas start (moved from T-10, Christmas Eve)
T-10 | Fri 24 Dec 2027 | Christmas Eve (special non-working day) - no task planned
T-9 | Sat 25 Dec 2027 | Christmas Day - no task planned
T-7 | Mon 27 Dec 2027 | Code map freeze; legacy reference-data change freeze
T-5 | Wed 29 Dec 2027 | Last legacy business day; GNG-2 (moved from T-4, Rizal Day); freeze announcement; final RA-sent file; legacy GL access list for FY2027 adjustments
T-4 | Thu 30 Dec 2027 | Rizal Day (regular holiday) - no task planned
T-3 | Fri 31 Dec 2027 | Last day of the year (special non-working day) - last legacy EOD; preliminary December TB; business freeze 22:00; legacy GL restricted to FY2027 adjustments; final extracts
T-2 | Sat 1 Jan 2028 | New Year's Day - production load, provisional GL opening (cut-over team on duty)
T-1 | Sun 2 Jan 2028 | Reconciliation, verification, P03 resubmissions until 12:00, GNG-3 at 18:00
T | Mon 3 Jan 2028 | Renewal go-live extraction 04:00; go-live 08:00; day-1 renewal priority queue; point of no return 18:00
T+10 | Thu 13 Jan 2028 | First daily Renewal extraction of new expiries (1 June 2028)
T+15 | Tue 18 Jan 2028 | Legacy FY2027 year-end close complete
T+18 | Fri 21 Jan 2028 | True-up 1 posted, reconciled and signed
T+30 | Wed 2 Feb 2028 | First month-end close (January 2028) completed; hypercare exit decision
T+60 | Fri 3 Mar 2028 | Interim true-up 2, only when needed
T+85 | Tue 28 Mar 2028 | Audited FY2027 financial statements (about March-April 2028; follows the audit timetable)
T+99 | Tue 11 Apr 2028 | Final true-up posted; FY2027 BIR annual returns filed from legacy
T+106 | Tue 18 Apr 2028 | Legacy GL locked
T+120 | Tue 2 May 2028 | True-ups closed

## Checkpoints
Checkpoints
Go / no-go checkpoints and their criteria
Checkpoint | When | Decision | # | Criterion | Measured value | Met
GNG-1 | T-15 | Start the production pre-load | 1 | Dress rehearsal completed within the window with at least 20 percent margin, rollback rehearsed
GNG-1 | T-15 | Start the production pre-load | 2 | Production environment, roles and PH-only access ready; masking off only in production
GNG-1 | T-15 | Start the production pre-load | 3 | Legacy control accounts, Migration Clearing and LG_ rule lines approved in production (DMQ18)
GNG-1 | T-15 | Start the production pre-load | 4 | Code map versions for production approved
GNG-1 | T-15 | Start the production pre-load | 5 | Transfer path (SFTP or console) tested
GNG-1 | T-15 | Start the production pre-load | 6 | December soft close on track for 20 December 2027
GNG-1 | T-15 | Start the production pre-load | 7 | Renewal processing team ready - January staffing plan signed, training done, day-1 queue rehearsed
GNG-1 | T-15 | Start the production pre-load | 8 | No open Critical issue of the migration or of a Day-1 module
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 1 | Reference data and clients loaded and accepted (G6) in production; daily deltas running
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 2 | Client review queue empty
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 3 | Final extract jobs timed within the window (dry run)
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 4 | In-flight items and remittance batches closed or listed for carry-forward
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 5 | P01 dry run covers every expiry to 31 May 2028 and every renewal term booked in legacy starting on or after T
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 6 | Draft RA-sent file validated; its rejects reviewed by the Renewal processing team
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 7 | Comptrollership access list for the legacy GL after the freeze named
GNG-2 | T-5 | Enter the legacy freeze on T-3 | 8 | Communications sent; branches and insurers informed
GNG-3 | T-1 18:00 | Go live on T | 1 | Every Day-1 object at G6 (100 percent)
GNG-3 | T-1 18:00 | Go live on T | 2 | Counts - received = control and loaded + skipped + rejected + excluded = staged, for every object
GNG-3 | T-1 18:00 | Go live on T | 3 | Financial rejects (F01, F02, G01) - 0, or each excluded item approved by the owner with a manual-entry plan
GNG-3 | T-1 18:00 | Go live on T | 4 | Amount reconciliation of open items, UPP and trial balance - 0.00 difference per currency
GNG-3 | T-1 18:00 | Go live on T | 5 | Migration Clearing - 0.00 per branch and currency
GNG-3 | T-1 18:00 | Go live on T | 6 | Legacy control accounts equal their sub-ledgers (ACSL, context LEGACY) - 0.00
GNG-3 | T-1 18:00 | Go live on T | 7 | Client review queue empty; screening run complete
GNG-3 | T-1 18:00 | Go live on T | 8 | Business smoke test passed
GNG-3 | T-1 18:00 | Go live on T | 9 | Rollback point (snapshot) taken and verified
GNG-3 | T-1 18:00 | Go live on T | 10 | Hypercare roster and support channels in place
GNG-3 | T-1 18:00 | Go live on T | 11 | Preliminary December TB signed as the provisional opening; legacy GL restricted to the named FY2027 adjustment users
GNG-3 | T-1 18:00 | Go live on T | 12 | Headers of every expiry to 31 May 2028 loaded; RA-sent file loaded; Renewal January staffing plan confirmed
POINT OF NO RETURN | T 18:00 | Continue in BIBS; fallback to legacy no longer offered (DMQ32) | 1 | No Critical issue that stops receipts, payment application, remittance or booking
POINT OF NO RETURN | T 18:00 | Continue in BIBS; fallback to legacy no longer offered (DMQ32) | 2 | Migration Clearing still 0.00; no posting in legacy since the freeze
POINT OF NO RETURN | T 18:00 | Continue in BIBS; fallback to legacy no longer offered (DMQ32) | 3 | Every branch has transacted in BIBS
TRUE-UP CLOSED | T+120 | Close the FY2027 true-ups | 1 | Final true-up reconciled to the audited FY2027 TB and signed by the Head of Comptrollership
TRUE-UP CLOSED | T+120 | Close the FY2027 true-ups | 2 | Legacy GL locked for all users; FY2027 adjustment register closed
TRUE-UP CLOSED | T+120 | Close the FY2027 true-ups | 3 | Migration Clearing 0.00 and legacy control accounts equal their sub-ledgers after the final true-up
TRUE-UP CLOSED | T+120 | Close the FY2027 true-ups | 4 | Opening journals no longer marked PROVISIONAL

## Freeze Windows
Freeze Windows
Freeze windows
Freeze | From | Until | Scope | Exception route
Reference data | T-7 (map freeze) | Go-live | Insurers, products, risk codes, packages, AOs, branches, LOVs in EBIX and QPS | Change request approved by the data owner; new code map version; delta load of R objects
Client master | T-3 22:00 (last delta) | Go-live | New and changed clients in QPS / EBIX / CMS | None after the freeze; changes keyed in BIBS after go-live
Business transactions | T-3 22:00 (after the last legacy EOD) | Go-live | All postings of the business modules of EBIX, QPS, CMS - bookings, receipts, UPP, dispositions, remittances, endorsements; GL journals other than the FY2027 adjustments | None; an urgent item is recorded on paper and keyed in BIBS on T
Legacy GL (FY2027 adjustments) | T-3 22:00 | Legacy GL lock (T+106) | Only FY2027 closing and audit adjustments, by the Comptrollership users on the signed access list; FY2028 periods never opened in legacy; no new business | Each journal in the FY2027 adjustment register; it reaches BIBS in the next true-up
BIBS configuration | T-2 00:00 | T+3 | Parameters, accounting rules, code maps, workflows in production | Emergency change approved by the go / no-go board
BIBS releases | T-7 | T+14 | Deployments to production | Hotfix of a Critical issue approved by the go / no-go board

## Rollback
Rollback
Rollback procedure (only on NO-GO or before the point of no return)
Step | Name | Action | Owner | Done at
RB-1 | Stop | The go / no-go board records NO-GO (or a failure before T 18:00 that the board judges unrecoverable). The Program Manager announces the rollback on the bridge. | GNG
RB-2 | Lock BIBS | Disable business logins to BIBS; stop the scheduled jobs (PAYMENT_AUTOMATCH, payment file handlers, Renewal extraction, e-mail dispatch). | IDO
RB-3 | Capture | If business transactions were keyed in BIBS after 08:00 on T, export them (receipts, applications, bookings) with MIG-CUTOVER-STATUS and the Operations reports for re-keying in legacy. | IML
RB-4 | Restore | Restore the production database to the rollback-point snapshot (CT-037); restore the object store for attachments of the same time; verify the restore (row counts of key tables, application start). | IDO
RB-5 | Reopen legacy | Set EBIX, QPS and CMS back to read-write; lift the GL restriction; re-enable the legacy batch jobs; confirm the last legacy EOD is intact. | BIT
RB-6 | Re-key | Operations re-keys in legacy the transactions captured in RB-3, with the BIBS AR numbers voided in the receipt register. | OPS
RB-7 | Communicate | Send the rollback notice to users, branches, insurers and bank channels (communication plan item 7). | PM
RB-8 | Review | Within 2 business days - root cause, new go-live date, which trial migrations to repeat; purge the production staging of the failed cutover within 5 days. | PM

## Communication
Communication
Communication plan
# | Message | Audience | Channel | When | Owner | Sent on
1 | Go-live date, freeze and what changes for each department | All BDOI users, branch heads | E-mail from the Program Manager; team briefings | T-21 | PM
2 | Payments after go-live - legacy invoice numbers stay valid; new invoices are BI- numbers | Insurers, BDO bank channels (bills payment, CLPC, direct credit), corporate clients | Letter / e-mail from Operations | T-21 | OPS
3 | Freeze of reference data and the change request route | Product, Marketing and Operations maintainers | E-mail from the Data Migration Lead | T-8 | DML
4 | Training schedule and log-in instructions | All BIBS users per persona | E-mail; training calendar | T-20 | PM
5 | Renewals of the January-May 2028 expiries are processed in BIBS from go-live, January expiries first; RAs already sent are not sent again; RAs sent up to 29 December go in the trackers | Renewal processing team, Retail and Corporate Marketing, branches | E-mail from the Head of the Renewal processing team; team briefing | T-21 | RNW
6 | Legacy GL after the freeze - FY2027 closing and audit adjustments only, by named users; true-up timetable to April 2028 | Comptrollership, external auditor, BDOI IT | Memo from the Head of Comptrollership | T-21 | COMP
7 | Last legacy business day T-5 (29 December); legacy freeze at T-3 22:00; BIBS opens T 08:00; what to do with urgent items over the holidays | All users, branches, insurers | E-mail; branch notice | T-5 | PM
8 | Go-live confirmed; support channels and hypercare contacts | All users | E-mail; intranet | T-1 19:00 | PM
9 | Rollback notice (only if NO-GO) - legacy stays in use; next steps | All users, branches, insurers, bank channels | E-mail; phone tree for branch heads | T-1 on NO-GO | PM
10 | Daily hypercare status | Go / no-go board, department heads | Daily report and bridge call 17:00 | T to hypercare exit | IPM
11 | Hypercare exit and hand-over to production support | All users, IT | E-mail | At exit | PM
12 | True-ups closed; legacy GL locked | Comptrollership, external auditor, Program Manager | Memo | T+120 | COMP

## Hypercare Roster
Hypercare Roster
Hypercare roster
Function | Who | Coverage | Escalates to | Names and phone (to fill)
Command centre lead | iorta TechNXT Project Manager | 07:00-20:00 T to T+5; 08:00-18:00 after | Program Manager
Migration and reconciliation | iorta Migration Lead; Migration Operator | 07:00-22:00 T to T+5; business hours after | iorta Project Manager
Application support (L2 / L3) | iorta developers - Operations, Accounting, CRM, Renewal | 07:00-20:00 T to T+5; on call to 22:00 | iorta Project Manager
Infrastructure | iorta DevOps | 24 x 7 on call T-3 to T+5; business hours after | iorta Project Manager
Business floor support | BDOI super-users per department (Cashiering, Remittance, Collections, Accounting, Marketing) | Branch hours T to T+10 | Data Migration Lead
Comptrollership | Reconciliation approver; GL lead | Daily 16:00 check T to first month-end; true-ups T+15 to T+120 | Head, Comptrollership
Renewal processing team | Head of the Renewal processing team; makers and checkers | 08:00-20:00 T to T+10 on the day-1 queue; P03 resubmissions on T-2 and T-1 | Program Manager
Legacy systems | BDOI IT legacy administrator | Business hours; on call T-3 to T+1 | BDOI IT head
Service desk (L1) | BDOI service desk | Service hours | BDOI IT head

## Hypercare Exit
Hypercare Exit
Hypercare exit criteria
# | Exit criterion | Met | Evidence
1 | No open Critical or High issue; Medium issues have an agreed fix date
2 | Migration Clearing 0.00 and legacy control accounts equal their sub-ledgers on 10 consecutive business days
3 | First month-end close completed with the ACSL GL-SL reconciliation (context LEGACY) without difference
4 | Payment files, automatch, remittance, DPPR / PR2307 batches and endorsements on legacy invoices each processed at least once in production without incident
5 | Staging and extract files of production purged within 5 days of sign-off (purge log)
6 | True-up 1 posted, reconciled and signed
7 | Every URGENT January renewal has an RA sent or an insurer request made
8 | Service desk ticket volume back to the level agreed in the support model; production support runbook (deliverable 24) accepted

## Decommissioning
Decommissioning
Decommissioning checklist per legacy system (BRID 12.1; DMQ27)
Legacy system | # | Criterion | Evidence | Signed by / date | Status
EBIX | 1 | Final extracts reconciled - F01, F02, F03, F04, F06, G01 and C01 signed off |  |  | OPEN
EBIX | 2 | Final true-up reconciled - final true-up signed against the audited FY2027 TB; legacy GL locked |  |  | OPEN
EBIX | 3 | Archive reconciled - archive objects H01, H02 and G02 of EBIX loaded and reconciled (counts and hash totals per record type against legacy) |  |  | OPEN
EBIX | 4 | Legacy Inquiry verified - by Audit / Compliance on samples of each record type |  |  | OPEN
EBIX | 5 | No open item needs the system - no open legacy invoice or legacy UPP needs an EBIX document; the legacy context in BIBS may still be open |  |  | OPEN
EBIX | 6 | Claims tail covered - no open claim that needs EBIX (DMQ27, DMQ30) |  |  | OPEN
EBIX | 7 | Access logs archived - read-only access logs exported to the archive |  |  | OPEN
EBIX | 8 | Retention covered - database backup retained per the retention decision (DMQ27); retention obligations covered (5 years online, 15 years archive, umbrella p.45) |  |  | OPEN
EBIX | 9 | Owners signed - EBIX system owner, Compliance and Comptrollership |  |  | OPEN
QPS | 1 | Final extracts reconciled - C01, P01, P03 and the R objects signed off |  |  | OPEN
QPS | 2 | No open item needs the system - last QPS-issued policy expired and its renewal decided (run-off tracker shows no open cohort), or the policy is archived |  |  | OPEN
QPS | 3 | Archive reconciled - archive objects of QPS loaded and reconciled |  |  | OPEN
QPS | 4 | Legacy Inquiry verified - by Audit / Compliance |  |  | OPEN
QPS | 5 | Access logs archived - read-only access logs exported to the archive |  |  | OPEN
QPS | 6 | Retention covered - database backup retained per DMQ27 |  |  | OPEN
QPS | 7 | Owners signed - QPS system owner, Compliance and the Heads of Marketing |  |  | OPEN
ISYS | 1 | No open item needs the system - claims and ACSL reports and the Marketing Diary replaced by BIBS reports |  |  | OPEN
ISYS | 2 | Archive reconciled - GL history (G02) and closed claims (H01 CLAIM) archived and reconciled |  |  | OPEN
ISYS | 3 | Final true-up reconciled - ISYS GL lines of the final true-up signed; ISYS GL locked |  |  | OPEN
ISYS | 4 | Owners signed - ISYS system owner, Claims and Comptrollership |  |  | OPEN
CMS | 1 | Final extracts reconciled - collection state F03 and UPP F02 reconciled and signed off |  |  | OPEN
CMS | 2 | Archive reconciled - disposition history archived (H01) if required by DMQ34 |  |  | OPEN
CMS | 3 | Owners signed - Head of Operations (Collections) and BDOI IT |  |  | OPEN
Excel masterlists and file shares | 1 | Final extracts reconciled - submitted-policy masterlists migrated (P04) or archived |  |  | OPEN
Excel masterlists and file shares | 2 | Archive reconciled - KYC documents and legacy documents (C04, H02) archived with checksums |  |  | OPEN
Excel masterlists and file shares | 3 | Retention covered - folders set to read-only, then removed per the retention decision |  |  | OPEN
Excel masterlists and file shares | 4 | Owners signed - owning department and Compliance |  |  | OPEN
Legacy context in BIBS | 1 | No open legacy invoice - every legacy invoice paid, reversed, written off or reclassified |  |  | OPEN
Legacy context in BIBS | 2 | No legacy UPP balance - every legacy UPP applied, refunded or reclassified |  |  | OPEN
Legacy context in BIBS | 3 | Legacy accounts at zero - legacy control accounts and Migration Clearing at 0.00 |  |  | OPEN
Legacy context in BIBS | 4 | Chart decision recorded - Comptrollership decides whether the legacy accounts are closed in the chart |  |  | OPEN

## _lists (hidden)
NOT STARTED | Y | Y | OPEN
IN PROGRESS | N | N | DONE
DONE |  |  | N/A
BLOCKED
N/A